## The Hypocrite mktg plan
The Hypocrite |  |  |  | current
new
USPs | Target audiences |  |  | all
Richard Bean (award wining, One Man Two Guvnors, Hull) | classic drama
Mark Addy (local, Game of Thrones, Full Monty) | Richard Bean audiences
Caroline Quentin (Men Behaving Badly, Jonathan Creek) | comedy
RSC (International reputation, quality) | schools
Ambition & scale | HU postcodes
Hull cast members | commuterland culturebuffs
Local history (Hotham, Beverley Gate etc) | culturally engaged audiences beyond 30 minute drivetime (Leeds, Sheffield, York)
First show of Year of Exceptional Drama 2017 | HU6 and HU3 - Community Dialogues
stakeholders - local and industry
Activity | Notes | Timing | Staff | Target Aud. | Cost |  |  | % of investment
Design | [6 empty] | Design | 70%
show artwork |  | 2016-08-01 | RP | all | 2220
show artwork redesign | with Mark Addy | 2017-11-01 | RP | all | 900
general design | advertising, web banner etc |  | RP | all | 806
Print | [6 empty] | Print | 10%
Double page spread in season brochure | 29,000 printed, distributed locally to businesses and regionally to arts venues | 2016-11-01 | RP/EL | current | n/a
A0, A3 posters and A5 flyers | Displayed FOH and distribution to local businesses and postcodes - see distribution plan | 2016-11-01 | EL | new | 314
Reprint | with Mark Addy artwork | 2016-12-01 | EL | new
Exit flyering | Treasure Island, Bromance | 2016-12-01 | EL | current | n/a
Show programme | 3,500 copies | 2017-02-01 | EL | current
Programme editorial | commissioned editorial | 2017-01-01 | EL | current
Over door banner |  | 2017-01-01 | EL | all | 240
Flyering
Poster site in St Stephens
Pop-up banner
Print distribution to hotels | posters and flyers | 2017-01-01 | DM | new | n/a
Foyer display | rehearsal and production shots | 2017-02-01 | SH | current | n/a
Direct Mail
Season brochure | 19,600 mailed |  |  |  | n/a
Direct mail
Advertising | [6 empty] | Advertising | 6%
HDM | full page on sale advert, for launch on 22 Sept | September | RP | all | n/a | Hull2017 paying
LOCO Mag | full page advert & full page editorial | Jan | RP | all | 350
Press
Hull2017 launch | international, national, regional and local media, event held at HTT | 2016-09-01 | RP | new | n/a
HTT season launch | national, regional and local media release | 2016-11-01 | VT | all | n/a
Press & guest night 1 Mar | run in partnership with RSC | 2017-03-01 | VT | current | n/a
Guest night 7 Mar |  | 2017-03-01 | VT | current | n/a
See separate press plan | delivered in partnership with RSC & Cornershop | Sept 16 onwards | VT | all
Photography & Filming | [6 empty] | Photography & filming | 9%
Mark Addy reshoot | Karl Andre & make up artist | 2016-11-01 | RP | new | 245
Costume hire for MA photoshoot | Bristol Costume Hire and Birmingham Costume Hire | 2016-11-01 | RP | new | 171.21
Holy Apostles photography | Chris Pepper - before & after pics | Nov onwards | VT | all | 75
Rehearsal photography |  | 2017-02-01 | VT | all | n/a | RSC paying
Production photography |  | 2017-02-01 | VT | all | n/a | RSC paying
EPK filming | RSC | 2017-03-01 | RP / VT |  | n/a | RSC paying
Synopsis interview | Richard Bean | Jan/Feb | VT | new
Production trailer |  | Feb/Mar | VT | all
Vox pops |  | Mar | VT | all
Social Media | [6 empty] | Social Media | 1%
Fb advertising & boosted posts |  | Feb/Mar | VT | new | 50
Facebook, Twitter, Instagram posts | ongoing | Feb / Mar 17 | VT | new | n/a
Website & E-marketing
Content rich show page, incl. prod shots, trailer etc |  | 2016-09-01 | EL | current | n/a | from central budget
Cast announcement | to whole list | 2016-11-01 | EL | current | n/a | from central budget
Season launch eshot | to whole list | 2016-11-01 | EL | current | n/a | from central budget
February What's On | to whole list | 2017-01-01 | EL | current | n/a | from central budget
Rehearsal eshot | targeted to bookers | 2017-02-01 | EL | current | n/a | from central budget
Production shots & press e-shot | targeted to bookers
Trailer & production pics eshot | to whole list |  |  | current | n/a
Vox pops eshot | to targetted list of almost-bookers |  |  | current | n/a
Schools and groups
Schools letter
Schools calls
Discover Day for Schools | delivered and promoted by Hull 2017 | 2017-01-01 |  | new | n/a
Other | [6 empty] | Other | 4%
Hotel and ticket package
Production meeting in London | travel for RP | 2016-06-01 | RP |  | 125
Press night accommodation | hotel room | 2017-04-01 | RP |  | 67.5
RSC Hull meeting | hospitality | 2016-02-01 | RP |  | 27.45
Themed menu |  | Feb/Mar 17 | HOST | current | n/a
Guest night for customer serving staff
Purple Seven survey | Did You Enjoy That? | Feb /Mar 17 | RP / SH | current | n/a
Post Show Q&A | promote opportunity for discussion with artistic team
Foyer exhibition | in partnerhsip with History Centre | Feb /Mar 17 | RP |  | n/a
Hull Uni alumni event |  | 2017-03-01 | DM |  | n/a
|  |  |  | Total | 5591.16
Indicates activity planned but not completed due to sell out show.

## Sheet1
Activity | Budget | Timing | Responsibility
Design of Pay What You Can flyers | 100 | Sept | RP
Printing of PWYC flyers (5,000) | 275 | Sept | RP
PWYC flyer distribution - Hessle Road | 104 | Sept | RP - using internal distributors
PWYC flyer distribution - Hessle |  | Sept | PB - using Browns
2 days telesales support for schools calls |  | Sept | PB - in kind
Advance trailer | 725 | Sept | RP - using Josh?
Vox pops on press night | 240 | 2015-10-06 | RP - using Josh?
Production trailer | 450 | Oct | RP - using Josh?
Digital advertising (incl ad creation) |  | Sept/Oct | PB - internal, in kind?
Beermats |  | Sept / Oct | PB
1894
CBBC activity |  | Oct | RP / PB - for Sleeping Beauty
Note on B7: Ruth Puckering: Based on JayJay Media quote
Note on B8: Ruth Puckering: Based on JayJay Media quote
Note on B9: Ruth Puckering: Based on JayJay Media quote