## Workstreams
Time | Work Streams
| PM | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 | Team 10 | Team 11 | Team 12 | Team 13 | Team 14 | Team 15
|  | Projection Team | Cleansing Team | Security and Crowd Controlat QVS | Cranes | Supports | Police Escort | Blade | Signals Gang | A63 Lighting Gang | Hull City Center Lighting Gang | Traffic Management | Press | Volunteer Parade | Refreshments (example- needs adding) | Assumptions
|  |  |  | Hull CC 2017 | ALE | Pearl Green | PC Darren Storr | ALE
21:00 |  | Team 1: Event Finishes; Team 3: Meet at Docks for Safety & team briefing
21:10
21:20
21:30 |  | Team 3: Set out to QVS; Team 4: Meet at Docks for Safety & team briefing; Team 5: Meet at Docks for Safety & team briefing; Team 15: Assume the safety and team briefings will be done within 30mins- can give 1 hour as a buffer.
21:40
21:50
22:00 | Aquire QVS- set up crowd control | Team 1: Designated area around Monument for derigging; Team 2: Start cleaning area ready for blade installation; Team 3: Set up fencing around QVS; Team 4: Set off to QVS; Team 5: Supports and all materials loaded onto transport; Team 14: Team 3 on rolling breaks; Team 15: Assume it takes cranes/ lorries 30mins to travel from the docks to QVS.
22:10
22:20
22:30 |  | Team 4: Arrive at QVS; Team 8: Meet at Docks for Safety & team briefing; Team 9: Meet at Docks for Safety & team briefing; Team 11: Meet at Docks for Safety & team briefing
22:40
22:50 | Cranes at QVS | Team 15: Assume QVS is secure within 50mins of starting to put barriers up
23:00 |  | Team 2: Leave QVS; Team 4: Start setting up at QVS; Team 5: Set off to QVS; Team 8: Start prepping A63 route; Team 9: Start prepping A63 route
23:10
23:20
23:30 | Supports at QVS | Team 5: Arrive at QVS
23:40
23:50
0:00 | Tip support offloaded | Team 4: Offload tip support to correct position; Team 5: Offload tip support to correct position; Team 7: Meet at docks for safety and team briefing
0:10
0:20
0:30 |  | Team 5: Start drilling holes for tip support; Team 7: Blade loaded onto transport system; Team 10: Meet at Docks for Safety & team briefing; Team 14: Team 4 on break; Team 15: Assume Pearl Green able to drill holes for supports
0:40 |  | Team 15: Assume Pearl Green able to drill holes for supports
0:50
1:00 |  | Team 6: Meet at docks for safety and team briefing; Team 8: Finish prepping A63 route; Team 10: Start prepping Hull City Center route
1:10
1:20
1:30 |  | Team 8: Start prepping Hull City Center route
1:40
1:50
2:00 | Blade sets off from Alexander Docks | Team 6: Set off from Alexander Docks to QVS; Team 7: Blade sets off from Alexander Docks
2:10
2:20
2:30
2:40
2:50
3:00 | QVS - full posession | Team 1: Leave QVS; Team 3: QVS - full posession; Team 9: Finish prepping A63 route; Team 14: Team 4 finish break; Team 9 on break; Team 15: Assume projection team needs 5 hours for derigging
3:10
3:20
3:30 | Root support offloaded | Team 4: Lift root support into place; Team 5: Lift root support into place
3:40
3:50 |  | Team 5: Finish drilling holes for tip support
4:00 | Blade leaves A63 | Team 5: Start drilling holes for root support; Team 6: Blade off A63- vigilant of public; Team 7: Blade off A63 & arrives at Market Place; Team 9: Start reinstating A63; Team 14: Team 6 & 7 on break; Team 9 off break
4:10
4:20
4:30 |  | Team 5: Start bolting down tip support
4:40
4:50
5:00 | Blade leaves Market Place | Team 7: Blade leaves Market Place; Team 8: Finish prepping Hull City Center route; Team 10: Finish prepping Hull City Center route; Team 14: Team 6 & 7 finish break
5:10 |  | Team 5: Start loading on concrete ballast for tip support
5:20
5:30
5:40 | Hand A63 to Highways England for inspection | Team 9: Finish reinstating A63
5:50
6:00 | A63 is reopened to public. Tip support is secure | Team 5: Tip support is secure; Team 13: Joins blade upto Saville Street?; Team 14: Team 4 & 5 on break
6:10
6:20
6:30 |  | Team 3: Close off roads to ensure that no vehicles pass on Carr lane and under any lifting operations
6:40
6:50
7:00 | Blade arrives at Saville Street | Team 3: Be vigilant of anyone attempting to enter square; Team 6: Blade arrives at Saville Street; Team 7: Blade arrives at Saville Street; Team 13: Watch blade from City Hall?
7:10
7:20
7:30 | Blade manouvered into QVS | Team 5: Lift root support into place; Team 6: Blade manouvered onto QVS- ready for lifting; Team 7: Blade manouvered onto QVS- ready for lifting; Team 14: Team 4 & 5 off break
7:40
7:50 |  | Team 5: Bolt down support through pre-drilled holes
8:00
8:10
8:20
8:30 |  | Team 5: Load on concrete ballast
8:40
8:50
9:00 | Lift Blade onto supports | Team 4: Lift Blade onto supports; Team 7: Lift Blade onto supports
9:10
9:20
9:30
9:40
9:50
10:00 |  | Team 5: Check that the blade is securely fastened; Team 7: Ensure blade is secured
10:10
10:20
10:30 |  | Team 4: Crane start derigging
10:40
10:50
11:00
11:10
11:20 |  | Team 4: Cranes leave QVS
11:30 | Start packing away crowd control measures | Team 3: Start packing away crowd control measures
11:40
11:50
12:00
12:10
12:20
12:30 | Hand QVS over to Hull City Council
12:40
12:50
13:00
Note on E5: Milly Hennayake: Could meet at QVS? But need to transport barriers too
Note on J3: Milly Hennayake: No information on exact scope of work/ timings for both sections and order of works- therefore needs work
Note on K3: Milly Hennayake: Waiting on NM information on time per turn and order
Note on L3: Milly Hennayake: Waiting on NM information on time per turn and order
Note on M3: Milly Hennayake: Will be determined depending on works of teams 9, 10 & 11.
Note on N3: Milly Hennayake: Need to sort out press- 1 vehicle with camera man and video?