MADE IN HULL 2017

BUILD & BREAK

PHASED PLAN

CONTENTS

| Page 3 | Overview |
| --- | --- |
| Page 4 | Core Operations Team |
| Page 5 - 12 | Schedule Breakdown - Build |
| Page 13 | Rehearsal Days - 29/12/16 - 30/12/16 |
| Page 14 | Show Days 01/01/17 - 07/01/17 |
| Page 15 - 18 | Schedule Breakdown - Break - 07/01/17 |
| Page 19 | Appendices |
| Page 20 | Appendix 1 - Show Plans |
| Page 21 | Appendix 2.1 QVS Show Plan |
| Page 22 | Appendix 2.2 Underpass Show Plan |
| Page 23 | Appendix 2.3 The Deep Show Plan |
| Page 24 | Appendix 2.4 Zebedees Yard Show Plan |
| Page 25 | Appendix 2.5 Scale Lane Staith Show Plan |
| Page 26 | Appendix 3 - Structural Drawings |
| Page 27 | Appendix 3.1 QVS Projection Platforms |
| Page 28 | Appendix 3.2 QVS Front of House Tower |
| Page 29 | Appendix 3.3 QVS Projection Tower |
| Page 30 | Appendix 3.4 QVS Cable Pylon |
| Page 31 | Appendix 3.5 Zebedees Yard Lighting Tower |
| Page 32 | Appendix 3.6 C4DI (The Deep) Projection Platform |
| Page 33 | Appendix 3.7 Underpass Screen Support Small |
| Page 34 | Appendix 3.8 Underpass Screen Support Large |
| Page 35 | Appendix 4 - Hull Production Suppliers |
| Page 36 | Appendix 5 - Plant Schedule |
| Page 37 | Appendix 5 - Plant Schedule continued |

OVERVIEW

The purpose of this document is to provide a brief for Hull city council and individual venues with a brief guide to the production schedule for the build and de-rig of Made In Hull; the launch event for Hull 2017.

Should there be any queries on the contents of this brief, please direct all correspondence through Chris Clay in the first instance to be directed to the person(s) responsible for the area with which the matter concerns.

To accompany the brief there are also appendices outlining:- plant movement, temporary structure drawings, site plans & plant working zones to be referenced at will. We have also drawn up technical production information packs for each venue, detailing specific technical specifications. These are available at request.

CORE OPERATIONS TEAM

SCHEDULE BREAKDOWN

APPENDICES

APPENDIX 1 – SHOW PLANS

APPENDIX 2.1 QVS PHASE PLANS

APPENDIX 2.2 UNDERPASS SHOW PLAN

APPENDIX 2.3 THE DEEP SHOW PLAN

APPENDIX 2.4 ZEBEDEES YARD SHOW PLAN

APPENDIX 2.5 SCALE LANE STAITH SHOW PLAN

APPENDIX 3 – STRUCTURAL DRAWINGS

APPENDIX 3.1 QVS PROJECTION PLATFORMS

APPENDIX 3.2 QVS FRONT OF HOUSE TOWER

APPENDIX 3.3 QVS PROJECTION TOWER

APPENDIX 3.4 QVS CABLE PYLON

APPENDIX 3.5 ZEBEDEES YARD LIGHTING TOWER

APPENDIX 3.6 C4DI (THE DEEP) PROJECTION PLATFORM

APPENDIX 3.7 UNDERPASS SCREEN SUPPORT SMALL

APPENDIX 3.8 UNDERPASS SCREEN SUPPORT LARGE

APPENDIX 4

| HULL - PRODUCTION SUPPLIERS |  |  |
| --- | --- | --- |
| ROLE | COMPANY | SITE CONTACT |
| AUDIO | Tube | Melv Coote |
| LIGHTING | DBN | Nick Walton |
| PROJECTION & VIDEO | Bluman Associates | Simon Hudson |
| STRUCTURES & RIGGING | Star Events | Pete Holdich |
| POWER | Midas | David Noble |

APPENDIX 5 – PLANT SCHEDULE

| DATE | DEPARTMENT | ACTIVITY | LOCATION | PLANT REQUIRED | REQUIRED FROM | REQUIRED UNTIL |
| --- | --- | --- | --- | --- | --- | --- |
| 19/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 19/12/2016 | STAR EVENTS | TRUCK CROSSLOADING | BONEYARD | 926 | 11:00 | 12:00 |
| 19/12/2016 | STAR EVENTS | TRUCK UNLOADING | SLS | 7M | 13:00 | 16:00 |
| 19/12/2016 | STAR EVENTS | TRUCK UNLOADING | QVS | 7M | 19:00 | 20:00 |
| 20/12/2016 | STAR EVENTS | TRUCK UNLOADING | QVS | 7M | ALL DAY | ALL DAY |
| 20/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 21/12/2016 | PRODUCTION | WINDOW SCREENING | QVS | TRUCK MOUNT | ALL DAY | ALL DAY |
| 21/12/2016 | STAR EVENTS | TRUCK UNLOADING | QVS | 7M | ALL DAY | ALL DAY |
| 21/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 22/12/2016 | TUBE | CABLE INSTALL | QVS | 17MW/BASKET | 08:00 | 18:00 |
| 22/12/2016 | STAR EVENTS | TRUCK UNLOADING | ZEBEDEE'S YARD | 7M | 08:00 | 13:00 |
| 22/12/2016 | STAR EVENTS | TRUCK CROSSLOADING | BONEYARD | 926 | 18:00 | 18:30 |
| 22/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 23/12/2016 | STAR EVENTS | RIGGING INSTALL | UNDERPASS | 17MW/BASKET | 08:00 | 13:00 |
| 23/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 27/12/2016 | BLUMAN | PROJECTOR INSTALL | UNDERPASS | 17MW/BASKET | 12:00 | 16:00 |
| 27/12/2016 | BLUMAN | PROJECTOR INSTALL | SLS | 7M | 12:00 | 16:00 |
| 27/12/2016 | DBN | LX INSTALL | ZEBEDEE'S YARD | 60'PICKER | 13:00 | 19:00 |
| 27/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 28/12/2016 | TUBE | AUDIO INSTALL | THE DEEP | 7M | 08:00 | 10:00 |
| 28/12/2016 | DBN | LX INSTALL | UNDERPASS | 17MW/BASKET | 14:00 | 19:00 |
| 28/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 29/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 30/12/2016 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 07/12/2016 | ALL | TRUCK LOADING | QVS | 7M&17M | 21:00 | 04:00 |
| 08/02/2017 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 08/02/2017 | BLUMAN | PROJECTOR DERIG | UNDERPASS | 17MW/BASKET | 09:00 | 11:00 |
| 08/02/2017 | DBN | LX DERIG | UNDERPASS | 60'PICKER | 09:00 | 11:00 |
| 08/02/2017 | TUBE | AUDIO DERIG | THE DEEP | 7M | 09:00 | 11:00 |
| 08/02/2017 | BLUMAN | PROJECTOR DERIG | SLS | 7M | 11:00 | 13:00 |
| 08/02/2017 | STAR EVENTS | TRUCK LOADING | SLS | 7M | 11:00 | 13:00 |
| 08/02/2017 | DBN | LX DERIG | ZEBEDEE'S YARD | 60'PICKER | 11:00 | 13:00 |
| 09/02/2017 | STAR EVENTS | TRUCK LOADING | ZEBEDEE'S YARD | 7M | 08:00 | 14:00 |
| 09/02/2017 | STAR EVENTS | PA TOWER DERIG | QVS | 7M | 14:00 | 17:00 |
| 09/02/2017 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |
| 10/02/2017 | SITE & PRODUCTION | TRUCK UNLOADING & CROSSLOADING | BONEYARD | 926 | ALL DAY | ALL DAY |