## Summary
Artist | Accomod. booked | Budget confirmed | Budget totals | PLI received | Dates confirmed | Contract sent | Contract signed | PO sent | 1st invoice | Locations confirmed | Volunteer requirements | Update report sent | 2nd invoice | 3rd invoice | M&E update
Davy & Kristin McGuire | 2016-06-21 | 2016-07-05 | 18658.5 | 2016-07-31 | 2016-06-29 | 2016-06-27 | 2016-07-05 | 2016-07-11 | 2016-07-11 | 2016-07-05 | 8 volunteers 9-12 Sept. 7:30-11:30pm
Aswarm | 2016-08-04 | 2016-07-14 | 18831 |  | 2016-07-15 | 2016-06-29 | 2016-08-08 | 2016-08-10 | 2016-08-11 | 2016-05-20 | 24-28 Aug & 9-12 Sept 2 volunteers each day
Periplum | 2016-08-05 | 2016-07-14 | 17687 |  |  | 2016-06-29 | 2016-07-14 | 2016-07-22 | 2016-07-22 | 2016-08-03 | TBD
Scottee | 2016-07-25 | 2016-07-14 | 19486.57 | 2016-08-03 | 2016-07-06 | 2016-06-23 | 2016-08-08 | 2016-08-08 | 2016-08-10 | 2016-08-08 | None | 3 Aug draft | 2016-08-16
Joshua Sofaer | 2016-06-27 | 2016-06-10 | 18933.72 | 2016-07-05 | 2016-06-27 | 2016-06-23 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-08 | 28-30 Aug: 1 to install set. 31-5 Sept 2 to welcome | 2016-07-21 | 2016-07-22
Dominic Wilcox |  | 2016-07-14 | 17260 | 2016-08-11 |  | 2016-06-29 |  |  |  | 2016-07-28 | None | 9 Aug draft
Lone Twin | 2016-07-29 | 2016-07-14 | 18973.2 |  | 2016-07-29 | 2016-06-29 | 2016-07-25 | 2016-08-01 | 2016-07-29 | 2016-07-06 | 1-11 Sept: 2 volunteers per day
|  | commission budget total | 129829.99
|  | Venue (contingency) | 10170.01
|  | Overall budget total | 140000

## LONE TWIN
LOGG 2016 ARTIST | LONE TWIN
Area of Hull | Longhill
Site Visit/s dates/times | 4th August
Workshop/other dates/times | n/a
Delivery dates/Times | 25th August to 3rd September (requested delay to start to avoid clash with other projects)
Budget agreed | Yes
Invoice received | see summary
Contract signed | yes
Highlighted to ESAG | on August 11th
Framework doc agreed | Template sent
Concept/Creative matters
Locations used | St Margaret's Welcome Centre or East Mount Community Centre (see below)
Licensing/TEN | Unlikely required - chekcing with licensing
Permissions/Consent | They do ask participants to sign a waiver in advance regarding recording
PRS / PPL required | n/a
Venue agreement | Either St Margaret's or East Mount Community Centre as a project hub to be set after site visit. Venue agreement required between artist and venue
H & S matters | Unaccompanied performer in a suit - is it breatheable? Audio equipment within suit hazardous? Will tripping hazards be visible to the performer from within the suit?
Enviro Health matters | n/a
Staffing matters | will the Visitor be accompanied at all times? Yes, by local community member…
Volunteer request | request for 2 local volunteers in case local knowledge required. Sue Nicholson is a Pioneer from Longhill - 07834727438 - speak to Harriet/Shaun?
Volunteer needs | Potentially pack lunches and coffee/tea/water/biscuits. Break space can be located in community space with artists
Security matters | Exhibition space need to be invigilated?
Equipment matters | Suit, recording device, exhibition materials and space, etc.
Power/light/matters | self-contained costume. Will they need support in the community centre?
Access matters | aiming to include disabled person as participant with Visitor
Access Guide sent | Sent 26 July
Safeguarding matters | for recording, waiver required. Visitor is never alone with a child. Protocols in place. Need to determine balance of organised vs random schedule? Signage around Longhill?!
DBS docs checked | N/A?
Environmental matters | N/A
Audience control matters | N/A - the Visitor will be shadowing one person/family at a time. Potential exhibition space will unlikely be highly crowded as the locations are low-key.
Emergency concerns | Costume is not flammable
Insurance checked | Not yet.
Timeline okay | Yes
RA's checked | not yet
Marketing matters | No marketing required
M & E notes | Artists will be documenting using sound recording, video and photography all resulting in an exhibition. Ie the project itself is a form of evaluation.
Blog started by artist | Not yet.
Other detail required
Shared Artists Unit | Not required by the company
Key contacts for project | Karen Okra link with Longhill, Trisha (St Margaret's Welcome Centre)
Production Manager notes | H&S/safeguarding issues need sorting re: suit, loneworking, voice recording, etc. , paperwork, comms (us), venue permissions, exhibition install, volunteers.

## SCOTTEE
LOGG 2016 ARTIST | SCOTTEE
Area of Hull | East, 362 Holderness Road (subject to venue agreement)
Site Visit/s dates/times | 1st completed - 2nd due on 15+16 August
Workshop/other dates/times | N/A
Delivery dates/times | 1 to 4 September - daytime not evening (5pm finish?)
Budget agreed | yes
Invoice received | see summary
Contract signed | Molly has signed
Highlighted to ESAG | on August 11th
Framework doc agreed | Draft received from Anya
Concept/Creative matters | Balancing the LOGG and Gay agenda? Is there magic/curiousity ...and provocation? Need to see designs asap
Locations used | 362 Holderness Road
Licensing/TEN | Required - Anya applying
Permissions/Consent | Venue agreement with letting agent for perusal
PRS / PPL required | Need to establish if required
Venue agreement | Venue agreement with letting agent for perusal. Is some kind of indemnity insurance required?
H & S matters | Small, in decent condition with all facilities in place. Some electrical items and furniture is in the space and will need stacking and removing.
Enviro Health matters | Refreshments offered to public, so EH to be informed via ESAG and TEN
Staffing matters | Provided by Scottee team
Volunteer request | None requested
Volunteer needs | N/A
Security matters | We feel that security would be wise. Out of sight but available if required. SIA.
Equipment matters | We need to see a layout or designs for inside the unit.
Power/light/matters | Artist supplies lighting. Power is available in the unit.
Access matters | Decent access as per normal shop/office on the ground floor.
Access Guide sent | Sent out 26 July
Safeguarding matters | Policy required with regards children accessing the space. Age limits/accompanied. DBS unlikely. Signage required.
DBS docs checked | N/A
Environmental matters | None.
Audience control matters | How will they manage crowds outside, assuming it's popular?
Emergency concerns | Will need evac plan from shop unit - agree max number in the space at any one time.
Insurance checked | Not yet
Timeline okay | yes
RA's checked | Not yet
Marketing matters | This project needs marketing to achieve the numbers they're aiming for. Marketing Plan requested
M & E notes | There will need to be some sort of documentation probably from our team.
Blog started by artist | Not yet.
Other detail required
Shared Artists Unit | Not requested
Key contacts for project | Landlord/agent TBC, Andy Train, Chris Collumb from Fuel, Pride planning committee, etc.
Production Manager notes | Coordination with Scottee PM.

## DOMINIC
LOGG 2016 ARTIST | DOMINIC WILCOX
Area of Hull | Boothferry/Gypsyville/Walton Street
Site Visit/s dates/times | 1st completed
Workshop/other dates/times | Around 28 Sept - 2nd October schools performances
Delivery dates/times | 25, 28 Sept or 2 Oct at Market (TBC), 28 Sept at Rokeby School (1-3pm) (TBC)
Budget agreed | Has been reworked, awaiting Dominic's approval
Invoice received | see summary
Contract signed | Subject to budget being agreed
Highlighted to ESAG | on 11 August
Framework doc agreed | not yet
Concept/Creative matters | Experienced improvisors required for performances at market & schoools - being sourced
Locations used | Walton Road Market. Primary schools in the west, Rokeby Primary confirmed, but seem flexible - Francis Askew-26th September - Wheeler Primary-any of dates
Licensing/TEN | Adam advises this isn’t required but could check
Permissions/Consent | Walton St Market have agreed to host stall without charge
PRS / PPL required | n/a
H & S matters | Working with metal potentially sharp objects
Enviro Health matters | n/a
Staffing matters | Performers being sourced for performance element
Volunteer request | None.
Volunteer needs | N/A
Security matters | Objects will need to be attended by no security personnel required.
Equipment matters | Market stall being built by Dominic with guidance from performers
Power/light/matters | None. Power for microphones (performance) to be low voltage if required.
Access matters | None given the sites. May invite groups via James McGuire?
Access Guide sent | Yes
Safeguarding matters | Working within schools
DBS docs checked | Check DBS
Environmental matters | Waste management of items made - what happens to items after project? Who owns the objects?!
Audience control matters | May need to control if becomes very popular within market setting.
Emergency concerns | Will follow market evacuation procedures
Insurance checked | Not yet
Timeline okay | Awaiting confirmation from schools, venue and performers
RA's checked | Not yet
Marketing matters | Not required. Dominic may put up 'Lost & Found' posters nearby with a number to call. He wants to film/photo performances.
M & E notes | Will need to keep a record of participants
Blog started by artist | Imminently.
Other detail required | Performers to be sourced for improvised show in late September
Shared Artists Unit | Requested
Key contacts for project | Roisha (schools), Steve Hess (Walton St market), Men in Sheds
Production Manager notes | Confirm schools workshop dates, shared artists unit and perhaps assist Dominic with the market stall delivery? Paperwork - will most likely need assistance in writing risk assessments, etc.

## THOR
LOGG 2016 ARTIST | THOR / ASWARM
Area of Hull | Beverley Road and bus routes off
Site Visit/s dates/times | 1st completed
Workshop/other dates/times | 1st workshop complete. Returning early August (TBC) to record voices.
Delivery dates/times | 24-28 Aug proposed pop-up phone booths activity. 28 Sept-2 Oct for bus stop installation.
Budget agreed | yes
Invoice received | see summary
Contract signed | no
Highlighted to ESAG | on 11 August
Framework doc agreed | Template sent
Concept/Creative matters
Locations used | Bus stop on Beverley Road. Other locations for phone booth to be agreed but follow bus routes off Beverley Road
Licensing/TEN | May be required due to the performance nature of the activity around the woodburner/tea - not the sound installation necessarily.
Permissions/Consent | Req from JC Decaux (in progress), Council streetscene (in progress) - Kerry is warming up Ian from JCDecaux, Dave is warming up Andy W from KWL . Also Asda. Also locations for 'pop up' phone booth. Needs to secure permission from sources for content.
PRS / PPL required | n/a
H & S matters | Woodburner, hanging speakers, distractions from driving, crowds gathering,
Enviro Health matters | Offering free mint tea to audience
Staffing matters
Volunteer request | Requested - but need to confirm role as it is limited under Hull 2017 rules
Volunteer needs | Pack lunches, coffee, tea, water and biscuits. Will need a break area, potentially in the form of a gazebo in Asda car park.
Security matters | Possible overnight security to look after site
Equipment matters
Power/light/matters | self-contained power, lighting, etc - probably 12v
Access matters
Access Guide sent | sent 27 July
Safeguarding matters | Awareness required given the public nature of site
DBS docs checked | n/a
Environmental matters
Audience control matters | This project largely reliant on passing audience but some awareness raising required with groups/individuals involved in source material
Emergency concerns
Insurance checked
Timeline okay
RA's checked
Marketing matters | No marketing required
M & E notes
Blog started by artist | Imminently
Other detail required
Shared Artists Unit | Requested
Key contacts for project | Council: Kerry Ryan (public transport), Graham Lownsborough (works), Dave Baines (street lights). JCDecaux: Ian. Poetry: Rob Bell.
Production Manager notes | Finalise permissions from all partners (see above), coordinate all paperwork and perhaps be on hand for install. Identify locations for phonebox, may need overnight security organising. Also volunteer needs not yet identified.

## JOSHUA
LOGG 2016 ARTIST | JOSHUA
Area of Hull | North - North Point Shopping Centre
Site Visit/s dates/times | 1st completed.
Workshop/other dates/times | 1st completed.
Delivery dates/times | 27 Aug - 5 September
Budget agreed | Yes
Invoice received | see summary
Contract signed | Yes
Highlighted to ESAG | on August 11th
Framework doc agreed | yes
Concept/Creative matters | Designs received
Locations used | shop unit in North Point Shopping Centre, Bransholme
Licensing/TEN | Covered by shopping centre licence
Permissions/Consent | Venue agreement required. Consent form in development
PRS / PPL required | Joshua to handle it
H & S matters | A cast of your nose (using the alginate that dentists use to make impressions of your teeth). It takes about 5 minutes.Waiver required (in a creative way) regarding possible allergic reaction, etc.
Enviro Health matters | A thermoformed plastic version of the nose is made from the cast, water is used and plastic residues are left in the water - the water will be sived, plastic discarded into recycleing and water dispossed in outside grate
Staffing matters
Volunteer request | Requested
Volunteer needs | Pack lunches, coffee, tea, water and biscuits. Break area can be located in the back of the shop.
Security matters | n/a (because within North Point Shopping Centre)
Equipment matters | Thermoforming machine gets hot, this will be set up behind a screen with a windo in so public can see but not touch the equipment (see design)
Power/light/matters | North Point covering costs
Access matters | Centre and unit accessible to customers
Access Guide sent | sent 27 July. May invite groups via James McGuire?
Safeguarding matters | Detailed plan required as there is phyical touching. Age limit and/or adult/parent accompaniment arrangement to be agreed. Background checks on staff (Joshua has DBS - but to be checked)
DBS docs checked | Required from all staff - Joshua check is form Scotland?
Environmental matters | Water to be sived before emptied in outside grate
Audience control matters | booking system if it gets busy
Emergency concerns | Most of these will be in consultation with the shopping centre with their own Emergency arrangements
Insurance checked
Timeline okay
RA's checked
Marketing matters | Twitter & Instagram used by the artist
M & E notes
Blog started by artist
Other detail required
Shared Artists Unit | Not requested
Key contacts for project | Shopping Centre: Louise Smith
Production Manager notes | Coordinate paperwork: insurance, DBS, Ras, venue permissions, etc. Note: most of this is already done. Volunteer needs not yet addressed.

## D & K
LOGG 2016 ARTIST | DAVY & KRISTEN
Area of Hull | West - Carlton Bingo Hall, Anlaby Road
Site Visit/s/times | completed but will need another one for Adam
Workshop/other dates/times | n/a
Delivery dates/times | 8th & 9th get in 10th & 11th Live 12th Get out
Budget agreed | yes
Invoice received | see summary
Contract signed | yes
Highlighted to ESAG | 2016-08-11
Framework doc agreed | They'll probably need help with this
Concept/Creative matters | Development of 4 scenes
Locations used | Carlton Anlaby Road
Licensing/TEN | no
Permissions/Consent | From Carlton - Sunny Nagra
PRS / PPL required
H & S matters | Artists workign in the derolict building / Traffic on Anlaby road / Show at night
Enviro Health matters | Building / lighting & Sound
Staffing matters
Volunteer request | Yes - requested
Volunteer needs | Will require a break area with tea, coffee, water and biscuits, potentially in the form of a gazebo. Or could they sit in a car or go to a bar on Anlaby Road?
Security matters | Will need security
Equipment matters | Artist may need truss - already discussed between Adam and Davy
Power/light/matters | Building has no electric. Needs generator but issues with owner if it is located inside the building?
Access matters
Access Guide sent | sent 27 July
Safeguarding matters | N/A
DBS docs checked | N/A
Environmental matters | Disruption to pigeons and other creatures such as bats roosting in the building
Audience control matters | Close to the road, distraction to drivers, people crowding to see small work. Question: will artist be present? Or is it a volunteer role? Not sure if this can be volunteer's responsibility
Emergency concerns | Road accidents. Crowd issues? Fire from generator. Who is in charge if there is an emergency? Who stops the installation and moves the audience, etc?
Insurance checked | Follow up email sent 27/7
Timeline okay | Issue: confirming content
RA's checked | not yet completed.
Marketing matters | Going to be a popup show. We either need to wait for people to see something and then respond, or we need to advertise it ahead and/or invite audiences to come see. Eg can we invite newspapers to the first night and they can lead on spreading stories…
M & E notes | Need to monitor how many people are seeing the work.
Blog started by artist | Not yet
Other detail required | No.
Shared Artists Unit | Not requested
Key contacts for project | Carlton Bingo - Sunny Nagra
Production Manager notes | Awaiting confirmation of content for scenes, which will determine production needs. For example, potential to animate window from inside the building. Other installations will be projected using pico projectors (i.e. battery operated). Confirmation of permission to use site still work in progress.
Need for security/stewarding? Install, volunteers, paperwork.

## PERIPLUM
LOGG 2016 ARTIST | PERIPLUM
Area of Hull | Greatfield Estate and Preston Road (east)
Site Visit/s dates/times | completed
Workshop/other dates/times | 11 August TBC at Child Dynamix at St Stephen's and 20-28th August 1 day to be agreed with Child Dynamix and Purple House
Delivery dates/times | 23-25 Sept and 29-2 Oct
Budget agreed | yes
Invoice received | see summary
Contract signed | yes
Highlighted to ESAG | On the 11th August
Framework doc agreed | Sent Awaiting details to fill out
Concept/Creative matters | Design for bottle yet to be received. Vehicle for deliveries (ie float) yet to be confirmed.
Locations used | Greatfield Estate and Preston Road for deliveries. For workshops: Child Dynamix, St Stephens and Purple House
Licensing/TEN | Yes
Permissions/Consent | Informed Jane Price of area teams. Will need permission from venues displaying bottles once identified.
PRS / PPL required | Maybe but hopefully Periplum will sort.
H & S matters | Glass bottles. Moving vintage vehicle. Treasure chest content: people will bring things that they treasure, so they could bring potentially dangerous items.
Enviro Health matters | Disposal of bottles and treasure chests ie waste management
Staffing matters | Someone to deliver bottles, perhaps owner of vehicle?
Volunteer request | N/A
Volunteer needs | N/A
Security matters
Equipment matters | Milk float
Power/light/matters | Potentially for displays.
Access matters | Will be slightly unaware of access issues for those receiving bottles because we won't know who receives them or not.
Access Guide sent | Yes.
Safeguarding matters | Workshop participants. Bottle recipients could be targeted in an improper way - how can we analyse the way in which participants are selected by the community.
DBS docs checked | N/A
Environmental matters | N/A
Audience control matters | Treasure chest displays, however it's not happening all at one time because it will be taking the form of a trail
Emergency concerns | None.
Insurance checked | Not yet.
Timeline okay | Not yet confirmed.
RA's checked | no
Marketing matters | Depends on when it happens. We don't want any marketing leading up, but we will need to have a response once the bottles start getting delivered.
M & E notes | Periplum to keep a log of who the bottles have been sent to, and the process of nominating participants.
Blog started by artist | Not yet
Other detail required | No.
Shared Artists Unit | Probably for bottles and other supplies such as treasure chests.
Key contacts for project | Jenny Mason of St. Stephens, Paul Clark and Jane Stafford of Child Dynamix. Christina Reading of Purple House and Claire Taylor of Greatfield Hub.
Production Manager notes | Awaiting schedule of deliveries and time between delivering, collection and delivery to named individuals. Awaiting confirmation of milk float, and workshop times. Also confirm treasure chest trail locations (Louise?)