## CALENDAR
ll
GGF | Cross-hatching = indicative dates
Project Heralding | Cross-hatching = indicative dates |  |  | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST | [30 empty] | SEPTEMBER | [29 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER
Project Live | Cross-hatching = indicative dates | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
Civil Twilight Ends |  | APRIL S 1: 20:13; APRIL S 15: 20:41; APRIL S 29: 21:10; MAY S 13: 21:38; MAY S 27: 22:05; JUNE S 10: 22:24; JUNE S 24: 22:30; JULY S 8: 22:22; JULY S 22: 22:02; AUGUST S 5: 21:33; AUGUST S 19: 21:01; SEPTEMBER S 2: 20:26; SEPTEMBER S 16: 19:50; SEPTEMBER S 30: 19:15; OCTOBER S 14: 18:42; OCTOBER S 28: 18:12; NOVEMBER S 11: 16:48; NOVEMBER S 25: 16:31
Significant Dates |  | APRIL S 8: School holidays; APRIL S 9: School holidays; APRIL M 10: School holidays; APRIL T 11: School holidays; APRIL W 12: School holidays; APRIL T 13: School holidays; APRIL F 14: Good Friday; APRIL S 15: School holidays; APRIL S 16: Easter Sunday; APRIL M 17: Easter Monday; APRIL T 18: School holidays; APRIL W 19: School holidays; APRIL T 20: School holidays; APRIL F 21: School holidays; APRIL S 22: School holidays; APRIL S 23: School holidays; MAY M 1: Bank Holiday; MAY S 27: School holidays; MAY S 28: School holidays; MAY M 29: Bank holiday; MAY T 30: School holidays; MAY W 31: School holidays; JUNE T 1: School holidays; JUNE F 2: School holidays; JUNE S 3: School holidays; JUNE S 4: School holidays; JULY W 26: School holidays; JULY T 27: School holidays; JULY F 28: School holidays; JULY S 29: School holidays; JULY S 30: School holidays; JULY M 31: School holidays; AUGUST T 1: School holidays; AUGUST W 2: School holidays; AUGUST T 3: School holidays; AUGUST F 4: School holidays; AUGUST S 5: School holidays; AUGUST S 6: School holidays; AUGUST M 7: School holidays; AUGUST T 8: School holidays; AUGUST W 9: School holidays; AUGUST T 10: School holidays; AUGUST F 11: School holidays; AUGUST S 12: School holidays; AUGUST S 13: School holidays; AUGUST M 14: School holidays; AUGUST T 15: School holidays; AUGUST W 16: School holidays; AUGUST T 17: School holidays; AUGUST F 18: School holidays; AUGUST S 19: School holidays; AUGUST S 20: School holidays; AUGUST M 21: School holidays; AUGUST T 22: School holidays; AUGUST W 23: School holidays; AUGUST T 24: School holidays; AUGUST F 25: School holidays; AUGUST S 26: School holidays; AUGUST S 27: School holidays; AUGUST M 28: Bank holiday; AUGUST T 29: School holidays; AUGUST W 30: School holidays; AUGUST T 31: School holidays; SEPTEMBER F 1: School holidays; SEPTEMBER S 2: School holidays; SEPTEMBER S 3: School holidays; SEPTEMBER M 4: School holidays; OCTOBER S 28: School holidays; OCTOBER S 29: School holidays; OCTOBER M 30: School holidays; OCTOBER T 31: School holidays; NOVEMBER W 1: School holidays; NOVEMBER T 2: School holidays; NOVEMBER F 3: School holidays; NOVEMBER S 4: School holidays; NOVEMBER S 5: School holidays
Hull 2017 Programe Significant Dates - NOTE, not comprehensive |  | APRIL T 11: Slung Low 2; APRIL W 12: Slung Low 2; APRIL T 13: Slung Low 2; APRIL F 14: Slung Low 2; APRIL S 15: Slung Low 2; APRIL F 28: John Grant; APRIL S 29: John Grant; APRIL S 30: John Grant; MAY M 1: John Grant; MAY T 18: Depart; MAY F 19: Depart; MAY S 20: Depart; MAY S 21: Depart; MAY S 27: Big Weekend; MAY S 28: Big Weekend; MAY M 29: Back to Ours 2; MAY T 30: Back to Ours 2; MAY W 31: Back to Ours 2; JUNE T 1: Back to Ours 2; JUNE F 2: Back to Ours 2; JUNE S 3: Assemble Fest; JULY S 1: SL 3 / PRS / Paper City; JULY S 2: PRS / Paper City; JULY S 22: Hull Pride; JULY S 29: LGBT50 / Veterans; JULY S 30: Veterans; AUGUST T 10: Great Blueness?; AUGUST F 11: Great Blueness?; AUGUST S 12: Great Blueness?; AUGUST S 13: Great Blueness?; AUGUST M 14: Great Blueness?; AUGUST T 15: Great Blueness?; AUGUST W 16: Great Blueness?; AUGUST T 17: Great Blueness?; AUGUST F 18: Great Blueness?; AUGUST S 19: Great Blueness?; SEPTEMBER F 1: DTS / Freedom Fest; SEPTEMBER S 2: DTS / Freedom Fest; SEPTEMBER S 3: DTS / Freedom Fest; SEPTEMBER M 4: DTS cont. to 1st Oct; SEPTEMBER M 25: Turner Prize Opens; SEPTEMBER T 28: Conts Strong Lang.; SEPTEMBER F 29: Conts Strong Lang.; SEPTEMBER S 30: Conts Strong Lang.; OCTOBER W 4: Slung Low 4; OCTOBER T 5: Slung Low 4; OCTOBER F 6: HULL FAIR / SL 4; OCTOBER S 7: HULL FAIR / SL 4; OCTOBER S 8: HULL FAIR / SL 4; OCTOBER M 9: HULL FAIR; OCTOBER T 10: HULL FAIR; OCTOBER W 11: HULL FAIR; OCTOBER T 12: HULL FAIR; OCTOBER F 13: HULL FAIR; OCTOBER S 14: HULL FAIR; OCTOBER M 30: Back to Ours 3; OCTOBER T 31: Back to Ours 3; NOVEMBER W 1: Back to Ours 3; NOVEMBER T 2: Back to Ours 3; NOVEMBER F 3: Back to Ours 3; NOVEMBER S 4: Back to Ours 3
Type of Activity | What happens
Digital | Green Ginger Fellowship website and social media goes live | bar: APRIL M 3
Press | Hull Daily Mail run story and pictures about the vault | bar: APRIL M 3
Press | BBC Radio Humberside / other local media pick up story | bar: APRIL T 4 to APRIL W 5
Press | HDM run follow up story about the Institute | bar: APRIL T 6
LIVE- CRATES | Crates moved around city | bar: APRIL M 10 to APRIL T 11
Marketing | Institute take out Ad in HDM + flyers /posters distributed | bar: APRIL T 11
Press | HDM run story about crates being moved around the city | bar: APRIL T 11
Digital | GGF begin investigations by opening crates and reporting on stuff inside | bar: APRIL T 13
Digital | GGF find something in a crate alluding to opening of Seventh Alley | bar: APRIL F 14
LIVE - CRATES | Crates appear at Freedom Centre | bar: APRIL W 19
Marketing | Letters delivered to Preston Road households | bar: APRIL W 19
Digital | GGF post all details of the 7 Alleys "event" | bar: APRIL W 19
LIVE - 7 ALLEYS | Horse and Carriage delivery of scrolls | bar: APRIL F 21; APRIL S 23
Marketing | LOGG eco-wash stamps appear in East Park | bar: APRIL T 25 to APRIL T 27
LIVE - CRATES | Crates are moved to East Park | bar: APRIL S 29
LIVE - 7 ALLEYS | Horse and Carriage parades around East Park area | bar: APRIL S 30
Digital & Press | Reports of appartitions manifesting in East Park | bar: APRIL S 30 to MAY T 2
LIVE - 7 ALLEYS | Shows in East Park | bar: MAY W 3 to MAY S 6
Digital | GGF report on finding crate containing a strange Gold object, they decide to run a competition | bar: MAY T 18
Digital | GGF announce the prize for their competition | bar: MAY F 19
Digital | Golden object competition closes | bar: MAY W 24
Press | Mike Covell article in HDM about the origins of the Golden Nose of Green Ginger | bar: MAY W 24
Press | HDM reporting on a lady called Margaret finding a crate in her allotment in Longhill. | bar: MAY T 25
Live | LOGG eco-wash stamps appear on paving stones outside Northpoint Shopping Centre | bar: MAY F 26
Digital | Louise and Northpoint approaches the GGF to offer the shop | bar: MAY F 26
Digital | GGF repost HDM Margaret article to their Facebook and assure followers they are in contact with Margaret. | bar: MAY M 29
LIVE - CRATES | LoGG Crates appear as part of set at Back to Ours | bar: MAY W 31
LIVE- CRATES | LoGG crates appear as part of set at Back to Ours | bar: JUNE S 3
LIVE - CRATES | A large stack of crates is delivered to Northpoint Atrium by GGF | bar: JUNE M 5
Press & Digital | GGF open BTO crate contents (noses of Bransholme). HDM article about contents, confirming Northpoint hosting GNGG till August | bar: JUNE T 6
LIVE - CRATES | Crates disappear from Northpoint atrium (into the shop) | bar: JUNE W 7; JUNE F 9; JUNE S 11; JUNE T 13
Digital | GGF report on the progress of the Guild of Commoners | bar: JUNE M 12
LIVE - NN | Nobody Nose opening ceremony | bar: JUNE S 17
LIVE - NN | Nobody Nose Operational | bar: JUNE S 17 to AUGUST S 19
LIVE | A hole is dug on Beverly Road | bar: JUNE M 19
LIVE | Excavations at Rediffusion - performers - crate in hole | bar: JUNE T 20
LIVE | Excavations at Rediffusion - performers - crate next to hole | bar: JUNE W 21
LIVE - REDIFF | GGF called in to look at the Rediffusion crates - they take the crate away to investigate | bar: JUNE W 21
Digital | GGF find a strange contraption in the crate and call out on social media for ex RD workers to explain what it is. | bar: JUNE T 22
Press | Press article about the Re-rediffusion crates - call out for ex RD workers to explain | bar: JUNE F 23
Digital | An ex-Redifussion employee comes forward and the GGF reveal that the apparatus are for collecting voices. | bar: JUNE S 24
Digital | Re-Redifussion come forward as a group - their relatives were part of the secret research arm. They request contraptions, as they have plans for them. | bar: JUNE M 26
Digital | Banter from GGF about Re-Redifussion | bar: JUNE M 26 to JULY S 2
Press | Press call out for people to contribute their voice + pic of VEARO | bar: JULY M 3
LIVE - REDIFF | Aswarm - voices are gathered | bar: JULY M 3 to JULY T 6; JULY W 12 to JULY S 16
LIVE - GUILD | Longhill Performance Week ending in bonfire | bar: JULY S 8 to JULY S 15
Digital | The Fellowship find a miniature crate in the ashes left from the bonfire, which on opening emits voices | bar: JULY S 15
Digital | Fellowship report that minature crate seems to have grown - Ant not convinced. Deepens rift. | bar: JULY S 15
Digital | GGF uproar about burning crates | bar: JULY T 18
Digital / Press | GGF/Rediff update that voices are becoming volatile, looking for a power source to install super voice | bar: AUGUST T 1
Digital | Nose Guardian and Assistants are preparing for departure of GNGG | bar: AUGUST T 1; AUGUST M 14 to AUGUST F 18
Press | Article in HDM about the GNGG being gifted back to city of Hull by being placed residence at Hull History Centre till the end of the year | bar: AUGUST T 1; AUGUST T 15
LIVE - NN | Gold Nose of Green Ginger closing ceremony and reception at Hull History Centre | bar: AUGUST S 19
LIVE - REDIFF | Aswarm - voices are gathered locally | bar: SEPTEMBER W 6 to SEPTEMBER S 9
LIVE - CRATES | large crate appears in Pickering Park | bar: SEPTEMBER M 11
Digital | GGF &RRD investigate crate and find power source | bar: SEPTEMBER M 11
LIVE - REDIFF | Super voice installation | bar: SEPTEMBER F 22 to SEPTEMBER S 30
Digital | Fellowship report that tiny crate found at Longhill Burn has grown in size. | bar: AUGUST M 21 to AUGUST S 27; SEPTEMBER T 26
Marketing | Tiny footprints start being seen around the area | bar: OCTOBER M 2
LIVE - CRATES | Fellowship send the tiny things crate out to school/supermarket | bar: OCTOBER M 2 to OCTOBER S 8
LIVE | Signs of life are seen at the Pumping Station - lights seen flickering from tower. | bar: OCTOBER W 4 to NOVEMBER F 3
Marketing | Invitations land to attend cardboard city - grand reawakening of the city - frozen until LoGG reappeared. | bar: OCTOBER M 9
LIVE - CC / CRATES | Signs of life are seen at the Pumping Station / Inside the Crate | bar: OCTOBER M 9 to OCTOBER T 19
Digital | Fellowship report that they are also cataloguing a lot of LARGE artefacts | bar: OCTOBER M 16
LIVE - CC | Cardboard City open to public | bar: OCTOBER F 20 to NOVEMBER S 5
Digital | Fellowship report that tiny footprints appear to be growing | bar: OCTOBER M 23
LIVE - CRATES | A large crate appears on Land of Green Ginger / Whitefriargate | bar: OCTOBER S 28 to NOVEMBER S 11
Digital | GGF report that they believe there will be some kind of mass gathering | bar: OCTOBER S 28
LIVE - CRATES | Other large crates appear along the Macnas route | bar: NOVEMBER F 3 to NOVEMBER S 11
Digital | GGF report that the tiny people crate has started to grow | bar: NOVEMBER M 6
LIVE - MACNAS | Parade | bar: NOVEMBER S 11
Digital | GGF report on their final findings | bar: NOVEMBER M 13 to NOVEMBER S 19