## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Budget inadequate to support all associated activities. | Cancelation of activities or activities not meeting the requirements of speakers/audience. | Julia | 3 | 5 | 15 | Request activities requirements prior to booking them to ensure budget covers this. Gather supplier quotes for any materials, catering or equipment that will be required to ensure budget and estimates are accurate. | 1 | 5 | 5 | Open
2 | Curator not delivering | Exhibition not going ahead or last minute recruitment of new curator to hang the exhibition. | Julia | 2 | 5 | 10 | Drawing up curatorial agreement which must be signed by curator and project delivery team |  |  |  | Open
3 | Not meeting project targets | Undermining the nature of the agreement. | Julia | 2 | 5 | 10 | Checking throughout project that we are on course to achieve these and taking actions outlined in this document to ensure we mitigate risk. | 2 | 5 |  | Open
4 | Partners not signing off publicity material before deadline. | Limited public awareness of project due to late delivery or partners being disatisfied with material. | Chloe | 4 | 3 | 12 | Ensure partners are given adequate time to send amends and clearly communicate deadlines. | 2 | 3 | 6 | Open
5 | Artists not engaging with project, attending meetings, approving items or supplying information. | A disorganised exhibition and inaccurate communication regarding the event. | Julia | 3 | 5 | 15 | Artists signed an artists agreement re their responsibility for the project. Artists required to send progress updates on what stage their work is at and statement. Information gathering to take place early in the project to limit last-minute risk. | 1 | 5 | 5 | Open
6 | Volunteers turning up and no KAG rep being present. | Volunteers disengaging - having a negative experience. | Julia | 3 | 2 | 6 | Proposed walk through with volunteers, and briefing with emergency numbers for project leads. | 2 | 2 | 4 | Open
7 | Health and safety/damage of working during hanging week. | Injury of volunteer and/or damage to work. | Julia | 3 | 4 | 12 | Artists have insured their work and volunteers are supervised at all times and will not be asked to do anything which will compromise their safety. | 1 | 4 | 4 | Open
8 | Abuse towards volunteers whilst leafleting. | Negative experience for volunteers. | Hull 2017 | 3 | 3 | 9 | Hull 2017 to brief volunteers on dealing with difficult circumstances. | 3 | 3 | 9 | Open
9 | Poor attendance at exhibition | Reputational damage and artists feeling disengaged and disappointed about the show. | Chloe | 3 | 5 | 15 | Lots of promotion, utilising partners to promote the show, and social media engagement. | 1 | 5 | 5 | Open
10 | Representatives, i.e. Artists from KAG leading invigilation not communicating positively or effectively. | Audience feeling disappointed and alienated. | Chloe/Julia | 3 | 4 | 12 | Briefing artists properly before show. | 2 | 4 | 8 | Open
11 | Flooding of gallery | Damage work, and gallery closes | Julia | 1 | 5 | 5 | Contact Wykelands and KAG in the event of an emergency. Artists are responsible for insurance of their own art, as per artist agreement. | 1 | 5 | 5 | Open
12 | Artists ' health | No delivery of work, or no invigilation. | Julia | 3 | 3 | 9 | Ensure artists are told to call project lead if there are any problems with delivery of work, or invigilation as early as possible. | 2 | 3 | 6 | Open
13 | Vandalism of art | Distressing for artists and volunteers. | Julia | 1 | 3 | 3 | Artists to ensure work as per their agreement, and invigilators to be vigilant in their duties. Report any incidents. | 1 | 3 | 3 | Open
14 | Art falling off walls or plinths | Danger to visitors, upset for artists. | Julia | 2 | 4 | 8 | Ensure that work is put up securely during installation, and artists' provide any info regarding hanging beforehand, plus ensure their work. | 1 | 4 | 4 | Open
15 | Incorrect labelling of art | Miscommunication of work's details. | Julia | 2 | 3 | 6 | Ensure artists send details beforehand and ensure this is checked by curator. | 1 | 3 | 3 | Open
16 | Too many people turn up for events due to issues with booking information. | Those booked being replaced by adhoc visitors who have not booked. | Chloe | 5 | 4 | 20 | Hull 2017 team to communicate outcome regarding booking and promote where attendees should book, to ensure we do not go over capacity. | 1 | 4 | 4 | Open
17 | Health of volunteers | Less promotion and support during exhibition opening times. | Julia | 3 | 2 | 6 | Julia to brief volunteers, and provide number to call if unwell. | 3 | 2 | 6 | Open
18 | Negative press coverage | Reputational damage to gallery | Chloe | 2 | 4 | 8 | Chloe to liaise successfully with media, and brief any interviewees beforehand. | 1 | 4 | 4 | Open
19 | Children's entry to gallery | Injury or risk of offence | Julia | 3 | 4 | 12 | Attended safeguarding meeting, seek advice from Caroline on signage, and teacher's getting releases from parents. | 1 | 4 | 4 | Open
20 | Events clashing with other City of Culture events. | Potential to reduce audience. | Chloe | 4 | 3 | 12 | Drawing up an events calendar to capture other events and liaise with other groups re The Female Gaze dates | 2 | 3 | 6 | Closed
21 | Suppliers fail to deliver AV equipment |  | Chloe | 3 | 3 | 9 | Ensure agreement is in place and delivery time and date is agreed well in advance. On the day of the event, arrive early and call supplier if there are any problems. | 2 | 3 | 6 | Open
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...