## Sheet1
Royal Ballet: Opening the New
All Site Schedule_RV3
SITE |  | New Theatre |  |  |  |  | Queens Gardens | Trinity Square
In time | Out time | Activity | music | LX | VT | Dancers / Notes | Activity | Actvity
WEDNESDAY 13/09/2017
9:00 | 13:00 | Prerig LX & Flown Masking Packs for lunch will be brought for Crew.
13:00 | 14:00 | Lunch
14:00 | 18:00 | Continue Prerig LX & Flown Masking / Rig Projector / Pianos Get in
14:14 |  | Andy Collett & Les Bone Train Arrival in Hull
18:18 |  | Technical Crew Train Arrival in Hull
THURSDAY 14/09/2017
9:00 | 13:00 | Start of day briefing
9:00 | 13:00 | Get in LX / Sprung Floor / Flown/ Wigs Packs for lunch will be brought for Crew. (11am)
13:00 | 14:00 | Lunch
14:00 | 18:00 | Lay Lino/ Production desks set-up / Prepare to focus
16:15 |  | Janie Valentine & Ross MacGibbon Train Arrival in Hull
18:00 | 19:00 | Supper
18:00 | 19:00 | Piano Tune
19:00 | 23:00 | LX Focus
FRIDAY 15/09/2017
6:00 | 8:00 | [5 empty] | Rubbish pick / site mark-up / Build of screen support structures
8:00 | 10:00:00 | 16 room vases: JZ flowers. |  |  |  |  | Delivery & install of generators / Concessions and Bar Build commences
8:00 | 16:00 | Camera set-up | [5 empty] | Ramp & Stage Build commences / 2 x SIA Security on site
9:00 | 13:00 | Lighting Plotting/ Sound design levels
10:01 |  | Kevin O'Hare Train Arrival in Hull/ Food delivery salads, snacks
12:14 |  | Dancers/Musicians & Broadcast Team Train Arrival in Hull |  |  |  | COMPANY TRAIN PHOTO OP |  | L&P Team Train Arrival in Hull & Check-in to Holiday Inn
12:00 |  | Food delivery Sandwich Packs (Lunch) |  |  |  |  | Security & First Aid on site
12:00 | [6 empty] | Fence & Barrier delivery / Build of stage, PA and FOH
13:00 | 14:00 | Lunch
13:00 | 14:00 | Pigeon rehearsal on stage | [5 empty] | JZ Flowers: 2x wedding displays(jane at minster)
14:00 | 18:00 | Lighting Plotting |  |  |  |  | Install of screens
14:00 | 18:15 | Pigeon rehearsal in Dock
15:00 | [6 empty] | Build of stage tent
16:00 |  | Sandwich Packs delivery for Supper |  |  |  |  | Testing of PA, Screens and Broadcast Link | Dance schools arrive & into costume
16:15 | 18:30 | [6 empty] | Bevvy of Swans vols called
16:30 | 18:30 | [6 empty] | Full Take Flight Dress Rehearsal until 18:30
16:30 | 17:00 | Set stage/ Barrers and Rehearsal Piano
16:30 | 17:00 | Stage available for dancers
17:00 | 18:00 | Crew Supper | [5 empty] | Rehearasl Ends 18:00
1700 | 18:15 | Class on Stage
18:15 | 18:30 | Set for Rehearsals
18:18 |  | Rachel Vickers / Stage Management & Wardrobe Train Arrival
18:30 | 18:50 | [6 empty] | Dance Schools depart for New Theatre Dress Rehearsal
19:00 | 22:30 | Technical Rehearsal 1 (final curtain call, stage + piano, Violin, CD1, with costumes wig hair and makeup | Stage + Piano/Violin/CD1 |  |  | With audience, press, media. In performance order.
20:00 | 0:00 | [5 empty] | Site clear of all contractors / 1 x SIA Overnight Security on site / First Aid off site | 2 x SIA Overnight Security on site
SATURDAY 16/09/2017
0:00 | 8:00 | [5 empty] | Security changeover (overnight asset protection) | 2 x SIA Overnight Security on site
6:00 | [6 empty] | Site dressing | 180 white roses (2x poses) Haith
8:00 | 17:00 | [6 empty] | 6 x SIA Security on site
9:00 | 13:00 | Technical work / Set Barrers and Rehearsal Piano
9:45 | 11:45 | [6 empty] | Bevvy of swans vols called Parish centre. Dancers: hands on History Museusm
10:00 | 11.:00 | Food delivery salads/snacks |  |  |  |  | Broadcast arrive on site | 3 x Traffic Management Crew On site
10:00 | 11:45 | [5 empty] | Install of tree uplighting | Final Take Flight Rehearsal including mass warm up on site
10:00 | 14:00 | 14 flower (dancers) 2x small gift (RV/JF) + building of Pedistall urns in Entrance.
12:00 | 13:00 | Rehearsal time for NAPA and Skelton Hooper |  |  |  |  | Delivery & install of portaloos
12:00 |  | Sandwich packs delivered to Venue |  |  |  |  | Road Closure at Guildhall Road in place
12:00 | [6 empty] | Security Changeover - Overnight to Day Shift x 4
12:14 |  | Alex Beard Train Arrival in Hull
13:00 | 14:15 | Class on stage |  |  |  |  | Erection of information / Welfare Marquee
13:00 | 14:00 | Crew Lunch Break
13:10 |  | Dancers travel New Theatre to Trinity Square on Bus
14:00 | 18:00 | [5 empty] | Testing continues (PA, Screens, Broadcast link) | 2 x additional SIA Security + 2 Medics on site
14:15 |  | Set for Technical Rehearsal set (strike piano and Barres) |  |  |  |  | Ticket gate barriers to be set
14:30 | [7 empty] | ALL Performer Call (Dance Schools & Vols) - meet back in holding spaces
14:30 | 17:30 | Technical Rehearsal 2 Sandwich packs delivered to site (4pm) | Musicians in position, Stage + Piano/Violin/CD2 |  |  | Stage + Piano / No Costume + Wigs
15:00 | [6 empty] | Bins delivered & distributed across site
15:00 | 15:30 | [5 empty] | SIA & Steward Briefing | Dancer Warm-up
15:30 | [6 empty] | Show Security on shift 14 x SIA from 15:30 to 23:00 | Set for performance One
15:36 | [7 empty] | Prelude begins
15:45 | 16:00 | [6 empty] | Take Flight Performance One
16:00 | 16:30 | [5 empty] | Volunteer arrival / Sign-in at Unison Building | Break
16:30 | [6 empty] | Volunteer Briefing at Unison Building
16:36 | [7 empty] | Prelude begins
16:45 | 17:00 | [6 empty] | Take Flight Performance Two
17:00 | [6 empty] | Road Closure at Wilberforce Drive in Place / Welfare Team on-site | Performance ends 17:05 bus arrives to take kids to Theatre.
17:05 | [7 empty] | New Theatre
17:15 | [6 empty] | Volunteers deployed
17:30 | [6 empty] | Event First Aid on site | All dancers off site
17:30 | 20:30 | [6 empty] | Site Breakdown
17:30 |  | Reset for performance |  |  |  | No wigs Hair/ Costumes as required. + make up in performance order.
17:30 | 18:30 | Supper
18:00 |  | Doors FOH set |  |  |  |  | GATES OPEN
18:00 |  | Piano Tune
18:30 |  | Doors open
18:55 |  | Half Hour Call
19:00 |  | Standby Theatre doors open
19:15 | 19:20 | Stand By call
19:25 | 19:29 | [5 empty] | GARDENS: GARY AVIS & KOFI INTRO: PROGRAMME FIRST HALF
19:29 | 19:30 | [5 empty] | HOLDING SLIDE
19:33 | 19:44 | The Vertiginous Thrill Of Exactitude |  |  |  |  | Programme 1 running sim.
19:45 | 19:47 | Kevin O 'Hare opening speach | Recorded Music: Franz Schubert |  |  | MIC
19:47 | 19:50 | Film Montage of dancers |  |  | Film | VT
19:50 | 19:55 | Ballet 101 | Recorded music
19:55 | 20:01 | Heart’s Furies | Music: Leoš Janáček Kate Shipway (piano)
20:01 | 20:02 | Introduction to Piece and dancer.Robert Parker |  |  |  | MIC
20:02 | 20:05 | Hamlet Solo | Music: Duke Ellington, Billy Strayhorn
20:05 | 20:11 | Méditation from Thaïs | Music: Jules Massenet, live
20:11 | 20:19 | Tarantella
20:19 | 20:29 | A Dancer’s Story
20:29 | 20:35 | The Two Pigeons
20:35 |  | INTERVAL (in Gardens)25 minuites |  |  |  |  | INTERVAL (in Gardens)
20:36 | 20:50 | [5 empty] | Kofi and Gary Avis in the gardens talking about what its like to be a dancer, the Royal ballet and the programme
20:45 | 21:00 | [5 empty] | Film loop starting with HC&L adds and making off finishing with 8 months VT from Hull 2017.
|  | INTERVAL Finishes in Gardens finishes at 21:15 |  |  |  |  | INTERVAL Finishes in Gardens finishes at 21:15
21:01 | 21:09 | Swan Lake
21:09 | 21:14 | Death of the spoken Word
21:14 | 21:21 | Qualia
21:15
21:21 | 21:24 | The Dying Swan |  |  |  |  | Programme part 2 running
| 21:30 | Vintage bus arrives on site to take RB Dancers to Gardens
21:24 | 21:33 | Romeo and Juliet
21:33 | 21:40 | After the Rain
21:40 | 21:49 | Sylvia
21:49 | 21:54 | Czárdás Tap Dance
21:54 | 22:03 | Le Corsaire
22:03 | 22:08 | Curtain Call/ Kevin on stage again.
22.1 | 22:20 | ON THE BUS TO THE GARDENS,
22.2 | 22.3 | [5 empty] | Intro:Gary Avis & Kofi: Bow in Queens Gardens
22.3 | 22.35 | [5 empty] | Dancers back to NT.
22:45 |  | De Rig and breakdown (see separate planning ) |  |  |  |  | AUDIENCE CLEAR / Site breakdown commences
23:00 | [6 empty] | Volunteers off-site / Roads Re-open (except Guildhall Road)
0:00 | [6 empty] | Security Changeover (Asset Protection) 2 x SIA 00:00 TO 16:00

## Sheet2
Start at QG | 19:26 | 19:29 | Part one: 2.5 mins.
| 19:29 | 19:30 | Holding screem
Start Interval | 20:25 | 20:35 | Kofi and Gary
| 20:35 |  | Film loop ads
Hull Film : dance
8 months