|  |  |
| --- | --- |
| **Name of Individual / Organisation** | All Star Entertainment |
| **Name of Project** | M62 Creative Corridor Youth Empowerment Programme (Block Party) |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |
| --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** |
| 18/08/16 | 28/10/16 | Research and Development of project. Putting Project plans in place. Speaking with partners. Putting recruitment plans in place. Securing venues and workshop spaces. Recruiting artists/ trainees etc. Putting marketing and communication plans in place. Putting evaluation plans in place |
| 30/01/17 | 30/01/17 | Press Release out |
| 16/02/17 | 16/02/17 | Launch Event |
| 19/04/17 | 20/04/17 | **BLOCK PARTY! 1** Tasters/workshops and sharing event The **HIVE** Youth Hub **Birkenhead,Merseyside** |
| 27/04/17 | 28/04/17 | **BLOCK PARTY! 2** Tasters/ workshops and sharing event - **Make Liverpool** |
| 29/04/17 | 30/04/17 | **BLOCK PARTY! 3** Tasters/ workshops and sharing event - **Salford** |
| 24/05/17 | 25/05/17 | **BLOCK PARTY! 4** Tasters/ workshops and sharing event - **Bradford** |
| 25/08/17 | 27/08/17 | **BLOCK PARTY! 5** Tasters/ workshops and main event - Australia Houses **HULL 2017** |
| 14/10/17 | 14/10/17 | Evaluation and sharing from programme gathered by this date |
| 14/10/17 | 14/10/17 | Launch of Hull Block Party Creatives Collective |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances