**BLADE**

**Installation & Operations meeting  
3rd November 2016**

Attending: Chris Clay, Richard Townend, Andrew Knight, Richard Bickers, Milly Hennayake

Apologies: Hazel Colquhoun

|  |  |
| --- | --- |
| **POINT** | **ACTION** |
| **1. REQUIREMENTS FOR AN EVENT LICENCE** |  |
| RT to look into highway permit for temporary storage of equipment | RT |
| CC to forward Hull 2017 public liability insurance details to RT. | CC |
| **2. CONSULTATION WITH HUMBERSIDE POLICE AND ROAD USERS** |  |
| **2a. Confirm users of Carr Lane**  RT – public transport is the main concern, only users will be buses, taxis, motorbikes and cyclists.  AK – large vehicles to go down Paragon Street.  CC - confirmed Hull City Hall load-in is located on Paragon Street. |  |
| **2b. Consultation with bus operators**  RT confirmed bus operators are aware and has a weekly meeting with them. |  |
| **2c. Consultation with taxi operators**  RT to confirm contact for Black Cabs.  CC to consult private hire taxis. | RT  CC |
| **2d. Requirements for signage**  ALL – No requirement for signage as the structure is motorway bridge height. No requirement for high winds signage as this will have to go directly on the structure which may ruin aesthetics |  |
| **3. CLEANSING** |  |
| **3a. Routine**  CC - speak to Streetscene around cleaning of Queen’s Victoria Square.  Supports are key areas to keep clean – Low level graffiti and litter. | CC |
| **3b. Emergency – graffiti etc.**  CC to speak to Streetscene to confirm equipment.  CC confirmed access to cherry pickers through KWL as they are partners | CC |
| **4. MAINTENANCE** |  |
| RB - bolts to be checked regularly.  CC – create Hull 2017 formal inspection list (weekly occurrence).  AK - trial installation (December) allows 3 week window to troubleshoot  RT – Winter maintenance - May require use of de-icer on surface. | CC / RC |
| **5. COORDINATION WITH OTHER 2017 EVENTS** |  |
| CC - confirmed “Made in Hull” projections will run until 9pm. Projectors to be loaded out by 02:00 on 07/01/17.  CC - to confirm timescale for “Made In Hull” de-rig and share schedule.  AK – Area to be clear before Blade install as it wouldn’t be a safe working area to have 2 contractors in at the same time.  RT – street furniture may change in the next 2 months.  CC - Hull 2017 has full list of City Hall events. | CC |
| **6. PLANNING FOR INSTALLATION DAY** - 08/01/2017 (tbc) |  |
| **6a. Closure of Queen Victoria Street**  ALL - maintain access to Princes Quay and allocate a viewing spot where pedestrians can come and watch. Crowd control barriers may be a better option and easier to set up.  CC - take a draft event safety management plant to ESAG on 10/11/2016.  Focus on activity on QVS.  MH – pull together a schedule and send to CC ahead of ESAG (focus of public safety)  MH – Master schedule will be in 5/10 minute blocks and categorised by work groups - press (BBC), contractor (North Midland) to control risks or time lags.  CC - Press to be accredited (notify MM) | CC  MH  MH  CC |
| **6b. Business engagement**  CC - to assure businesses that the installation won’t affect trade and access.  RT – be aware of business on Saville Street as they can be negatively vocal.  RT – Notify businesses at the root end - Café Nero  AK – to meet with Claire from Princes Quay, maintain communication. Consider the load-out date as Princes Quay top floor is reopening at Easter. | CC    AK |
| **6c. Security and crowd management**  ALL – to treat installation as event. Security included with the transport contractors to protect the site. |  |
| **6d. Crisis communications**  CC - speak to Hull 2017 Comms team and invite them to Blade meetings.  RT - confirmed public highways already have a plan for this. | CC |
| **7. ONGOING SECURITY** |  |
| RT – confirmed CCTV in the area. Option to put anti-climb paint on supports.  CC - 24 hr security as a precautionary measure and can reduce to Fri/Sat.  ALL - confirm Event Manager and command and control structure. CC to create flow-chart. | ALL / CC |
| **8. VOLUNTEER SUPPORT** |  |
| AK - volunteer presence required over 12 week period. Identify dedicated team, regard them as ambassadors. CC / RC put in a volunteer request | CC / RC |
| **9 . NEXT MEETING** |  |
| Every two weeks in advance of Blade delivery meetings.  RC to schedule. | RC |
| **10 . AOB** |  |
| ALL - Mobile catering TBC  RT - requires plan with final orientation / location / height.  RB - circulate final 3D plan  RT - Photography locations. May be an opportunity to have a photo in front of structure from City Hall balcony. | RB |