**CRITICAL PATH: BACK TO OURS (MAY)**

|  |  |  |
| --- | --- | --- |
| **Detail** | **Date** | **Responsibility** |
| All non-programme specific copy updated | w/c 27 Mar | LM |
| Confirmation of programme | Fri 31 Mar | Programming |
| All final copy and images received | Mon 3 Apr | Touring companies/LM |
| Round one artwork | 3-4 Apr | LM |
| First round sent to Hull 2017 | Wed 5 Apr | Bluestorm |
| Version sent to partners for approval | Wed 5 Apr | LM/Partnerships |
| Amends collated and sent back to Bluestorm | Thur 6 Apr | LM |
| Second round sent to Hull 2017 and final amends. SIGN OFF REQUIRED. | Fri 7 Apr | Bluestorm |
| Sent to print deadline | Mon 10 Apr | Bluestorm |
| Delivery of print to Lowgate House | Thur 13 Apr | Bluestorm |