## Sheet1
April 2016 | Commission Scripts, agree preliminary budgets, secure core team.
May 2016
June 2016
July 2016
August 2016
September 2016 | HQ selection: visit options and confirm. (AL)
London meeting: Core Creative Team
Announcement of Hull 2017 season 1 (with some highlights of season 2)
October 2016 | Draft 1 delivery/ Performance site scoping (Slung Low)
Create marketing image/photo for The Flood
November 2016 | Early Nov 16: Full team meeting/ Site visit (2 days)
Mid Nov 16: Performance site confirmation.
December 2016
January 2017 | Site visit/update meeting: (Slung Low)
Marketing image release to time with second wave of press
February 2017 | Company on to site.
Mid Feb 17: Make Digital Prologue released. A five minute video introduction to the world and the first story beat.
End Feb 17: Digital Prologue projected on to the side of the airstream caravan. The caravan visits different areas of the city every night for 7 days
March 2017 | Rehearsals for Flood Part 1.
April 2017 | April: 10th/11th: Flood Part 1: Dress and filming.
12th-16th April 17: Week long Performance of The Flood Part 1. This can extend for two weeks in consultation with Hull 17.
May 2017 | Recruitment/audition of these Flood Part 2 company.
Create a "previously on the Flood" video- 3 or 4 minute dynamic summary: used as a recruitment tool and as a continuation of the energy of the project.
June 2017 | Start participatory sessions with Part 2 company.
July 2017 | Start participatory sessions with Part 2 company.
Create Narrative Beat 3: a piece of the story that fits between the two live shows. This piece of story exists as a short video and Internet playground (personal diaries/twitter characters/Facebook profiles.)
August 2017 | August: Rehearsals for The Flood Part 2.
September 2017 | Mid September 17: The live performance of both Parts of The Flood.
On Wednesday/Thurs/Fri of the week Show 2 is performed. On Saturday and Sunday both Parts 1 and 2 are performed.
This format can run for a second week. Decision made in April 16 during recruitment.