LGBT 50

Pride in Hull / UK Pride meet

08/12/16

Colin Wilson

Andy Train

Cian Smyth

Agenda

Catch Up

ESAG

Programming

Marcomms planning

Branding

AT noted they’ve applied for a red arrows flypast – encouraged by Danny Flemming, PC. They’re doing something in Lincolnshire same day.

Queen’s Gardens max capacity is 10,000. Helen Thackeray advised that was tops. ESAG advised fencing off of site would be necessary. AT noted this led them to believe they would need control of roads either side of Queens Gardens – Guildhall Road and Queens Dock Avenue (?)

CW noted Helen will guide on drink licensing and site planning for QG.

Parade to begin outside College at Queens Gardens through Lowgate, right at Trinity Church, right on to Market place through Whitefriargate and across Victoria square alongside city hall up to paragon street to cenotaph, then to Jameson street. ESAG advised straight on from there to QG. Pride want it to go around Albion street , Prospect street, Library and around. Advised they should account for 2000 people attending the parade. Decision to be made later.

Staging and licensed services on QG site will have to be completed by 11.00am in order to accommodate parade gathering at Hull College for depart by 12.00pm.

ESAG suggested later closing time in QG to be 11.00pm rather than 9.00pm should talent on stage be significant.

Police considering all on duty officers that day would wear rainbow epaulettes.

Fire and rescue are going to wrap an engine in rainbow.

CS to look into event site consultancy to assess and deliver event management plan, site control, and costing for Pride.

CW asks if we have suppliers that they can contact around staging, fencing and security. Chris Clay had noted in ESAG that they should get a consultant in to advise on stewarding plan to inform which firm should provide service and how to do so.

CS notes need for good soundsystem.

CW to send CS route map for parade.

**Programming**

CW noted that Marc Almond’s manager is keen to be involved and keen on performance collaboration.

CW says Jimmy Somerville is a definite no.

CS to provide Erasure management’s email.

CW says KD Lang is planning stuff in Europe next year, more Autumn. Very positive no though.

CW is also in touch with David McAlmont. Thinking of moving to san Francisco but will know by February.

Symphonia also being considered.

**Marcomms**

CS noted the need to ensure Hull 2017 association is not utilised in sponsorship raising and that brand protection will need to be negotiated at a later stage.