**RIBA/LOOK UP 2017 COMPETITION**

Draft Outline Programme v2 010716

2016 **Organisation & Brief**

Agree responsibilities & budget by 29 July

Agree brief & programme by 26 Aug

**Competition Launch/Competitor Selection**

EOI Invitation & Outline Brief issued:12 Sept (3 weeks) – up to x practices

RFC’s by 23 Sept

EOIs submitted by: 30 Sept[[1]](#footnote-1)

EOIs reviewed/final shortlist w/c 02 Oct[[2]](#footnote-2)

Competition Invitation issued 09 Oct (3 practices)

**Competition**

Competitor Site Visits w/c 17 Oct

2017 Competition submissions 09 Jan[[3]](#footnote-3)

Presentations & Review w/c 09 Jan

Winner Announced 17 Jan

**Detail Design & Consents**

Detail Design 23 Jan – 24 Feb (5 weeks)

Consents 20 Jan – 21 April (8 weeks)

**Fabrication/Installation**

Fabrication 24April – 11 Aug (16 weeks)

Installation 14 – 23 Aug

Launch 24 Aug

Freedom Festival 1-4 Sept

**On Site**

On site 25 Aug – 27 Oct (8 weeks)[[4]](#footnote-4)

1. EOIs to include statement re approach to architect/artist collaboration, named lead designers, practice cv’s, 500 word statement ‘what we want to do’ [↑](#footnote-ref-1)
2. Review Panel to include 2 or 3 ‘advisors’, comment through process and judge final submissions [↑](#footnote-ref-2)
3. Submissions to include model to common scale, visuals, material samples, written description and outline costings (to assess reasonable degree of aesthetic, cost, programme & technical feasibility) [↑](#footnote-ref-3)
4. Period covers launch of Turner Prize exhibition [↑](#footnote-ref-4)