## Creative Critical Path
event name: Made in Hull
client: Hull City of Culture 2017
event date: 1st to the 7th January 2017
project code:
Revision
[12 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing | [9 empty] | Current week commencing
KEY
Events and Master sheet | [6 empty] | The WW2 and rebuilding | [9 empty] | Fishing | [9 empty] | The Docks | [9 empty] | Migration | [9 empty] | Hull game changers | [9 empty] | Work and industry | [9 empty] | music and culture | [9 empty] | sport | [9 empty] | Art & Literature (poetry) | [9 empty] | Architecture in Hull | [9 empty] | People of Hull | [9 empty] | Visitors to Hull (royal, famous)
Completed
Needs Immediate Action
[6 empty] | Era | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 70's | 80's | 90's | 00's | 30's | 40's | 50's | 60's | 70's | 80's | 90's | 00's
Topic and Clearance
Venue | Landlord or owner for license | Type of Installation | Title | Name of Artists | Clearances orgs.
Queen Victoria Square | City Council | Audio Visual - Projection mapping | The Last 75 years. | Zsolt Balogh | YTA/BBC/Pathe |  | 00's: Now
Beverly Gate | City Council | staging/ props |  | Creative core team and University student | Police CCTV | bar: 00's
White friar Gate: street | Trinity Estates | Audio | CCTV : my street is talking. | Core Team: Dan Jones |  |  | 00's: Now
White friar gate Unit: 3 | Trinity Estates | Interpretation on the outside of the windows | Interp of street | Hull 2017 | NA
White friar gate Unit: 4/5 | Trinity Estates | Audio Visual - LED screens | Character of Hull | Chris Hees | TBC | Football Shirts through the ages | 50's: Rugby
White friar gate Unit: 6 | William Hill | Visual LED x2 (no SX) | Characters of Hull | Invisible flock | NA | Spring bank, Hessel road, Martfleet lane, Brands Home centre: Bench | 00's: now
White friar gate Unit: 8 | Trinity Estates | Visual Installation (no SX) | Characters of Hull | Invisible flock | NA | Boxes and archive projection | 00's: now
White friar gate Unit: 9 | Trinity Estates | Visual Installation (no SX) | Characters of Hull | Invisible flock | NA | Eyes | 00's: now
White friar gate Unit: 16 | Trinity Estates | AV. Back projection. | Characters of Hull | Sodium Productions | TBC | Caravan making production Line | bar: 60's to 80's
White friar gate Unit: 17 | Trinity Estates | Installation and vintage Tv / Audio | Characters of Hull | Sodium Productions | TBC | Archive footage TBC | bar: 70's to 80's
White friar gate Unit: 20 | Trinity Estates | Installation: Print | Characters of Hull | Andy Roe | NA | bar: 80's to 00's
White friar gate Unit: 23 | Trinity Estates | AV, Lx | Characters of Hull | NH/AL. |  |  | 60's: Boxing and Ballet
White friar gate Unit:
White friar gate Unit:
White friar gate Unit:
White friar gate Unit:
White friar gate Unit:
White friar gate Unit:
Zebedee's Yard | Trinity Estates | Sound installation, Lx | The stadium 105db | Invisible Flock | NA | Football (club clearance given) | 80's: Football
Land Of Green Ginger | City Council | installation (light) roaming AV | Hulywood icons | Quentin Butworth | TBC | Hollywood Film lines. | bar: 50's to 90's
Silver Street | City Council | installation (light) roaming AV | Hulywood icons | Quentin Butworth |  | Hollywood Film lines. | bar: 50's to 90's
Scale Lane | City Council |  | Hulywood icons | Quentin Butworth |  | Hollywood Film lines. | bar: 50's to 90's
Scale Lane Straigth | City Council | AV - Projection Mapping | Dignity of Work | Made Amplify | TBC | Working and unemployment | bar: 90's to 00's
Underpass | City Council | AV - 4x screens and sound installation , Lx | The Ghost of Music: Hull people like to party | Jesse Kanda. | BBc/ private/Pathe | bar: 60's to 90's
The Deep and Amphitheatre |  | Lx in deep, AV on deep, AV on ampitheatre wall, sound on one side, sound from Trinity church | Arrivals and departures | Imitating the Dog | BBC/Pathe/YFA/CC | bar: 40's to 60's; 50's to 80's; 60's to 90's; 30's to 00's; 00's to 00's; 60's; 80's; 30's to 00's; 00's; 70's to 80's
The Wash to Humber street (off height street) 1st | City Council | Roaming AV , interactive | you in Hull | Urban Projections | bar: 00's
The Wash to Humber street (off height street) 6th | City Council | Roaming AV , interactive | you in Hull | Urban Projections | bar: 00's
The Wash to Humber street (off height street) 7th | City Council | Roaming AV , interactive | you in Hull | Urban Projections | bar: 00's
Humber Street Gallery | City Council | Outside create your own record and buskers x2: possible Paul Hetton as he started busking in Hull +1. maybe Roland. FD | TBC | Hull 2017 | TBC Private | Dead Bod art work
Fruit (Night 1) | Fruit |  | Pot Luck
Fruit (Night 2) | Fruit |  | Pot Luck |  | Music (live slam) with Lisa Ronson, Aint missbehaving and 3 others across 2 stages | bar: 00's
Fruit (Night 3) | Fruit |  | Pot Luck |  | Talk Night with Nick Evans and Russ Litten, Dean wilson/ other positions/ Literary etc. | Shane rodes wrecking ball press NH. | bar: 00's
Fruit (Night 4) | Fruit |  | Pot Luck | Sean to contact today and tell NH. | Night brought to you by the Adelphi | bar: 00's
Fruit (Night 5) | Fruit |  | Pot Luck |  | Night brought to you by Jay night / out door arts | bar: 00's
Fruit (Night 6) | Fruit |  | Pot Luck | Sean to do. | Comedy night: with Dean Wilson, Luce Beaumount, and Jerremy Hardy, jack Dee friends? | bar: 00's
Fruit (Night 7) | Fruit |  | Pot Luck |  | Art installation and theatre 360 performance | Anna Bean | bar: 00's
|  |  | Pot Luck |  | John Prescot Streets to deputy and lords. Sunk island discs. Kirsty Young or Sue Lawly.
Other ideas to scope:
Screen night with guests -BFI (lizzy frankie / Ben roberts) or BBC (Patrick Holland/ Nick Fraser), jerrmy Thomas, conection to Rank) Mark herman (brassed off). Sean Macallister and Nick showing Hul films and oe of the siria film - Rank films come out of Hull part one, with audience nd clips and the part 2
School Ballet piece.
Bernie Laverick - Humber calling Song - could this be part of the Dead Bod sting? Could he be the other busker.
Kids Choir singing- We are the Humber Calling.
UNICEF Iraq - not sure how this fits.
Missing or light on areas identified
Representation of different groups: now being covered by Imitating the dog and Invisible flock.
Disability and or community activity - solution on community we are talking to the college, community engagement in within Made Amplify piece & Quentin B piece as well as call to actions. Disability TBC. James McGuire / NH to discuss.

## OperationsProject Critical Path
event name:
client: Hull City of Culture
event date:
project code:
Revision
Current week commencing
KEY
Milestones |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 0 |  |  |  | 1 |  |  |  | 0
Completed |  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | May |  |  |  | December |  |  |  | January
Needs Immediate Action |  |  | weeks before Parade
|  |  | days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
dates
|  | notes | name /responsibility
Key Meetings | Internal Project Team Meetings
Creative Project Team Meetings (face to face)
Production agency Conference call (weekly)
Artists Stakeholder Meetings
Internal Debrief
External Debrief
Wash up report meeting
Licensing, Approval & Permissions | Licensing, Approval & Permissions processes commences
Premises License Eel Brook Common (up to xxxxx) submitted
Newspaper advertising of licence application
Premises notice notice of application (28 consecutive days starting from the day after the day the application is made)
Licensing, Approval & Permissions Secured
No Objection from stakeholders
Temporary Traffic Order
Acoustic consultant - pre event background assessment
Acoustic consultant - on the day monitoring and reporting
Resident Mitigation plan developed
Financials /Contracting - Client | Phase 1 budget prepared
Phase 1 Budget approved
Phase 2 budget prepared
Phase 2 budget approved
Phase 3 budget prepared
Phase 3 budget approved
Budget revisions & updates (weekly)
Payment Schedule/ Cancellation Terms
Project Revenue Target met
Reconciliation & Final Invoicing
Audit File
Drawings/ Plans/ Designs | Site layout / plans amends / updates
Plans issued
Traffic Management | Road signage plan produced
Traffic Management Planning
Traffic Management Stewarding plan produced
Contingency planning
Health & Safety | Event Safety Plan as part of ESMP
Contingency planning as part of ESMP
Risk assessments produced alongside the ESMP
Table top exercises
First Aid planning produced
Risk & issue management / risk register development
Crowd Management | Pedestrian Signage Plan produced
Crowd Management Planning as part of ESMP process
Crowd Management Stewarding Plan produced as part of ESMP process
Command and Control panel meetings
Emergency procedures developed
Table Top exercises
Stewarding & Security | Agreement of crowd and traffic management steward resourcing and allocation plans
Site Security planning
Site Security plan produced
Contingency planning
Table top exercises
Steward and security logistical plan agreed
Media Management | Discuss media requirements
Develop accreditation plan
Venue Management | Investigate ELT position
Technical Production | Production Schedule
Radio Communications Plan produced
CCB Barrier assessment
ELT Specification
Production Compound/Accreditation Compound - Specification
PA System - Specification produced
Toilets - Specification produced
Power - Specification produced
Cable management
Viewing platforms
Trakway
Submit Production Plans to Local Authorities
Signage Planning | CM Signage Plans compiled
CM Signage Plan authorised/signed off
CM Art work to graphics company
Health & Safety / CMP Signage produced
CM Signage installed
TM Signage plans compiled
TM Signage plans authorised/sign-off
TM Signage produced
TM Signage Installed
Financials/Contracting - Suppliers | Supplier Terms & Conditions
Supplier Payment Schedule
POs
Hull City of culture and xx agency Operations | Insurance
Onsite IT Requirements/ Scoping Doc
Onsite Financial Requirements
Onsite Equipment Requirements
Project Overview
Onsite Schedule & Key Docs
Job Close Processes
Crew and project team logistics | Accommodation
Travel
Refreshments
Accreditation- different levels and production agreed.
Crew and performer Welfare
Crew Handbook
Legal Requirements | Identify legal requirements e.g. planning permission/ licenses
Obtain appropriate permissions/ licenses
Data sharing agreement
Sustainability | Identify project team champion
Stakeholder Register
Communication Plan with stakeholders
Sustainability Management Tracker
Event Impact Assessment

## Stakeholder Meeting dates
event name:
client: Hull City of Culture | [12 empty] | Current week commencing
event date: 1st Jan to the 14th Jan 2017 | [12 empty] | `
project code:
Revision: |  |  | No. of Months | 4 |  |  | 5 |  |  |  | 4 |  |  |  |  | 3 |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | January |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | weeks before Happening |  |  | 15 | 14
|  |  | days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  |  | dates | 13 | 20 | 27th | 3rd
Key Dates & Trigger Points |  | notes | name /responsibility
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Dates - Scenarios |  |  |  |  | 25
25
Core Group Milestones | First meeting of core group to consider options dates, routes and format of live parade. Discuss possible dates. |  |  | 17
Second core stakeholder group meeting
Full authority and stakeholder meeting to review key planning documentation regarding format and placemnet
Full authority and stakeholder meeting to review dates, route and format.
Stakeholder meeting to update on placement, Live event, finalise command and control structure, review resident mitigation plan etc.
Meetings of sub groups to discuss and agree specific aspects of the parade e.g. – emergency service liaison, publicity, traffic measures, command and control etc.
Final full authority and stakeholder meeting if required.

## Community Engagement Plan
event name:
client: Hull City of Culture.
event date:
project code:
Revision: Rv
Current week commencing
`
|  |  | No. of Months | 4 |  |  | 3 | 5 |  |  |  | 4 |  |  |  |  | 3 |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | January |  |  | February | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | weeks before Parade |  |  | 15 | 14 | 14
|  |  | days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  |  | dates | 13 | 20 | 27th | 3rd | 3rd
Key Dates & Trigger Points |  | notes | name /responsibility
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Parade Dates - Scenarios |  |  |  |  | 25
25
Community Engagement Comms Plan | Agree Locations can take place
Detailed assesement and understanding of impacts
Agree advice and information / develop and finalise factsheet
Submit TMO / Premises Licence
Inform PR & Media?
Community & stakeholder engagement - ongoing comms
Community & stakeholder engagement - letter & map highlighting route / closures / estimated timings
Hull website live with copy & map highlighting route / closures / estimated timings
BHF website live copy & map highlighting route / closures / estimated timings
Day Activity.
Online comms messaging
Hotline for residents to call?

## Trigger Overview
event name:
client: Hull City Of Culture
event date:
project code:
Revision: Rv_ |  | No. of Months | 0
Month
|  | days | m | m | m | m
dates
name /responsibility
Key Dates & Trigger Points
Bank Holidays | Christmas day
boxing day
new years day
Other relevant | bank holidays and other dates.
Possible Scenarios