## Summary (hidden)
Tab name: | 1 |  | Tab name: | Tab name: | Tab name:
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!

## Overview Timeline
[8 empty] | NOV |  | DEC |  |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
ITEM | START | END | responsibility | Stakeholder? | not started | in progress | complete | time axis 2016-11-21 to 2018-01-01
PROJECT MANAGEMENT | bar: 2016-11-21 to 2018-01-01
Partners Co-production Agreement | 2016-11-21 | 2016-12-26 |  | Y | bar: 2016-11-21 to 2018-01-01
Venue Negotation Complete | 2016-11-21 | 2016-12-12 | bar: 2016-11-21 to 2018-01-01
BBC Rights Acquisition of source text - for all partners | 2016-11-21 | 2016-12-12 | bar: 2016-11-21 to 2018-01-01
Project Sub-teams to Establish - MarComms; | bar: 2016-11-21 to 2018-01-01
Community Engagement |  |  |  | Y | bar: 2016-11-21 to 2018-01-01
Project Management inc Contracting | bar: 2016-11-21 to 2018-01-01
Digital | bar: 2016-11-21 to 2018-01-01
[8 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
COMMUNITY ENGAGEMENT | bar: 2016-11-21 to 2018-01-01
Northern Ballet Training with Hull College | 2016-11-26 |  |  | Y | bar: 2016-11-21 to 2018-01-01
Northern Ballet Recruit Hull Dancer | 2016-11-26 |  |  | Y | bar: 2016-11-21 to 2018-01-01
Deadline for schools & community info | 2017-02-13 | 2017-02-13 | bar: 2016-11-21 to 2018-01-01
Deadline for Hello Hull publication | Ian Read to confirm | bar: 2016-11-21 to 2018-01-01
Circulation to schools & Community | 2017-02-13 | 2017-02-13 | bar: 2016-11-21 to 2018-01-01
Schools & Community Engagement | 2017-04-01 | 2017-06-30 | bar: 2016-11-21 to 2018-01-01
Children's Laureate Event at City Hall | 2017-06-07 | 2017-06-07 |  | Y | bar: 2016-11-21 to 2018-01-01
Mister Maker at City Hall | 2017-06-10 | 2017-06-10 | bar: 2016-11-21 to 2018-01-01
[8 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
COMMUNITY FILMING | bar: 2016-11-21 to 2018-01-01
BBC secure Cbeebies Talent | 2016-11-26 | bar: 2016-11-21 to 2018-01-01
Recce locations | 2016-12-19 | 2017-01-09 | bar: 2016-11-21 to 2018-01-01
Secure location permissions / licences | 2016-12-19 | 29/02/2017 | bar: 2016-11-21 to 2018-01-01
Partners scope community Filming plans | 2016-12-05 | 2017-02-26 | bar: 2016-11-21 to 2018-01-01
Children's Literature Festival | 2017-06-26 | 2017-07-02 | bar: 2016-11-21 to 2018-01-01
Filming at Children's Lit Fest | 2017-07-01 | 2017-07-02 | bar: 2016-11-21 to 2018-01-01
[8 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
[8 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
PRODUCTION LIVE | bar: 2016-11-21 to 2018-01-01
Draft Performance Schedule | 2016-12-05 | 2016-12-05 | bar: 2016-11-21 to 2018-01-01
Get In to Venue | 2017-08-07 | 2017-08-07 | bar: 2016-11-21 to 2018-01-01
Technical week | 2017-08-07 | 2017-08-13 | bar: 2016-11-21 to 2018-01-01
Performance week | 2017-08-14 | 2017-08-19 | bar: 2016-11-21 to 2018-01-01
Get Out Complete | 2017-08-21 | 2017-08-21 | bar: 2016-11-21 to 2018-01-01
[8 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
[8 empty] | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
MARCOMMS & TICKETING | bar: 2016-11-21 to 2018-01-01
Initial Public Announcement | 2016-09-22 | 2016-09-22 | bar: 2016-11-21 to 2018-01-01
Partners MarComms Team Meeting | 2016-12-12 | 2016-12-12 | bar: 2016-11-21 to 2018-01-01
Image Creation complete by | 2016-12-12 | 2016-12-12 | bar: 2016-11-21 to 2018-01-01
Brochure Copy | 2016-12-12 | 2016-12-12 | bar: 2016-11-21 to 2018-01-01
Mar Comms Plan - High Leve | 2017-01-16 | bar: 2016-11-21 to 2018-01-01
Mar Comms Plan - Detailed | 2017-02-06 | bar: 2016-11-21 to 2018-01-01
Season Brochure | 2017-02-20 | 2017-02-20 | bar: 2016-11-21 to 2018-01-01
On Sale DAte - All Tickets | 2017-04-10 | bar: 2016-11-21 to 2018-01-01
Second PR Annoucement | 2017-04-10 | bar: 2016-11-21 to 2018-01-01
Remote Box Office Set Up | 2017-08-07 | bar: 2016-11-21 to 2018-01-01
Remote Box Office Demount | 2017-08-20 | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01
Thing | bar: 2016-11-21 to 2018-01-01

## Detailed Critical path
Event Name: Great Blueness
Client: Hull City of Culture/ Northern Ballet/CeBeebs
Event Date: August 2017
Project Code:
KEY
Milestones in Progress
Milestone Completed
Needs Immediate Action
Key Meetings | Start Date | End Date | Name / Responsibility
Internal Project Team Meetings (BBC, Northern Ballet and HCC)
Creative Project Team Meetings (face to face)
Production Conference call (weekly)
Stakeholder Meetings
Internal Debrief
External Debrief
Wash up report meeting
Design for Community Engagement.
Creative kick off meeting with key internals.
Identify venues
Create deck for briefing and brief
Designer identified for Environmental community engagement
contracted: Designer chosen.
Phase 1 identify top 3 locations and present to wider project team.
Phase 2 and engagement with community surrounding areas short listed.
sign off of concept
design development
production development
tech development
Budget development
Sign off and agree.
Creative for other aspects (show)
Creative Kick off Project meeting
Core team meeting - Creative workshop
Continuous stakeholder client liaison
Present environmental creative themes and core concepts to stakeholders
Review of creative themes and core concepts with wider teams (monthly meeting moving to fortnightly.)
Approval of scope on creative community core concepts
3D scope of works briefed and commenced. (design)
Present technical production for approval
H&S approve technical production and operational plans
Stakeholder meetings (council and community)
Inter-agency liaison with department leads: Design, Interpretation, Digital, Marketing, PR
written word first draft for the show and outer zones.
Development Phase 1
Development Phase 2
Post-event reconciliation with boards for stakeholders.
Finance Stages & Reconciliation
Contracts for venue, community venues- agreed & finalized
Budget approved
Payment schedule agreed
Venue Contract signed
Tic's and payment schedules agreed with suppliers
Purchase orders sent to suppliers
Budget reconciled
General Project
Approval of operational project scope
Stakeholder management: Internal and external
Programming, interpretation and design Concept and strategy development
Operations management draft completed.
Onsite Community Project
Reccees for (external programming)
Load in dates
Tech and creative rehearsal period
Live dates:
Site de-rig and official handover of space back to venue owners.
Sponsorship
Identify key partners/opportunities and VIK deals
Engagement with partners/sponsors
Agree reciprocal benefits for confirmed sponsors and contracts signed if applicable
Agree with Directorate any external branding agreements required.
Collation of partnership deliverables (e.g. company logos, artwork, text for websites)
Activation of sponsor activity
Reconciliation report of worth to the sponsors/client
Creative implementation
Creative briefed (internal and external) with budget parameters
3D Design development (outline) deadline
Creation of technical drawings
Approval/sign-off of final design & 'look & feel'
Environmental production commences
scheme implementation
scheme sign off and install on site sign off.
Way finding
Outline concept and development
Scheme sign off
Artwork
Production
Install on site
Venue for shows-
Layout of venue designed | TBC | TBC
Set designed with seating plan | TBC | TBC
camera locations agreed | TBC | TBC
build(get in) | TBC | TBC
Show dates and number
derig | TBC | TBC
Assets & Products for show
Assets & Product for event identified
Quantities and delivery details agreed
Storage resourced and agreed (including additional costs if appropriate)
Rehearsal scope identification f requirement. (if outside of venue)
Items delivered to site for distribution to required area
Signage, Branding & Way finding design - within the footprint of the venue
Signage & branding requirements identified
Signage & branding spec developed (both community and then reused for show)
Signage & branding spec approved
Print companies agreed
Design templates approved
Design/art working
Print company payment schedule agreed.
Stage 1: sign off process for all branding and signage
All branding and signage sent to print
Print adjustments as required
Branding & signage delivered to site for install
Cross check signage is in correct location
Technical Production
Technical initial briefing and development
Assigned Production team (all stakeholders)
Key technical suppliers agreed
Supplier briefings & recces
Key technical suppliers contracted
Develop technical production
On-going meetings & discussions with technical suppliers
Structural licensing and planning if required
Reconciliation report - technical
Venue Management
Queuing CAD and numbers plan designed and submitted
Site plans developed
Site plans issued to key stakeholders
Site plans revised and reissued as required
Final site plans submitted to key stakeholders and departments.
Onsite schedule developed
Onsite schedule issued to key stakeholders
Onsite schedule revised and re-issued as appropriate
Final onsite schedule issued to key stakeholders
Power - specification produced
Cable management
Operational Management
Radio Communications Plan produced
Operational space requirements defined
Vehicle requirements defined and scheduled
IT requirements identified
Event Capture (Videographer & Photographer)
BBC - content capture team meetings scheduled.
Delivery of assets from capture team
Complete the post-event internal reporting documents, inclusive of upload of images etc.
Edit commences and post production
agreed credits to Tv show.
Accreditation (Special events)
accreditation mechanic and models discussed
accreditation developed for different events
Onsite technical/service requirements identified - case by case basis
Onsite technical/service requirements agreed
Miscellaneous
Contingency budgeting
IT requirements identified
IT requirements confirmed & ordered
Rehearsal schedules submitted and agreed
Onsite briefing plans submitted and agreed
Event operations management plan distributed
Media and Press Community phase of project.
Numbers identified and confirmed
Accreditation process confirmed
Technical requirements confirmed
Media (local) engaged and Plan placed together.

## Stakeholder
Holiday dates Dates & Trigger Points |  | responsibility
Annual Leave- Hull city of culture:
Niccy Hallifax | 20th Feb - 7th March 2017
Henrietta Duckworth
Gareth Huges Holiday
David Watson holiday
Ian Read Holiday
Jenny Hutt Holiday
BBC Holidays to be added
Northern Ballet holidays to be added.
Bank Holidays | New years day
Easter Holidays
May day
Other relevant dates
Possible Dates - Scenarios
Stakeholder Group Milestones | First meeting of stakeholders to consider options dates, format of live community activation, show and recordings. Discuss possible dates.
Second core stakeholder group meeting (SAG)
Third core stakeholder group meeting (SAG)
Final core stakeholder group meeting (SAG)
Full authority and stakeholder meeting to review key planning documentation regarding format and placement
Full authority and stakeholder meeting to review dates, route and format.
Venue meetings
Meetings of sub groups to discuss and agree specific aspects of the parade e.g. – emergency service liaison, publicity, command and control etc.
Final full authority and stakeholder meeting if required for community project.

## Community enagement_licencing.
Key Dates & Trigger Points |  | Dates | Name / Responsibility
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible show Dates - Scenarios
Community Engagement Comms Plan | Agree Locations can take place
Detailed assesement and understanding of impacts
Agree advice and information / develop and finalise factsheet
Submit TMO / Premises Licence
Inform PR & Media?
| Community & stakeholder engagement - ongoing comms | 28 days prior to activation begins.