## Calendar 2017
| 2017-04-01 |  | 2017-05-01 |  | 2017-06-01 |  | 2017-07-01 |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  | 2017-10-01 |  |  | 2017-11-01 |  | 2017-12-01 |  |  | 2017-01-01
|  |  | Research artists, write and sign off press release and artist biographies. Tate and artists sign off. Lead images selected and copyright cleared. Tate and artists sign off. |  | Marketing identity developed and signed off by Tate. [End] Loan letters sent. [End] Awards presenter confirmed. |  | [Mid] Deadline for copy of Tate Members guide (Sept release) |  | [Mid] Deadline for Tate Members E-Bullitin (Sept release) Curatorial media training (if required)
Artists films made.
1 | Sa |  | Mo |  | Th |  | Sa |  | Tu |  |  |  | Fr | INSTALLATION INSTALLATION INSTALLATION |  | Su | EXHIBITION OPEN EXHIBITION OPEN EXHIBITION OPEN |  | We | EXHIBITION OPEN EXHIBITION OPEN EXHIBITION OPEN | Fr | EXHIBITION OPEN EXHIBITION OPEN EXHIBITION OPEN | Awards press release written, approved by parties Internal briefing pack completed and circulated to staff attending awards | Mo | EXHIBITION OPEN | New Year's Day
2 | Su |  | Tu |  | Fr |  | Su |  | We |  |  |  | Sa |  |  | Mo |  |  | Th |  | Sa |  |  | Tu
3 | Mo |  | We | Press announcement event | Sa |  | Mo | Outline volunteer request (12 weeks notice) | Th |  |  |  | Su |  |  | Tu |  |  | Fr |  | Su |  |  | We
4 | Tu |  | Th |  | Su |  | Tu | Final exhibition content agreed with H17 Proposed exhibition layout submitted 'The final specification date' | Fr | Guest list for opening event signed off by parties |  | Final images for catalogue supplied to the partners by artists | Mo |  |  | We |  |  | Sa |  | Mo |  |  | Th
5 | We |  | Fr | Artists contracts issued | Mo | All initial ideas/exhibition proposals submitted to H17 by artists | We |  | Sa |  |  |  | Tu |  |  | Th |  |  | Su |  | Tu |  | 10am Jury meeting @ Ferends to decide winner AM Press preview PM Technical TV rehearsal PM Awards Ceremony | Fr
6 | Th |  | Sa |  | Tu |  | Th |  | Su |  |  |  | We |  |  | Fr |  | Names and emails for artists' guests for Awards Ceremony to be received Tate guest list for Awards Ceremony to be received | Mo |  | We |  |  | Sa |  | Exhibition end
7 | Fr |  | Su |  | We |  | Fr |  | Mo |  |  |  | Th |  |  | Sa |  |  | Tu |  | Th |  |  | Su | Deinstall begins
8 | Sa |  | Mo |  | Th |  | Sa |  | Tu |  |  |  | Fr |  |  | Su |  |  | We |  | Fr |  |  | Mo | DEINSTALL
9 | Su |  | Tu |  | Fr |  | Su |  | We |  |  |  | Sa |  |  | Mo |  |  | Th |  | Sa |  |  | Tu
10 | Mo |  | We |  | Sa |  | Mo |  | Th |  |  |  | Su |  |  | Tu |  | Guest list for awards ceremony to be signed off by all parties | Fr |  | Su |  |  | We
11 | Tu |  | Th |  | Su |  | Tu |  | Fr | Opening event invites sent out |  |  | Mo |  |  | We |  |  | Sa |  | Mo |  |  | Th
12 | We |  | Fr |  | Mo |  | We |  | Sa |  |  |  | Tu |  |  | Th |  |  | Su |  | Tu |  |  | Fr
13 | Th |  | Sa |  | Tu |  | Th |  | Su |  |  |  | We |  |  | Fr |  |  | Mo |  | We |  |  | Sa
14 | Fr |  | Su |  | We |  | Fr | Names and emails for artists' guests for Opening Ceremony to be received by H17 Tate guest list for Opening Ceremony to be received by H17 | Mo | Exhibition catalogue signed off by Tate and artists and sent to print Volunteer shift offer deadline (6 weeks notice) |  |  | Th |  |  | Sa |  |  | Tu |  | Th |  |  | Su
15 | Sa |  | Mo | w/b 15 May Artist briefing meeting @ Ferens | Th |  | Sa |  | Tu |  |  |  | Fr |  |  | Su |  |  | We |  | Fr |  |  | Mo
16 | Su |  | Tu |  | Fr |  | Su |  | We |  |  |  | Sa |  |  | Mo |  |  | Th |  | Sa |  |  | Tu
17 | Mo |  | We |  | Sa |  | Mo |  | Th |  |  |  | Su |  |  | Tu |  |  | Fr |  | Su |  |  | We
18 | Tu | Assistant Producer Start Tate send long list to H17 | Th |  | Su |  | Tu |  | Fr |  |  |  | Mo |  |  | We |  |  | Sa |  | Mo |  |  | Th
19 | We |  | Fr |  | Mo |  | We |  | Sa |  |  |  | Tu |  |  | Th |  |  | Su |  | Tu |  |  | Fr
20 | Th |  | Sa |  | Tu |  | Th |  | Su |  |  |  | We |  | Opening press release written, approved by parties Internal briefing pack completed and circulated to staff attending the Press Preview event | Fr |  | Awards Ceremony invites sent out | Mo |  | We |  |  | Sa
21 | Fr | Research @ Tate Britain | Su |  | We |  | Fr |  | Mo | PRE-FABRICATION PRE-FABRICATION |  |  | Th |  |  | Sa |  |  | Tu |  | Th |  |  | Su
22 | Sa | Research @ Tate Britain | Mo |  | Th |  | Sa |  | Tu |  |  |  | Fr |  |  | Su |  |  | We |  | Fr |  |  | Mo
23 | Su |  | Tu |  | Fr |  | Su |  | We |  |  |  | Sa |  |  | Mo |  |  | Th |  | Sa |  |  | Tu | Artwork returned to lenders
24 | Mo | Jury meeting to shortlist 4 nominees @ Tate Tate Director calls artists Tate confirms 4 artists w/ H17 | We |  | Sa |  | Mo |  | Th |  |  |  | Su |  | Exhibition install complete | Tu |  |  | Fr |  | Su |  |  | We
25 | Tu | Artists confirmed and letter of intent issued | Th |  | Su |  | Tu |  | Fr |  |  |  | Mo | AM Press preview event @ Ferens PM Opening event @ Ferens |  | We |  |  | Sa |  | Mo |  | Christmas Day | Th
26 | We |  | Fr |  | Mo |  | We |  | Sa |  |  |  | Tu | Exhibition opens to the public |  | Th |  |  | Su |  | Tu |  | Boxing Day | Fr
27 | Th |  | Sa |  | Tu |  | Th |  | Su |  |  |  | We | EXHIBITION OPEN |  | Fr |  |  | Mo |  | We |  |  | Sa
28 | Fr |  | Su |  | We |  | Fr | Exhibition catalogue essay sent to artists for approval | Mo |  | August Bank Hol. |  | Th |  |  | Sa |  |  | Tu |  | Th |  |  | Su
29 | Sa | Press release including artist citations written and approved by all parties Briefing pack complete and circulated to staff attending announcement event | Mo |  | Th |  | Sa |  | Tu | Collection date Artwork to be collected and/or delivered to Ferens |  |  | Fr |  |  | Su |  |  | We |  | Fr |  |  | Mo
30 | Su |  | Tu |  | Fr |  | Su |  | We | INSTALLATION |  |  | Sa |  |  | Mo |  |  | Th |  | Sa |  |  | Tu
31 |  |  | We |  |  |  | Mo | Final Volunteer request deadline (8 weeks notice) | Th | [6 empty] | Tu |  |  |  |  | Su |  |  | We
| Programming |  | Marketing/Comms/Digital |  | Development/Events |  | KEY EVENT HAPPENING

## Sheet1
Turner Prize Timeline 2017-18
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Mar | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
[6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13
Apr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
[18 empty] | Assistant Producer Start |  |  | Research @ Tate Britain | Research @ Tate Britain |  | Jury meeting to shortlist 4 nominees @ Tate | Artists confirmed and letter of intent issued |  |  |  | Press release including artist citations written and approved by all parties
[18 empty] | Tate send long list to H17 | [5 empty] | Tate Director calls artists |  |  |  |  | Briefing pack complete and circulated to staff attending announcement evening
|  |  | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | Tate confirms 4 artists w/H17
May | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We |  | Fr | Sa | Su | Mo | Tu |  | Th | Fr | Sa | Su | Mo | Tu | We
Press announcement event
14 Mo: 19; 15 Mo: 20 |  |  |  |  | 21 | [6 empty] | 22
Jun | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
[5 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26
Jul | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  |  | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31
Aug | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th
[7 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35
Sep | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
|  |  |  | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39
Oct | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu
|  | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44
Nov | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th
[6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48
Dec | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
|  |  |  | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31