## Sheet1
HPSS/ PRODUCTION SCHEDULE NOTES |  |  | Minutes
13th-19th February | Archie | RIG
1. Gareth and James needed to supervise build of tallescope
2. HPSS to provide 6 of Meet Fred's fixture requirements
3. Archie to provide 2 of Meet Fred's fixture requirements (2 Source Fours)
4. Tine to provide Red Shed's LX plan using all Archie fixtures
5. PA REQUIREMENTS TO BE APPROVED BY BEN / TECHNICIAN
6. 2 or 3 TECHNICIANS?
7. Tues 21st Theatre not in use until 4pm
8. 4 acclaim fresnels to be taken to drama studio (3 already in there?)
Wednesday 22nd | Sirius | MR B
1. 1 crew member 6am start to clear classroom, set up steel deck and rig light.
MEET FRED
2. 2.5 hours LX rig: currently HEAVY moving LEDs rigged which could provde difficult?
3. Needs entire own inventory because Archie can only rig the week before?
PICTURE HOUSE
4. Lumen technicians will arrive to set up their projector
| Kingswood | MEET FRED
5. Inventory has all light fixtures
6. 2 hours to rig LX
| North Point | PIGEON DETECTIVES
7. Centre closes at 6pm
8. Steel deck to be brought from Sirius Academy?
9. 1 hour to set up steel deck
10. 1.5 hours to set up all PA
11. 1.5 hours to set up all LX
12. Total 6 hours- end at midnight
Thursday 23rd | North Point | PIGEON DETECTIVES
1. Centre closes at 6pm
2. Artists arrive immediately for LX focus and sound test
3. 1.5hours for focus and test
4. Get-out start at 11.30pm
5. 3 hour get-out ending at 2.30am?
| Archie | MEET FRED
6. 2 crew to help on the day!
JOAN
7. 2 hours to rig LX?
8. Get-in to be quiet as above theatre with Meet Fred performance
9. Get-out to be through Agora not Winter Garden
10. Leave drama studio as Mark Thomas dressing room
| Winifred | MR B
11. Unideck to be collected from Freedom Centre
| Gemmell | SECRET GIG
1. All day access: 8am - 11pm
Friday 24th | Archie | RED SHED
1. Decision: rig sound equipment as rigging light equipment the week before? Note: School will be rehearsing Rock of Ages. OR rig sound equipment on day of first performance. EITHER WAY 2 CREW WILL BE NEEDED THIS DAY
MR B
2. After Red Shed get-out, move sofas from common room and move billboards into common room
| Sirius | PIGEON DETECTIVES
3. Have the mainhall, to yourselves, all day, how long would you like? - separating each task into hourly sections for production schedule. Including: when should the band arrive?- Currently 5pm
| North Point | JOAN
1. Centre opens at 8am (access before from whenever speculated) My plan to suggest to Louise: equipment get-in (- the only bit that will cross public route) beforehand. All rigging to be cordoned off throughout the day
2. Centre closes at 6pm. Seating to be brought from Winifred Holtby
3. Get-out to be careful so as to not disturb Hekima
| Winifred | MR B
1. Crew member present for shows in case of fault
2. Uni Deck to be taken to Sentamu after get-out
Saturday 25th | Archie | MR B
1. Change of room: common room, 4th floor, careful with equipment upstairs
2. De-rig all Meet Fred and Red Shed lights
| Freedom | PIGEON DETECTIVES
3. Have the theatre, to yourselves, all day, how long would you like? - separating each task into hourly sections for production schedule. Including: when should the band arrive?- Currently 5pm
| Hymers | JOAN
4. Space available all day, to yourselves, how long do you need before company arrive? - Currently 4 hours.
5. Get-out to be as quiet as possible - very close to Hekima performance
| Sirius | SIRIUS
1. Lights pre-rigged from Wednesday 22nd (because earliest show: 1pm)
2. De-rig may need to include re-rigging lights taken away, how long? What equipment- for moving LEDs
| Kingswood | RED SHED
1. Inventory will have all fixtures
2. Can rig some with Meet Fred on Wed 22nd. Depending on plan
3. Potentially will need to return lights to their original positions