## Sheet1
In the box below, please provide a short explanation of how the Production of Made in Hull could have been improved?
Respondents | Response Date | Response Text | Categories
1 | 2017-01-26 16:21 | Explanation of the above answers. I can only speak for myself. The sound was quite hard to hear. Not just myself, I saw people having to lean in very close to hear the audio on my piece. The lighting was not right until the very last night, even though I had said so from the first night. And that finally happened because I was there to direct it. So though the lighting team were very professional with me, they didn't have an understanding of what I, the artist wanted.
2 | 2017-01-26 14:46 | The structure for our projectors could have been boxed in and waterproofed as was agreed in the initial conversations about the technical specifications for the project. Because this was not done there was equipment broken and damaged due to water and weather. The result was our tech time was only half of what it should have been which led to our piece not being shown for the first hour of the launch of Made in Hull. The result was thousands of people missing our piece on the first night.
3 | 2017-01-26 12:19 | Communication between on the ground production staff and artists wasn't always great - that would certainly have improved the smooth running of the project both before and during installation.
4 | 2017-01-25 19:09 | Nothing
5 | 2017-01-23 10:39 | Errors occurred during installation due to lack of communication, which led to lack of time to perfect certain things through testing.