## Venue Contacts
Hull 2017
Network Neighbourhood Touring
Venue Contacts
Organisation | Area | Venue Type | Capacity | Contact Name | Role | Tel | Email | Notes | Website | Address
ARCHBISHOP SENTAMU ACADEMY | East |  |  | Jenny Rose | Assistant PA to Principal |  | rose.j3@sentamuacademy.org
Kevin Matchett / Finance Director
|  |  |  | James Crook / |  |  |  | Manages community bookings
|  |  |  | Pete Dooks | Site Manager | mobile 07713 922619. | dooks.p@sentamuacademy.org ,
Freedom Centre | East | Theatre | 300 | Tony Forrester | Centre Manager |  | tony.forrester@freedomcentre.info
Expressive Arts Centre
|  | Festival Stage | 1000
Kingswood Academy | North | Theatre | 250 | Christine Gillard | Learning Centre Manager | 01482 879967 x274 | cgillard@thekingswoodacademy.org |  |  | Wawne Road, Hull, HU7 4WR
|  | Event Space | 200
Boulevard Academy | West | School Hall | 200 | Rachel Waters | Teacher | 01482 217898 | rachel.waters@theboulevardacademy.com |  |  | Massey Close, Hull, HU3 3QT
|  | Sports Hall | 400
Hymers School | West | Old Gym | 150 | David Elstone | Headteacher |  | dcelstone@hymers.org
|  | Theatre | 220
|  | Mem Hall | 150
|  | School Hall | 500
William Gemmell Social Club | West
Walton St Social Club | West |  |  | Mike
Winifred Holtby Academy | North | Theatre | 200 | Gemma Ryan Blackburn | Community Lettings Manager | Mob: 07972 363515 | E: g.ryan-blackburn@robertson.co.uk |  |  | Andrew Marvell College, Barham Road, Hull HU9 4EE
Drama Studio
Sports Hall
Western Library | West
Malet Lambert Academy | East
East Park | East |  |  | Alison Walker

## Project Plan
Hull 2017
Network Neighbourhood Touring - Timeline & Milestones
2016 | Milestone | Notes
July | NNT Programming Team Meeting | Monthly Meeting Through Project
Local Venue & Project Team Recruitment
NNT Brand & Marketing Comms Plan Developed
Aug | NNT Programming Team Meeting
Pilot Events Programme Confirmation
NNT Brand & Marketing Comms Plan Confirmed
Sept | NNT Programming Team Meeting
Hull 2017 Programme Launch - inc NNT
Project Team Start
Oct | NNT Programming Team Meeting
| Half Term - Pilot Events | One Event per area
Nov | NNT Programming Team Meeting | Debrief Pilot Events
Programming Festival 1 - Confirmation
Dec | NNT Programming Team Meeting
Contracts Issued Festival 1
2017
Jan | NNT Programming Team Meeting
Festival 1 Programme Launch & Tickets Release
Programming Festival 2 - Confirmation
Feb | NNT Programming Team Meeting
Half Term - Festival 1
Contracts Issued Festival 2
March | NNT Programming Team Meeting
Festival 2 Programme Launch Tickets Release
April | NNT Programming Team Meeting
May | NNT Programming Team Meeting
Half Term - Festival 2
June | NNT Programming Team Meeting
Programming Festival 3 - Confirmation
July | NNT Programming Team Meeting
Contracts Issued Festival 3
August | NNT Programming Team Meeting
Festival 3 Programme Launch & Tickets Release
Sept | NNT Programming Team Meeting
Oct | NNT Programming Team Meeting
Half Term - Festival 3
Nov | NNT Programming Team Meeting
Programming Festival 4 - Confirmation
Dec | NNT Programming Team Meeting | Future Festival Planning
Contracts Issued Festival 4
2018
Jan | NNT Programming Team Meeting
Evaluation Festivals 1 - 3
Feb | Half Term - Festival 4
March | NNT 2017 Project Concludes

## Project Mgt
Hull 2017
Network Neighbourhood Touring
Project Governance
Project Management
Hull 2017 Core Team | NNT Project Team | Local Programme Network | Touring Productions
Exec Producer | 1 x Programme Director | 1 x Venue Manager & Programming Lead (each venue) | Artists
| 1 x Project Administrator (p/t) | 1 x Venue Technical Liaison (each venue) | Booking Agent
Programme Consultants / Local Partners & Promoters
Technical & Operations Team | 1 x Technical Co-ordinator (p/t) | 1 x Local Technical Manager (each area) | Technical Manager
Artist Liaison |  | 2 x Local Technicians (each area) | Technicians
1 x Technical Apprentice (each area)
Marketing & Comms Team |  | 1 x Local Marketing & Engagement Manager (each area) | Marketing Agency
Community Engagement Team |  | 2 x Box Office Team (each area) | PR Agency
1 x Marketing & Engagement Apprentice (area area)
Education Director |  | 1 x Schools - Performing Arts Lead Teacher (each school venue)
Volunteering Team |  | 1 x FOH Manager & Volunteers Co-ordinator (each area)
10 x Hull 2017 Volunteers (each area)
Finance Team
Monitoring & Evaluation
(University of Hull Evaluation Partner)
Programming Process
Monthly Programming Meetings of NNT Project Team and Local Venue Leads
Central Location - Hull 2017 Offices | NNT Programme Director (Chair) | Lead Representatives from each venue:
| Project Administrator | 3 x East - Freedom Centre, Sentamu & Malet Lambert
| Technical Co-ordinator | 4 x West - Boulevard Academy, Hymers, Walton St & Gemmell
| Programme Consultant / Local Promoter | 2 x North - Winifred Holtby & Kingswood
Hull Programming Partners ( Hull Dance; HICP; Humber Mouth; Hull Truck)
Hull 2017 Exec Producer
| Hull 2017 MarComms Liaison | 3 x Local Marketing & Engagement Managers
| Hull 2017 Technical Liaison | 3 x Local Technical Managers from each area
Monthly Area Programming Meetings of NNT Project Team and Area Leads |  | Lead Representative form each venue;
Local Area Location | NNT Programme Director | East - Freedom Centre & Sentamu
| Project Administrator | West - Boulevard Academy, Hymers, Walton St & Gemmell
| Technical Co-ordinator | North - Winifred Holtby & Kingswood
Marketing & Engagement Manager from each area
Duty Technical Manager from each area