## Guidance
RISK NO | DATE REGISTERED | RISK CATERGORY | RISK DESCRIPTION | POTENTIAL IMPACT | LIKELYHOOD | CONSEQUENCE | RISK RANK | PREVENTION PLAN | CONTINGENCY PLAN | OWNER | RESIDUAL SCORE
1 | 2016-12-01 | Artistic | Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | MEDIUM | HIGH | HIGH | Artistic director oversees all artistic content and communicates frequently with other artists. Assistant artists well briefed about artistic vision of project. Initial design meeting all artists present. | Meeting called with whole artistic team if and when issues arise. | Kerith Ogden | MEDIUM
2 | 2016-09-21 | Financial | Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | LOW | HIGH | MEDIUM | Accurate initial forecast in place. Range of quotes sought. Consultation with other stakeholders before project commences. |  | Andrew Kim. | CLOSED
3 | 2016-09-21 | Time | Decision making causes delays | Additional pressure on internal project team | MEDIUM | MEDIUM | MEDIUM | Deadlines for key activity planned in with members of the team aware of these and making decsions well in time for planned activity. | Where pressure is put on Project Manager contingency budget used to pay for extra support / time to resolve issues. | Katherine Warman | MEDIUM
4 | 2016-10-20 | Artistic | Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | LOW | HIGH | HIGH | FULL MarComms plan. Local and knowledgeable community coordinators recruited in order to reach target audience. Proper outreachand engagement programme rolled out in order to reach participants. | More on the ground marketing action put in place. Whole team briefing on spreading the word. | Katherine Warman | MEDIUM
5 | 2016-10-20 | Time | Failure to contract all parties effectively | Inability to deliver project | LOW | HIGH | MEDIUM | Recruitment of project manager used to contract artists / personell. Negotiations handled by Project Manager in timelt fashion. |  | Katherine Warman | CLOSED
6 | 2017-01-05 | Time | Failure to engage creative team | Inability to deliver project | LOW | HIGH | MEDIUM | Contracting trusted artists to deliver project. Use reccomendations where possible. Offer good rates of pay to ensure quality personell recruited. | Use Handmade Parade's extensive network to find other artists who might be avaialble. | Kerith Ogden | MEDIUM
7 | 2016-11-05 | Financial / Time | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | LOW | MEDIUM | LOW | Use PO's correctly to ensure payments managed. Manage expectation about payments. Track payments on system on an ongoing basis. | Missed payments put through as matter of urgency, liaise with partners / suppliers to ensure clear communication. | Katherine Warman | LOW
8 | 2016-11-05 | Artistic / Scope | Failure to secure appropriate venue | Inability to deliver project | MEDIUM | HIGH | MEDIUM | Early discussion with venues / council. Backup plan in place for not securing first choice. Proper hire fees negotiated so all parties happy. | Make a plan to use chosen venue in most effective manner. Move budget to travel costs if 'makes' need to happen off site. | Katherine Warman | MEDIUM
9 | 2017-01-12 | Healthy and Saftey | Failure to secure necessary permissions or licences | Inability to delivery project | LOW | HIGH | MEDIUM | Communicate with relevant council partners at early stage of project. Find out key information and liaise with HCoC team early on to draw on their expertise. | Talk with HoC about any issues arising in apprpriate timeframe. | Katherine Warman | MEDIUM
10 | 2016-10-21 | Artistic / Scope | Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | LOW | HIGH | LOW | Proper briefings with all levels of team working on project. Clear management structure and role remits. Budget considerations taken into account before making key decisions. | Meetings / regular communication between Kerith Ogden and Katherine Warman called to ensure any scope creep managed and targets are being worked to. | Katherine Warman and Kerith Ogden | LOW
11 | 2016-09-20 | Financial / Artistic | Insufficient budget | Inability to deliver project | LOW | HIGH | MEDIUM | Forecasts are consulted upon for accuracy at early point. Project manager recruited early on in order to manage finance. | Handamde Parade's execuitve team used to check budget against past projects. | Andrew Kim | CLOSED
12 | 2016-11-05 | Health and Saftey | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | LOW | MEDIUM | MEDIUM | Early checking of public liability insurance held and documentation kept on hand to share with partners where appropriate. | If the liability runs out, make sure it is scheduled to be renewed in timely fashion | Katherine Warman | MEDIUM
13 | 2016-09-20 | Scope / Artistic | Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | LOW | HIGH | MEDIUM | Project Mananger recruited at earliest point possible. Clear handover between artistic director and project manager. Project manager contracted for suitable amount of hours. Role remits outlined between AD and project manager. | Any confusion arising worked through with good communication. Personell illness / incapacity resolved through delegation of workload. | Katherine Warman and Kerith Ogden | MEDIUM
14 | 2016-09-20 | Time / Artistic | Partners fail to support/deliver as expected | Additional pressure on internal project team. Inability to deliver project effectively. | MEDIUM | HIGH | MEDIUM | Contracting trusted artists to deliver project. Regular face to face meetings. Using local knowledge and hiring local people where possible in order to have most impact. Where issues arise, have backup options in place in terms of personell. Spread workload evenly between team. Clear communication with Hull 2017 when issues arise to gain support / resolve issues. | Earliest instance contact Hull 2017 team in order to raise issue and find solution to problem. Manage issues using existing expertise of Handmade Parade management team. | Katherine Warman and Kerith Ogden | MEDIUM
15 | 2017-01-12 | Time / Financial | Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | MEDIUM | MEDiUM | MEDIUM | Use knowledge from Hull 2017 tech and ops team and City Council to find best contacts for services / suppliers. | Chase up suppliers who fail to respond. Use suppliers with reccomendations and good communication. | Katherine Warman | MEDIUM
16 | 2017-01-05 | Scope / Artistic | Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | LOW | MEDIUM | LOW | Most documents managed by project manager. Other documents stored and shared in Dropbox folder. | Check in with management team if / when any changes made. | Katherine Warman | LOW
17 | 2017-01-12 | Artistic | Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on artists / project team | HIGH | HIGH | HIGH | Reliable documentation to allow others to pick up in someone's absence. Team all aware of each person's role. Backup options for personell in place. | Kerith to ask assistant artists to take on more work. Good communication about capacities discussed before decisions made. | Kerith Ogden | MEDIUM
18 | 2017-12-01 | Artistic | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | LOW | HIGH | MEDIUM | Clearly defined project scope, and aims. Use Artistic Director's extensive experience to make judgement calls about how far reaching project will be. Regular commuication with project manager to manage budget to keep within project scope. | Discuss any changes arising, ongoing conversations about capacity. | Kerith Ogden | MEDIUM
19 | 2016-10-21 | Artistic / Time | Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | HIGH | LOW | MEDIUM | Using experienced artists to lead, less experienced artist work under supervision of lead artists. Regular comunication undertaken to make sure everyone working within their capabilities. | Regular check in with all staff to see if they are happy with work / any capacity issues. | Kerith Ogden, Katherine Warman, Liz Dees, | MEDIUM
20 | 2017-01-05 | Artistic | Suppliers fail to deliver | Inability to deliver project | LOW | HIGH | MEDIUM | Contracts set in place with regular suppliers. Agreements in writing before payment released. Trusted suppliers used for products and services. | Issues brought to thr attention of Kerith Ogden / Katherine Warman who can manage appropriately and involved Hull 2017 team if necessary. | Katherine Warman and Kerith Ogden | LOW
21 | 2016-10-21 | Artistic | Weather or natural environment | Inability to deliver project as intended | MEDIUM | HIGH | HIGH | Artworks are weatherproofed. Suitable date chsoen for outdoor elements.. Indoor alternatives in place for event day. Good communication systems in place in case of bad weather on parade day. | Project Manager to monitor weather forecast and implement contingency plan of alternative event if weather is bad. | Katherine Warman | HIGH

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | Jeff | 3 | 5 | 15 | Suppliers made aware of 30-day payment terms and all been set up on system already. POs raised and awaiting approval. Project budget includes detailed projected cashflow and Finance team are aware. | 2 | 3 | 6 | Open
2 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | Jeff | 3 | 5 | 15 | Not yet determined insurance requirements - on agenda for next project team meeting. | 3 | 5 | 15 | Open
3 | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | Jeff | 4 | 4 | 16 | Scope of project signed off at SLT at greenlight. Detailed project brief attached to commissioning & production agreement. All aware that no additional budget is available for extra activity. | 2 | 4 | 8 | Open
4 | [5 empty] | 0 |  |  |  | 0
5 | [5 empty] | 0 |  |  |  | 0
6 | [5 empty] | 0 |  |  |  | 0
7 | [5 empty] | 0 |  |  |  | 0
8 | [5 empty] | 0 |  |  |  | 0
9 | [5 empty] | 0 |  |  |  | 0
10 | [5 empty] | 0 |  |  |  | 0
11 | [5 empty] | 0 |  |  |  | 0
12 | [5 empty] | 0 |  |  |  | 0
13 | [5 empty] | 0 |  |  |  | 0
14 | [5 empty] | 0 |  |  |  | 0
15 | [5 empty] | 0 |  |  |  | 0
16 | [5 empty] | 0 |  |  |  | 0
17 | [5 empty] | 0 |  |  |  | 0
18 | [5 empty] | 0 |  |  |  | 0
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...