## Front Page
Front Page
Substance
Expenditure | Projected | Projected Actual
2016 Launch Event | 4272 | 4272
Future Forum | 38125 | 33376
City Hall /Substance Live | 71650 | 67472.01
Film Programme | 16085.76 | 15118.76
Adelphi | 4050 | 4050
MIF | 7600 | 7600
Project Fees | 21000 | 21000
Travel Costs/Meetings | 2000 | 2000
Project costs to date | 687
Total | 165469.76 | 154888.77
Contracted Expenduiture
Substance Ltd | 102000 | 62000
Total | 102000 | 62000
Hull 2017 budget
Hull 2017 | 125000 | 125000
Ticket income | 9000 | 5000
BFI Income | 19000 | 19000
Total | 153000 | 149000
Variance
Projected Expenditure | 165469.76 | 154888.77
Actual Budget | 153000 | 149000
Variance | -12469.76 | -5888.77

## 2016 Launch Event
Launch Event 2016
Venue hire |  |  | Production | 1516
|  |  | Talent | 1895
Total |  |  | Misc | 648
|  |  | Marketing | 213
Production
Production costs | 1291 |  | Total | 4272
Dressing Room | 45
Security | 180
Total |  | 1516
Talent
Magnetic North | 1400
Will Alsop | 375
DJ | 120
Total |  | 1895
Misc
Rider | 45
catering | 219
Travel | 179
Drinks | 141
Hotel | 64
Total |  | 648
Total
Marketing
Marketing: EDM | 86
Marketing: social | 100
Wrist bands | 27
Total |  | 213

## Future Forum
Future Forum | Budget |  | Projected Actual | C350.ZK106.K245 | Budget |  |  | Projection
[5 empty] | Venues |  | 1650 | Venues | 1150 | C350.ZK106.K245
Venue |  |  |  |  | Production |  | 14500 | Production | 15494 | C350.ZK106.K245
Fruit | 800 |  | 650 |  | Access |  | 2000 | Access | 0
Hull Minster | 450 |  | 500 |  | Marketing |  | 3350 | Marketing | 2893.5 | ZK109.K138.C350
1@thedock | 400 |  | 0 |  | Catering |  | 3600 | Catering | 2692.5 | C350.ZK112.K120
C4DI Theatre |  |  | 0 |  | Panels |  | 11400 | Panels | 9150 | C350.ZK101.K208
[5 empty] | Travel/Acc |  | 1625 | Travel/Acc | 1996 | C350.ZK101.K208
Total |  | 1650 |  | 1150 | Total |  | 38125 | Total | 33376
Production* |  | C350.ZK106.K245 |  |  |  | Hull 2017 | 10225
General | 10000 |  |  |  |  | Substance | 27900
Conference seating (delgates and panels) |  |  | 1500
EMs |  |  | 200
HPSS |  |  | 6677
North East Medical |  |  | 275
Radios |  |  | 0
Van |  |  | 0
Hull Minster |  |  | 300
Operations Manager | 400 |  | 1000
Artist Liaison | 600 |  | 0
After Party |  |  | 1000
Site dressing | 3500
8 x pop up banners |  |  | 336
10? x vinyls for coffee tables |  |  | 80
Coffee cupsdisposable coffee cups |  |  | 228
3 x A4 signs for coffee points |  |  | 12
1 x A2 sign ‘Register Upstairs’ |  |  | 7
2 x A0 posters |  |  | 40
1 x large S vinyl |  |  | 50
3 x A3 size Fret cut S vinyls |  |  | 9
3 x small S correx for car park |  |  | 9
12 x large S correx wayfinding signs |  |  | 200
S stencil – chalk |  |  | 50
3 x large window vinyls |  |  | 120
Design |  |  | 250
Substance Programme 15,000 |  |  | 1960
Substance Programme 15,000 design |  |  | 440
Collosall Wave vinyls |  |  | 751
Total |  | 14500 |  | 15494
Access
BSL | 2000
Total |  | 2000 |  | 0
Marketing |  |  | ZK109.K138.C350
Design | 500
Lanyards | 250
Film/photo | 600
EDM | 500
Misc | 1500
Future Forum print?? Design |  |  | 300
Future Forum print - 250 copies, A7 6 x 2pp cards |  |  | 195
Future Forum EDM/Mail outs
Future Forum - social media |  |  | 300
Future Forum - Photography |  |  | 500
Future Forum - slides |  |  | 60
Future Forum, Lanyards - x 250 |  |  | 292.5
Tote Bags |  |  | 396
Design of programme |  |  | 350
Print |  |  | 500
Hack & Host Mainfesto
Total |  | 3350 |  | 2893.5
Catering
Breakfast | 1000 |  | 592.5 | Projected at 150
Lunch | 2000 |  | 1500
Evening drinks | 600 |  | 600
Total |  | 3600 |  | 2692.5
Panels |  | C350.ZK101.K208
Keynote Speakers | 2000
Panels (content, People, Chairs, Presenters) | 9400
Nikki Bedi: Presenter |  |  | 1000
John Harris: Presenter |  |  | 750
Quietus |  |  | 2000
Canvas |  |  | 400
Cities of Culture: What's the Point? |  |  | 700
BBC Academy workshop for British Council/Warren panel |  |  | 400
Blast Theory: We Made Ourselves Over |  |  | 200
Arts save the NHS |  |  | 500
Hack and Host: Art Can Change the World |  |  | 250
Eggs Collective |  |  | 250
Aisha Zia |  |  | 200
Mainfesto Print |  |  | 300
Hull Uni: Identity Crisis |  |  | 200
Keynote Speakers |  |  | 750
C4DI: Alex Mitchell |  |  | 250
NFA |  |  | 1000
Total |  | 11400 |  | 9150
Travel/Acc |  | C350.ZK112.K288
Accom | 1000 |  | 746
Travel | 625 |  | 1250
Total |  | 1625 |  | 1996

## Film Programme
Substance Film Budget |  |  |  |  | OVERVIEW
[5 empty] | Venue | 1200 | 1200 | C350.ZK106.K245
Venue |  |  |  |  | Production | 13040 | 12840 | C350.ZK106.K245
Vue | 1200 | HIC |  | 1200 | Hull 2017 - Marketing | 1100 | 333 | ZK109.K138.C350
[5 empty] | Hull Independent Cinema - Marketing | 350 | 350 | ZK109.K138.C350
Total | 1200 |  |  | 1200 | Miscellaneous | 395.76 | 395.76 | C350.ZK101.K208
[5 empty] | Total | 16085.76 | 15118.76
Production
Curation | 9500 | Aesthetica |  | 9500
Production | 1440 | HIC (ITSL) TBC |  | 1440
Host fees & expenses | 900 | TBC |  | 700
Reception | 400 | HIC (Furleys) TBC |  | 400
Management | 800 | HIC |  | 800
Total | 13040 |  |  | 12840
Marketing - Hull 2017
Print | 1000 | H17
|  |  | Ad design | 60
|  |  | Poster design | 75
|  |  | Poster Print | 48
|  |  | Social Media | 150
Distribution | 100 | H17
Total | 1100 |  | Total | 333
Marketing - HIC
Advert in brochure | 250 | HIC |  | 250
Social Media | 100 | HIC |  | 100
Total | 350 |  |  | 350
Miscellaneous
Travel, other | 281.36 |  |  | 281.36
York meeting train | 68.64 |  |  | 68.64
York ASFF train | 45.76 |  |  | 45.76
Total | 395.76 |  |  | 395.76

## Substance Live
Hull Venue - Humber Bridge
Venue hire
Hull Venue | 0 |  |  |  | Venue hire | 0
Humber Bridge | 0 |  |  |  | Prod City Hall | 47000 | 45443.25 | C350.ZK106.K245
[5 empty] | Talent | 17400 | 17400 | C350.ZK101.K208
Total |  | 0 |  |  | Marketing | 4000 | 3593.85 | ZK109.K138.C350
[5 empty] | Travel/Acc | 3250 | 1035 | C350.ZK101.K208
Production Hull Venue |  | C350.ZK106.K245 |  |  | Total | 71650 | 67472.1
Production costs | 45000
HPSS
PA System Main |  |  | 4164.86
Stage A LX and Rigging |  |  | 6567
B Stage Staging |  |  | 403.43
PA System B Stage |  |  | 3144.96
B Stage LX and Rigging |  |  | 2400
Backline B Stage |  |  | 303
AV |  |  | 8735
Audience LX |  |  | 975
Crew & Transport |  |  | 1195
Pipe & Drape |  |  | 160
Carpet |  |  | 375
Electrician |  |  | 250
Stage Manager |  |  | 500
Local Crew |  |  | 1080
Venue Costs
Mojo Barrier |  |  | 1000
First Aid |  |  | 500
City Hall Venue Hire |  |  | 5000
Stuctural Engineer |  |  | 150
City Hall Crew |  |  | 2500
Security |  |  | 2000
Artist Liaison |  |  | 150
EM |  |  | 100
Wristbands |  |  | 100
PRS |  |  | 500
Box Office Fee |  |  | 400
Ticket Printing |  |  | 100
Misc requests |  |  | 2000
Catering | 2000
Nadine Shah Buy Out |  |  | 80
Jane Weaver Buy Out |  |  | 60
Hannah Peel Buy Out |  |  | 20
Chambers Buy Out |  |  | 20
Dyr Sister |  |  | 10
Lone taxidemist Buy Out |  |  | 50
Beer/Nibbles |  |  | 250
Brass Band Nibbles/Water |  |  | 200
Other rider elements
Total |  | 47000 |  | 45443.25
Talent |  | C350.ZK101.K208
Hannah Peel | 6000 |  |  | 6000
Nadine Shah | 3000 |  |  | 3000
Jane Weaver | 3000 |  |  | 3000
PINS | 1500 |  |  | 1500
Dyr Sister | 300 |  |  | 300
Lone taxidemist | 900 |  |  | 900
Elizabeth Alker | 900 |  |  | 900
Chambers | 300 |  |  | 300
Dan Conway | 1500 |  |  | 1500
Total |  | 17400 |  | 17400
Marketing |  | ZK109.K138.C350
Design | 500
Print | 1500
Advertising | 2000
EDM |  |  | 426.85
Substance Live image for social |  |  | 250
Substance Live - Design of slide for Season 4 Launch |  |  | 30
Substance Live - Design of social poster image |  |  | 60
Substance Live poster A3 and A4 resizing design (Mattix) |  |  | 40
Substance Live - posters, A4, A3 |  |  | 67
Substance Live flyers - A5 design |  |  | 60
Substance Live - flyers print, A5 d/s landscape x 8,000 |  |  | 570
Substance Live - film |  |  | 500
Substance Live - social media |  |  | 300
Substance Live - documenting event |  |  | 500
Editorial |  |  | 0
Substance Live - film interview |  |  | 500
HDM takeover artwork |  |  | 240
Distribution (exit flyering) |  |  | 50
Total |  | 4000 |  | 3593.85
Misc |  | C350.ZK112.K288
Hotels | 2500 |  | 785
Travel | 750
Natalie Sharp Travel |  |  | 250
Total |  | 3250 |  | 1035

## Adelphi
|  | Venue | 200 | C350.ZK106.K245
Venue |  | Production | 850 | C350.ZK106.K245
Adelphi | 200 | Misc | 3000 | C350.ZK101.K208
Total | 200 | Total | 4050
Production
Tech | 250
Travel/accom | 600
Total | 850
Fees
Bill Drummond | 2000
Other | 1000
Total | 3000

## Hull 2017 Expenditure
Hull 2017 Spend
Hotels/Accom
| Bil Drummond |  | 113
| Misc |  | 64
| Misc |  | 7
Commissioning
| Substance Ltd |  | 31000
| Substance Ltd |  | 31000
Travel | Misc |  | 1018
Venue Hires | Polar Bear |  | 411
Marketing | EDM |  | 2303
Production | Launch event |  | 1291
Hospitality | Rider for Magnetic North |  | 219
Total Spend |  |  | 67426
Budget |  |  | 125000
Remaining |  |  | 57574
Income (Tickets) |  |  | 9000
BFI |  |  | 19000
Total Remaining Spend |  |  | 85574
Substance North Ltd
Hull Launch Event |  |  | 1620 | Check figure
Manchester |  |  | 7600 | Check figure
Fees |  |  | 21000
Total Spent |  |  | 30220
Grant |  |  | 62000
Remaining |  |  | 31780 | Covers costs in orange in the future forum tab
Budget Codes
Production: Staging and scenic | C350.ZK106.K245
MusicCommisions | C350.ZK101.K208
Marketing | ZK109.K138.C350
Branding |  | 2000
Travel and Accomm | C350.ZK112.K288
Catering | C350.ZK112.K120 |  |  | FF ONLY