## Sheet1
| 2017-09-13 |  |  |  | 2017-09-14 |  |  |  | 2017-09-15 |  |  |  | 2017-09-16
| Activity | Crew | Notes |  | Activity | Crew | Notes |  | Activity | Crew | Notes |  | Activity | Crew | Notes
9 | Prerig LX and Flown Masking 0900 - 1300, 4 hours | 4x HNT Technicians (2x LX, 2x Flys) + Aidan | Satellite install TBC | 9 | Start of Day Breifing | ALL |  | 9 | Lighting Plotting 0900 - 1300, 4 hours | 1x HNT Stage Manager 1x HNT Chief LX 1x HNT Head Flyman 1x HNT Dep LX/Sound + Aidan + Andy + Johanna (RB Stage Manager) + 3x RB LX Techs TBC | Camera Get in TBC | 9 | Technical Work as Required 0900 - 1300, 4 hours then set barres and piano for rehearsals | 1x HNT Stage Manager 1x HNT Chief LX 1x HNT Head Flyman 1x HNT Dep LX/Sound + Aidan + Andy + Johanna (RB Stage Manager) + 3x RB LX Techs TBC |  | 9
9.3 |  |  |  | 9.3 | Get in LX Get in Sprung Floor Get in Flown cloths 0900 - 1300, 4 hours | 1x HNT Stage Manager 1x HNT Chief LX 1x HNT Head Flyman 1x HNT Dep LX/Sound 4x HNT Casual Tech (Stage/LX Bias) + Aidan + Andy |  | 9.3 |  |  |  | 9.3 |  |  |  | 9.3
10 |  |  |  | 10 |  |  |  | 10 |  |  |  | 10 |  |  |  | 10
10.3 |  |  |  | 10.3 |  |  |  | 10.3 |  |  |  | 10.3 |  |  |  | 10.3
11 |  |  |  | 11 |  |  |  | 11 |  |  |  | 11 |  |  |  | 11
11.3 |  |  |  | 11.3 |  |  |  | 11.3 |  |  |  | 11.3 |  |  |  | 11.3
12 |  |  |  | 12 |  |  |  | 12 |  |  |  | 12 |  |  |  | 12
12.3 |  |  |  | 12.3 |  |  |  | 12.3 |  |  |  | 12.3 |  |  |  | 12.3
13 | Lunch |  |  | 13 | Lunch |  |  | 13 | Lunch |  |  | 13 | Class on stage 1300 - 1415 | CREW LUNCH BREAK |  | 13
13.3 |  |  |  | 13.3 |  |  |  | 13.3 |  |  |  | 13.3 |  |  |  | 13.3
14 | Prerig LX and Flown Masking 1400 - 1800, 4 hours Rig Projector TBC Get in Pianos into Pit TBC | 4x HNT Technicians (2x LX, 2x Flys) + Aidan + Andy Collett (RB) | Andy Collett Train arrives 14:15 | 14 | Continue get in 1400 - 1800, 4 hours production desks set up prepare for focus | 1x HNT Stage Manager 1x HNT Chief LX 1x HNT Head Flyman 1x HNT Dep LX/Sound 4x HNT Casual Tech (Stage/LX Bias) + Aidan + Andy |  | 14 | Continue Lighting | 1x HNT Stage Manager 1x HNT Chief LX 1x HNT Head Flyman 1x HNT Dep LX/Sound + Aidan + Andy + Johanna (RB Stage Manager) + 3x RB LX Techs TBC |  | 14 | Set for Rehearsal |  |  | 14
14.3 |  |  |  | 14.3 |  |  |  | 14.3 |  |  |  | 14.3 | Technical Rehearsal 2 Stage + Piano session No costume, Wigs | ALL SHOW CREW 1x HNT Stage Manger 1x Head of Flys 1x Chief LX 1x Dep LX/Sound/General Crew All RB Crew as required |  | 14.3
15 |  |  |  | 15 |  |  |  | 15 |  |  |  | 15 |  |  |  | 15
15.3 |  |  |  | 15.3 |  |  |  | 15.3 |  |  |  | 15.3 |  |  |  | 15.3
16 |  |  |  | 16 |  |  |  | 16 |  |  |  | 16 |  |  |  | 16
16.3 |  |  |  | 16.3 |  |  |  | 16.3 | Set Ballet Barres and Piano for Rehearsals |  |  | 16.3 |  |  |  | 16.3
17 |  |  |  | 17 |  |  |  | 17 | Class on Stage 1700 - 1815 | CREW DINNER 1700 - 1800 |  | 17 |  |  |  | 17
17.3 |  |  |  | 17.3 |  |  |  | 17.3 |  |  |  | 17.3 | Reset for Performance |  | Remove Production Desks | 17.3
18 |  |  | RB Tech Team Train arrives 18:15 | 18 | Dinner |  |  | 18 | Set for Rehearsals |  |  | 18 | Dinner |  |  | 18
18.3 |  |  |  | 18.3 |  |  |  | 18.3 |  |  |  | 18.3 |  |  |  | 18.3
19 |  |  |  | 19 | LX FOCUS 1900 - 2300, 4 hours | 1x HNT Stage Manager 1x HNT Chief LX 1x HNT Head Flyman 1x HNT Dep LX/Sound 4x HNT Casual Tech (Stage/LX Bias) + Aidan + Andy + Johanna (RB Stage Manager) + 3x RB LX Techs TBC |  | 19 | Technical Rehearsal 1 Stage + Piano session inc Wigs, Costume INC PRESS CALL INC INVITED AUDIENCE | ALL SHOW CREW 1x HNT Stage Manger 1x Head of Flys 1x Chief LX 1x Dep LX/Sound/General Crew All RB Crew as required |  | 19 | Half Hour Call |  |  | 19
19.3 |  |  |  | 19.3 |  |  |  | 19.3 |  |  |  | 19.3 | SHOW ACT 1 | ALL SHOW CREW 1x HNT Stage Manger 1x Head of Flys 1x Chief LX 1x Dep LX/Sound/General Crew All RB Crew as required |  | 19.3
20 |  |  |  | 20 |  |  |  | 20 |  |  |  | 20 |  |  |  | 20
20.3 |  |  |  | 20.3 |  |  |  | 20.3 |  |  |  | 20.3 | Interval - TIMINGS TBC |  |  | 20.3
21 |  |  |  | 21 |  |  |  | 21 |  |  |  | 21 | SHOW ACT2 |  |  | 21
22 |  |  |  | 22 |  |  |  | 22 |  |  |  | 22 |  |  |  | 22
22.3 |  |  |  | 22.3 |  |  |  | 22.3 |  |  |  | 22.3 | Get Out 2230 - 0230, 4 hours TBC | 1x HNT Stage Manager 1x HNT Chief LX 1x HNT Head Flyman 1x HNT Dep LX/Sound 4x HNT Casual Tech (Stage/LX Bias) + Aidan + Andy + Johanna (RB Stage Manager) + 3x RB LX Techs TBC |  | 22.3
23 |  |  |  | 23 |  |  |  | 23 |  |  |  | 23 |  |  |  | 23
23.3 |  |  |  | 23.3 |  |  |  | 23.3 |  |  |  | 23.3 |  |  |  | 23.3
00.00 |  |  |  | 00.00 |  |  |  | 00.00 |  |  |  | 00.00 |  |  |  | 00.00
00.30 |  |  |  | 00.30 |  |  |  | 00.30 |  |  |  | 00.30 |  |  |  | 00.30
01.00 |  |  |  | 01.00 |  |  |  | 01.00 |  |  |  | 01.00 |  |  |  | 01.00
01.30 |  |  |  | 01.30 |  |  |  | 01.30 |  |  |  | 01.30 |  |  |  | 01.30
02.00 |  |  |  | 02.00 |  |  |  | 02.00 |  |  |  | 02.00 |  |  |  | 02.00