## Budget (hidden)
Thursday 7 December
Budget
Venues
Fruit | 800
Hull Minster | 450
Warehouse | 400
Vue |  | in film budget
Content
For Luke
Production
Aidan
Estimate | 10000
Access
BSL | 2000
Marketing
Design flyers for delegates | 500
Capture on the day (Photographer) | 600
Flyer design/print | 350
Intercity advertising (Poster sites) | 1000
EDM (with data from others) | 500
Other | 1500
Catering
Breakfast | 600 | £3 x 200
Lunch | 2000 | £10 x 200
Total | 20700
Total Budget | 35000 | Dependant on what Luke has spent already
Remaining | 14300 | For panels/keynotes/travel/accomm

## Timeline
Timeline
2017-07-24
2017-07-31 | Venues confirmed
2017-08-07 | 1/3 of partners in place/Sessions confirmed.
2017-08-14 | Website complete on Hull2017 site
List of key attendees drawn up
2017-08-21 | Budget complete
2017-08-28
2017-08-30 | Hull 2017 Programme Announcement
At least half of the sessions announced and partners in place
Invites land to key attendees
Tickets on sale
2017-09-04
2017-09-11
2017-09-18
2017-09-25
2017-10-02 | Guardian panel annonced, Boiler Room, Vice announce
2017-10-09
2017-10-16
2017-10-23
2017-10-30 | Full programme for Substance announced. Including weekend.
2017-11-06
2017-11-13
2017-11-20
2017-11-27
2017-12-04
2017-12-11
2017-12-18

## Partners
Organisation/Person | Contacting | Notes | Session Lead
The Guardian | Luke B | Helen Pidd, John Harris
Luke suggesting Anna nmeeting Sam/Martin over Freedom Festival |  | The AND and AND argument
Vice | Luke B | The Northern underground or its Grime up North, the new Grime from the North like Bugzy Malone.
Awaiting update
Noisey | Luke B
Being chased
Huffington Post | Luke B
Being chased
LADbible | Sam
Contacted/getting back to us
Boiler Room | Martin A | Panel with the new electronic underground - Rival Consoles etc
Will talk to them about Future Forum after securing Warp.
BBC3 (Jeremy Evans) | Martin A followed up | Is this the right partner?
Luke waiting for further email from Jeremy. Sam to follow up to Radio 3 head honcho.
The Creative Society (Martin Bright) | Luke B
Awaiting Update
C4DI hosted panel - | Martin/Luke | Will five bars of internet make people less lonely. What is a creative industry?
Martin followed up. Steering groups commenced - working on a question.
The Arts Council – Rebecca Horn. Sir Nicolas Serota will be there on the Tuesday night. | Martin A first contact
Luke in conversation with currently. | Sam in contact with Jessica Farmer/Luke in contact with Rebecca Horn
Designers Republic | Luke B | How do we sell the north?
Update required
The Northern Fiction Alliance / Wrecking Ball Press | Luke B | NFA Luke confirmed and going to speak to Shane
Martin Bedford (Leeds), Sean O'Brien (set in Newcastle and Hull) |  | The role of a northern voice / future northern novellists / how can joined up publishing
Salon North | Luke B | Notions of identity
Wellcome Trust | Martin/Luke | Arts role in public health. Someone from Hull Uni to research? |  | https://www.theguardian.com/culture/2017/jul/19/arts-can-help-recovery-from-illness-and-keep-people-well-report-says?CMP=share_btn_tw
| Not contacted yet | CCG
The Space |  | How does a city or town's cultural product hit a global audience?
CANVAS | Sam H
With Boiler Room / The Space
Frank Cottrell Boyce keynote speech | Luke B | keynote speech on Northern culture, post-Brexit
Why?
Paul Morley: host/chair | Luke B
Confirmed
Humber LEP | Martin A | Ensure that the Humber capitalises on the economic opportunities offered by Hull: UK City of Culture 2017.
Tim Rix |  | Be on a panel addressing this specific issue and how that is happening.
sIEMENS, gREEN pORT |  | Work with Hull: UK City of Culture 2017 to ensure that the ‘place’ context is wider than Hull and encompasses and capitalises on the Humber opportunities. The Investment and Delivery Plan requests LGF funding to support Quality of Place Investment and a Gallery, Conference and Exhibition Centre in Hull. LGF support is also requested in the Investment and Delivery Plan to significantly enhance the economic and social benefits of the Humber Bridge visitor offer.
Miranda Sawyer | Luke B
Almost confirmed
Culture Liverpool / Cities of the North | Martin A | Chris working from Cities of the North has confirmed. ShOuld choose who to get from Culture Liverpool and add to what makes a City of Culture a success?
Council of the North |  | Will the Council of the north succeed where previous inititatives haven't and why?
What we want to build is a representative a body of council leaders, businesses and MPs – alongside trade unions and the community and voluntary sector.
Andy B
University of Hull |  | Logistics?
Hack and Host |  | ‘artists as political activists’ in coversation with Jeremy Deller
Policy North |  | Contact by MA
Andy Burnham? keynote speech | Prescott office to approach
Hull2017 - John Pywell / Martin Green | Martin Atkinson | The next 25 years of Culture in Hull
George Osborne | Martin Green
Confirm other panels and find reason to include.
Wilberforce Society
Blast Theory
Luke
Hold off
Martin/Sam

## Schedules
Thursday 7 December
Main Space Panels/Provocations/Keynotes
Time | Venue | Schedule | Hosted By | Question | Session Lead | Chair | Panelist 1 | Panelist 2 | Panelist 3 | Panelist 4 | Panelist 5
9:30 | Humber Street | Welcome | Martin Green & younger voice
10:00-10:20 | Humber Street Gallery/Butler Whites | Keynote 1 and move on to next venue. Explanation on how the day works | Culture, creativity and future of the north from young strong northern artist - Lauren Laverne, Kate Tempest, Maxine Peake - similar)
10:30-11:15 | Fruit |  | Northern Fiction Alliance | Northern Souls Northern Fiction Alliance lead a discussion on how independent publishers and new voices are flourishing in the North, and how there has never been a better time to get your voice heard in the North.
10:45-11:30 | Pier Street |  | Hack and Host: Jeremy Deller | Art can change the world How the arts are driving political, social and economic change The Turner Prize has always been an event that has always been at the centre of controversy and previous Turner Prize nominees have pushed boundaries which have led to social and political change. Hack and Host explore how the creative sector is a vehicle for political, social and economic change
11:00-11:45 | Floor 3 Block C |  | C4DI | HullOS v2042gm – your City evolved. Connected, Accelerated and Accepted How technology transformed the city you knew. The future (like the past) is defined by technology – and we own it. We have imagined that around the year 2042, a resident of Hull buried a time-capsule containing future artefacts from their surroundings. In the year 2017 we dug it up early and opened the box. Members of the Hull C4DI (Centre for Digital Innovation) have combined their knowledge, expertise and imagination to define a future narrative for Hull. Their approach has been based around 4 views: a) Hull’s current resources and unique selling points. b) Hull’s current challenges c) Project Hull’s resources into a 20+ year future d) Apply the leveraged future resources to address many of Hull’s current challenges. |  | C4DI
11:30 - 12:15 | Fruit |  | Hull Univeristy
12:30 - 13:30 | Hull Minster | Lunch
13:30 - 14:00 | Hull Minster | Keynote
14:15 - 15:00 | Fruit |  | Arts Council
14:30 - 15:15 | Floor 3 Block C |  | British Council / Cities of Culture / Martin Green | How to make a successful city of culture?
14:45 - 15:30 | C4DI Theatre |  | Wellcome / CCG | How arts can save the NHS An all-party enquiry this summer showed how a thriving arts and culture scene has a huge impact on the health and well being of any town or city, leading to a fall in hospital admissions. Can arts relieve the pressure on the NHS? |  |  | Nicky Taylor: Theatre and Dementia Research Associate at West Yorkshire Playhouse who has pioneered the way for dementia friendly performances. | Upswing: Victoria Amedume to talk about the work in Hull | Art with Heart: Sarah Emmott and Rachel Moorhouse: http://www.artwithheart.org.uk/
15:15 - 16:00 | Fruit |  | British Council/Warren | It’s a little bit leave it How the next generation of artists are responding to Brexit When the decision wasn’t yours, but the impact will be lifelong, we discuss the concerns of Brexit with younger people across the north. This group will address the findings of the Next Generation UK research commissioned by The British Council and carried out by Demos, which surveyed young people across the country on their views of the UK, addressing the findings and recommendations through interviews, spoken word and discussions.
15:30 - 16:15 | Floor 3 Block C |  | Siemens / Wykeland / KCOM / Sewells / Strata / Assemble / Partnerships | How arts and business can find a working relationship with benefits beyond the obvious
16:30 - 17:15 | C4DI Theatre |  | The Quietus | London calling? Not anymore. Why musicians are better off away from the capital. The Quietus lead a discussion about whether London is really the best place for musicians and artists.
16:15 - 17:15 | Fruit |  | The Space/Susannah Simons | How do artists reach a global audience, and how does that benefit their hometown?
16:30 - 17:45 | Floor 3 Block C
18:00 | Summing Up | Hull Minster | The Guardian | Panel of individuals gathered together by the Guardian to sum up and publish an article of the summing up
19:00 | Sessions end
20:00 | Fruit | Performance
Sessions to find homes for
15 minutes Provocations with 15 mins Q&A (smaller capacities)
Time | Venue | Title of Session | Speaker | Chair
11:30 | C4DI Theatre
12:30 | C4DI Theatre
13:30 | C4DI Theatre
14:30 | C4DI Theatre
15:30 | C4DI Theatre
16:30 | C4DI Theatre
17:30 | C4DI Theatre
11:00-12:00 | The Warehouse
A session around the impact of site specific or large scale outdoor work and the benefit they bring to place.

## Schedule by Venue
Fruit | Question | Panel Lead | Chair | Panelist 1 | Panelist 2 | Panelist 3 | Panelist 4 | Panelist 5
Time