## Org Chart
Roles and responsibilities & Work Stream _ Draft one: Discussion Doc.
This is the start of the document I have added in Hull 2017 leads for sign off purposes on each line and also who could be best place to lead the element in question. This is very much a list of things for the lifetime of the project and some bits are obviously more pressing than others but I thought it may just help all and is very much as discussion document only.
Work Streams: lead and Sign off contact for stream. |  | Hull 2017 |  | BBC |  | Northern Ballet |  | Notes
Legal, contracting, partnerships.
Legal documentation: between all parties |  | Joint: Will Hutchinson |  | Joint: Kate Gomery |  | Joint: Mark Skipper
Outside Event Licensing |  | Niccy Hallifax(L) | [5 empty] | we will have a council person and Gareth Hughes will also be involved in this.
Show licensing |  | Niccy Hallifax/ Gareth Hughes |  | (L)
Show Timing |  | Niccy Hallifax |  |  |  | (L)
Legal (Venue) |  | (L): Will Hutchinson |  | Kate Gomery
Legal (Music : PRS & PPL) |  | Gareth Hughes/Niccy Hallifax |  | (L)
Rights clearance on other footage or imagery |  | Will Hutchinson |  | (L)
Liability & ownership (Post event) |  | Will Hutchinson |  | (L)
Live Show/Performance/Writer/TV rights |  | Will Hutchinson |  | (L)
Crediting on Shows |  | Niccy Hallifax |  | (L)
Post 2017 performance rights |  | Will Hutchinson |  | (L)
Contracting of suppliers |  | Gareth Hughes (L - community piece) |  | (L-TV production) |  | (L Show Production)
Contracting of dancers | [5 empty] | (L)
Contracting of other talent |  |  |  | (L)
Venue Negotiation |  | Niccy Hallifax (L)
Insurance - Community outside event |  | Audience & management ( Gareth Hughes (L) |  | TV production (L) |  | Performers (L)
Insurance (artists and staff) |  | Audience & management Gareth Hughes (L) |  | TV production (L) |  | Performers and show production staff (L)
Insurance (Production) |  | Gareth Hughes |  | (L)
Permission to film community |  | Niccy Hallifax |  | (L)
Public liability |  | TBD |  | TBD |  | TBD
Sponsorship | - | Will Hutchinson (L) | + |  | + |  | + |  | +
Partnerships | - | Liz Draper (L) | + |  | + |  | + |  | +
Creative, Community Production
Illustrations for the lifetime of the project. |  | Niccy Hallifax (SO) |  | Lead: BBC creative team |  | (Sign off -SO)
Content - community development (scenic) | - | Niccy Hallifax | + | (L) | + |  | + |  | +
Partnerships - community scenic |  | Niccy Hallifax/Liz Draper (L)
Location development |  | Niccy Hallifax (L) | [5 empty] | TBC
Outreach Programming |  | Ian Read |  |  |  | (L)
Content -Schools programming |  | Ian Read |  |  |  | (L)
Community production (scenic and design) |  | Gareth Hughes (L) | [5 empty] | TBC
Community Marketing (Hull) |  | Laura Smith (L)
Lit. festival |  | Henri Duckworth (L)
Educational Programmed for schools (dance) |  | Ian Read |  |  |  | (L)
Educational community engagement |  | Ian Read |  |  |  | (L)
Creative, Show Production - AIRCO
Show scheduling development |  | Niccy Hallifax |  |  |  | (L)
Box office |  | David Watson (L)
Rehearsal and scheduling |  | Niccy Hallifax |  |  |  | (L)
Logistics & operations | - | Gareth Hughes (L) | + |  | + | (L) | + |  | +
Filming production |  | Gareth Hughes/Niccy Hallifax |  | (L)
Editing and sign off |  | Niccy Hallifax |  | (L)
Show Content | - | Niccy Hallifax | + | (L) | + | (L) | + |  | +
Content - Showcase (environmental) outside of show | - | Niccy Hallifax (L) | + | (L) | + | (L) | + | need to discuss who will do which bit. | +
Concept for marketing & PR assets |  | Laura Smith |  | (L)
Floor Plan design and implementation | - | Gareth Hughes | + |  | + | (L) | + |  | +
Stakeholder Engagement | - | Liz Draper/Niccy Hallifax | + |  | + |  | + |  | +
Staff and dancer welfare | - | Gareth Hughes | + |  | + | (L) | + |  | +
Customer Acquisition | - | Phil Batty (L) | + |  | + |  | + |  | +
Ticketing |  | David Watson (L)
Customer Service |  | Phil Batty (L)
Front of House management |  | Jenny Hutt
Digital Media | - | David Watson | + |  | + |  | + |  | +
Social Media | - | David Watson | + |  | + |  | + |  | +
Concept of show |  | Niccy Hallifax |  |  |  | (L)
Development of seating and staging |  | Gareth Hughes |  |  |  | (L)
Show Event Production | - | Gareth Hughes/Niccy Hallifax | + |  | + | (L) | + |  | +
Stage Management |  | Gareth Hughes |  |  |  | (L)
Transport logistics | - | Gareth Hughes (L at venue) | + |  | + |  | + |  | +
Technical show event | - | Gareth Hughes | + |  | + | (L) | + |  | +
Creative pre and post show | - | Niccy Hallifax | + | (L) | + |  | + |  | +
Crowd management |  | Gareth Hughes (L)
Post Production (TV) | - | Niccy Hallifax | + | (L) | + |  | + |  | +
Marketing & PR
Website: Joint across platforms | - | David Watson | + |  | + |  | + |  | +
Print Management - outside of Show assets. | - | Laura Smith (L) | + |  | + |  | + |  | +
Creation of assets |  | David Watson | [5 empty] | TBD
Marketing | - | Laura Smith | + |  | + |  | + | TBD | +
PR | - | Ben McKnight | + |  | + |  | + | TBD | +
Filming for Legacy |  | David Watson |  | (L)
Raw footage Websites |  | Niccy Hallifax |  | (L) |  | (L) | + |  | +
Project management
Project Administration | - | TBC | + | (L) | + |  | + |  | +
Venue management | - | Niccy Hallifax/ Gareth Hughes (L) | + |  | + |  | + |  | +
Billing/ Open book accounting |  | Henri Duckworth
Budget management | - | Niccy Hallifax | + |  | + |  | + | TBD | +
Post Evaluation |  | Henri Duckworth/ Niccy Hallifax |  | (L)
Approvers
Legal |  | Will Hutchinson - General Counsel/ Henri Duckworth - Exec producer
Budget |  | Niccy Hallifax - Lead Producer
Creative and Production |  | Niccy Hallifax - Lead Producer
Technical |  | Gareth Hughes - Head of Technical Production
Digital |  | David Watson - Head of Digital
Marketing and Community |  | Laura Smith - Head of Marketing