## DELIVERY PLAN
MONITORING & EVALUATION DELIVERY PLAN
NAME OF ORGANISATION | Hull UK City of Culture 2017 Limited
NAME OF PROJECT/EVENT | Made in Hull
MONITORING & EVALUATION
|  |  | W/C 14 NOVEMBER | [6 empty] | W/C 21 NOVEMBER | [6 empty] | W/C 28 NOVEMBER | [6 empty] | W/C 5 DECEMBER | [6 empty] | W/C 12 DECEMBER | [6 empty] | W/C 19 DECEMBER | [6 empty] | W/C 26 DECEMBER | [6 empty] | W/C 2 JANUARY | [6 empty] | W/C 9 JANUARY | [6 empty] | W/C 16 JANUARY | [6 empty] | W/C 23 JANUARY | [6 empty] | W/C 30 JANUARY | [6 empty] | W/C 6 FEBRUARY | [6 empty] | W/C 13 FEBRUARY
ACTIVITY | RESPONSIBILITY | RESPONDENTS | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su
PROJECT MONITORING SHEET
Creative team to complete Equal Opps Form | EU | n/a | bar: W/C 5 DECEMBER F
Commissioned artists to complete Equal Opps Form | EU | n/a | bar: W/C 5 DECEMBER F
Populate sheet with existing data | Brennan Research | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Enter data into sheet for the previous week | NH / LH | n/a | bar: W/C 19 DECEMBER M; W/C 26 DECEMBER M; W/C 2 JANUARY M; W/C 9 JANUARY M
Submit completed sheet to EU | NH / LH | n/a | bar: W/C 9 JANUARY F
AUDIENCE / VISITOR SURVEY
Write brief for fieldwork agency | EU | n/a | bar: W/C 14 NOVEMBER T
Publicise RFQ | FB & MLS | n/a | bar: W/C 14 NOVEMBER F
Recruit and contract fieldwork agency | FB & MLS | n/a | bar: W/C 28 NOVEMBER T
Set up meeting with fieldwork agency | EU, FB | n/a | bar: W/C 5 DECEMBER M
Sign off audience measurement solution | EU & PB | n/a | bar: W/C 12 DECEMBER W
Sign off audience survey | EU & PB | n/a | bar: W/C 12 DECEMBER F
Fieldwork | Information by Design | Sample of attenders from 1-7 January | bar: W/C 19 DECEMBER M to W/C 23 JANUARY M
Delivery of audience measurement data | Information by Design | n/a | bar: W/C 2 JANUARY M; W/C 2 JANUARY T; W/C 9 JANUARY M; W/C 23 JANUARY W
Delivery of audience survey data | Information by Design | n/a | bar: W/C 30 JANUARY M; W/C 30 JANUARY F
Analysis of data | Brennan Research | n/a | bar: W/C 6 FEBRUARY M to W/C 13 FEBRUARY Su
EXPERENTIAL / EMOTIVE DATA CAPTURE
Pre-recruit 4 groups | Information by Design | n/a | bar: W/C 19 DECEMBER M to W/C 19 DECEMBER W
Partners (guided tour) | EU / LD | Partners | bar: W/C 19 DECEMBER M to W/C 19 DECEMBER W
Group 2 | Information by Design | Hull residents | bar: W/C 19 DECEMBER M to W/C 19 DECEMBER W
Group 3 | Information by Design | Hull residents | bar: W/C 19 DECEMBER M to W/C 19 DECEMBER W
Group 4 | Information by Design | East Riding residents | bar: W/C 19 DECEMBER M to W/C 19 DECEMBER W
Select data capture methodology for groups | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER F
Fieldwork | EU | As above | bar: W/C 26 DECEMBER Su to W/C 9 JANUARY M
Analysis of data | EU | n/a | bar: W/C 9 JANUARY T to W/C 16 JANUARY F
CREATIVE CORE TEAM SURVEY
Design pre-event survey | EU | n/a | bar: W/C 5 DECEMBER F to W/C 5 DECEMBER Su
Design post-event survey | EU | n/a | bar: W/C 5 DECEMBER F to W/C 5 DECEMBER Su
Deliver pre-event Survey | EU | Creative Core Team (see 'Notes' below) | bar: W/C 12 DECEMBER F to W/C 26 DECEMBER W
Deliver post- event Survey | EU | Creative Core Team (see 'Notes' below) | bar: W/C 9 JANUARY M to W/C 16 JANUARY F
Analysis of data | Brennan Research | n/a | bar: W/C 16 JANUARY Sa to W/C 30 JANUARY Su
CREATIVE CORE TEAM DEPTH INTERVIEWS
Design depth interview guide for pre-event | EU | n/a | bar: W/C 5 DECEMBER Sa to W/C 12 DECEMBER M
Design depth interview guide for post-event | EU | n/a | bar: W/C 5 DECEMBER Sa to W/C 12 DECEMBER M
Pre-event depth interviews | Brennan Research | Creative Core Team (see 'Notes' below) | bar: W/C 12 DECEMBER T to W/C 12 DECEMBER F; W/C 19 DECEMBER M to W/C 19 DECEMBER Sa
Post-event depth interviews | Brennan Research | Creative Core Team (see 'Notes' below) | bar: W/C 16 JANUARY M to W/C 16 JANUARY F
Analysis of data | Brennan Research | n/a | bar: W/C 26 DECEMBER M to W/C 26 DECEMBER Sa; W/C 16 JANUARY Sa to W/C 30 JANUARY Su
ARTIST & HERITAGE PARTNER DEPTH INTERVIEWS
Design depth interview guide for pre-event | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Design depth interview guide for post-event | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Pre-event depth interviews | Brennan Research | Artists, Heritage Partners (see 'Notes' below) | bar: W/C 12 DECEMBER T to W/C 12 DECEMBER F; W/C 19 DECEMBER M to W/C 19 DECEMBER Sa
Post-event depth interviews | Brennan Research | Artists, Heritage Partners (see 'Notes' below) | bar: W/C 16 JANUARY M to W/C 16 JANUARY F
Analysis of data | Brennan Research | n/a | bar: W/C 26 DECEMBER M to W/C 26 DECEMBER Sa; W/C 16 JANUARY Sa to W/C 30 JANUARY Su
PEER SURVEY
Design pre-event survey | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Design post-event survey | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Pre-event Survey | EU | Peer - TBC | bar: W/C 12 DECEMBER F to W/C 26 DECEMBER W
Post-event Survey | EU | Peer - TBC | bar: W/C 9 JANUARY M to W/C 16 JANUARY F
Analysis of data | Brennan Research | n/a | bar: W/C 16 JANUARY Sa to W/C 30 JANUARY Su
PEER DEPTH INTERVIEWS
Design discussion guide for pre-event | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Design discussion guide for post-event | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Pre-event depth interviews | EU | Peer - TBC | bar: W/C 12 DECEMBER T to W/C 12 DECEMBER F; W/C 19 DECEMBER M to W/C 19 DECEMBER Sa
Post-event depth interviews | EU | Peer - TBC | bar: W/C 16 JANUARY M to W/C 16 JANUARY F
Analysis of data | Brennan Research | n/a | bar: W/C 26 DECEMBER M to W/C 26 DECEMBER Sa; W/C 16 JANUARY Sa to W/C 30 JANUARY Su
DELIVERY PARTNER SURVEY
Design post-event survey | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Post-event Survey | EU | Delivery Partners (see 'Notes' below) | bar: W/C 9 JANUARY M to W/C 16 JANUARY F
Analysis of data | Brennan Research | n/a | bar: W/C 16 JANUARY Sa to W/C 30 JANUARY Su
MEDIA & PR
Media Monitoring | AJ & Gorkana | n/a | bar: W/C 21 NOVEMBER T to W/C 9 JANUARY Su
Media Analysis | AJ & Gorkana | n/a | bar: W/C 21 NOVEMBER T to W/C 16 JANUARY F
PR Report | PR Company | n/a | bar: W/C 23 JANUARY M to W/C 23 JANUARY W
Social Media Analysis | CM & Falcon | n/a/ | bar: W/C 23 JANUARY M to W/C 23 JANUARY W
DOCUMENTING
Design vox pops questions | EU | n/a | bar: W/C 12 DECEMBER M to W/C 12 DECEMBER W
Design brief for film documentation | DW | n/a | bar: W/C 12 DECEMBER T to W/C 12 DECEMBER F
Filming | Contracted filmographer | All audiences, TBC
Editing | Contracted filmographer | n/a
Provide raw footage | Contracted filmographer | n/a
Provide edited cut | Contracted filmographer | n/a
Analysis | Brennan Research | n/a | bar: W/C 16 JANUARY Sa to W/C 30 JANUARY Su
PROJECT DEBRIEF
Design agenda | NH | n/a
Debrief meeting | NH
Analysis | Brennan Research | n/a | bar: W/C 16 JANUARY Sa to W/C 30 JANUARY Su
NOTES
Creative Core Team | Niccy Hallifax
Sean McAllister
Rupert Creed
Ala Lloyd
Durham Marenghi
Dan Jones
Artists | Zsolt Balogh
Chris Hees
Helga Gift
Sodium
Invisible Flock
Preston Likely
MakeAMPLIFY
Jesse Kanda
Imitating the Dog
Quentin Budworth
Urban Projections
Heritage partners | Yorkshire Film Archives
Pathe
BFI
Huntley Film Archives
Hull History Centre
John Frost
Hull Maritime Museum
Hull History Museum
Delivery Partners | Hull City Council
Ground Control
VHEY
Hull Daily Mail
Daily Express
BBC Look North
Warren Centre
Open Doors
Hull Libraries Service
Hull Culture & Leisure