## Production costs
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | Notes 30/06 | Telephone | email | Order wording | Order cost exVAT | Insurance values
LIGHTING |  |  |  |  | They bring
Lighting stands | L.A.D. events | 240 |  |  | 4 x 60Kg stands with T-bars | 2m height | got verbal quote from Josh 26/06
site lighting | TGPS | 500 |  |  | Festoon etc
LIGHTING SUB-TOTAL |  |  |  | 740
AUDIO |  |  |  |  | They bring all but PA
FOH Pa | 3d productions | 7458.8 |  |  | 4 x hangs of V series | max 350Kg per hang | received quote 16/06
Install crew | 3d productions | inc above |  |  | 2 crew in & out | £200 per day | received quote 16/06
PA tech | 3d productions | inc in C11 |  |  | 3 days at £220 per day |  | received quote 16/06
crew transport | 3d productions | inc in C11 |  |  |  |  | received quote 16/06
Delivery | 3d productions | inc in C11 |  |  |  |  | received quote 16/06
Accomodation ands subs | 3d productions | inc in C11 |  |  |  |  | received quote 16/06
AUDIO SUB-TOTAL |  |  |  | 7458.8
STRUCTURES
dressing room tent | Nationwide | 607 |  |  | 6m x 9m | with floor & lights | received quote 07/06
booth tents | Nationwide | 330 |  |  | 3 no. 3m gazebos | staked | received quote 07/06
Lost kids gazebo | TGPS | 50
furniture | Nationwide | 29.5 |  |  | 4 x trestles,10 x chairs |  | received quote 07/06
delivery | Nationwide | 250 |  |  |  |  | received quote 07/06
STRUCTURES SUB-TOTAL |  |  |  | 1266.5
POWER & DISTRO
Show power | John F Hunt | 612 |  |  | 2 x 150KVA | Sync'd to load share | received quote 07/06
tanks | John F Hunt | 20 |  |  | 1 x 1000l tank |  | received quote 07/06
production power | John F Hunt | 135 |  |  | 40KVA |  | received quote 07/06
tank | John F Hunt | 20 |  |  | 1000l tank |  | received quote 07/06
site sets | John F Hunt | 250 |  |  | 2 x 20KVA | for festoon etc | received quote 07/06
Fuel | John F Hunt | 2000 |  |  |  |  | received quote 07/06
Delivery | John F Hunt | 1120 |  |  | delivered Monday, collected Tuesday |  | received quote 07/06
.
Distro | IDE | 295 |  |  | as required |  | received quote 07/06
cable ramp | IDE | 300 |  |  | 50m |  | received quote 07/06
delivery | IDE | 130 |  |  |  |  | received quote 07/06
tower lights | John F Hunt | 480 |  |  | 4 x LED |  | received quote 07/06
POWER & DISTRO SUB-TOTAL |  |  |  | 5362
PLANT & BARRIERS
ped barrier | Actavo | 412.5 |  |  | 150 ped barriers |  | requested quote 30/06 | get quote from actavo
Heras | Actavo | 120 |  |  | 40 x heras sets |  | requested quote 30/06
extra heras | Actavo | 240 |  |  | 80 x heras sets | for match
delivery | Actavo | 200 |  |  | 2 loads £50 e/w pl | delivered 7th, collected on 15th | requested quote 30/06
forks | Nixons | 540 |  |  | 3.5t all terrain forks |  | received verbal quote from David Graham 29/06
telehandler | Nixons | 205 |  |  | 7m telehandler |  | received verbal quote from David Graham 29/06
fuel | Nixons | 70 |  |  |  |  | received verbal quote from David Graham 29/06
delivery | Nixons | 340 |  |  | delivered Mon 7th, collected Tues 15th |  | received verbal quote from David Graham 29/06
crane | Central crane hire | 900 |  |  | 30t crane for 2 days | £450 per day | received quote 08/06
Trakway | Live | 8320 |  |  | 20m pad with 55.2m x 3m road. | installed 7th, 8 panels taken out 10th, re installed 14th, full derig 15th | requested updated quote 29/06
PLANT SUB-TOTAL |  |  |  | 11347.5
CREW
site crew | TGE | 1600 |  |  | 1 man for 8 days @ £200 pmpd | Tues - Tues
additional crew | TMC | 741.6 |  |  | 6 men, Saturday, 0900-1300 & 1700-1900 | for addistional fencing
stage hands | TMC | 2348.4 |  |  | 16 x 8 hr days & 6 x 4hr get-out | £15 per hour | requested quote 30/06
lighting techs | TGE | 1640 |  |  | 7 man days @ £200 plus 2 for get-out @ £120 | £200 per man | need to find
PDs |  | 375 |  |  | 15 days @ £25 | For site crew and lighting techs
mileage |  | 300 |  |  | charged @ £0,40 per mile | For site crew and lighting techs
CREW SUB-TOTAL |  |  |  | 7005
MISCELLANEOUS
Ballast | JP concrete |  | 289.5 |  | 24 x 1t blocks | may be able to stake in to ground | received quote 15/05 | hopefully don't need
delivery | JP concrete |  | 750 |  |  | see above | received quote 15/05 | hopefully don't need
comms | Events team | 0 |  |  | 40 x DP3400's
Cleansing | Hull CC | 700 |  |  | clean on Sunday 13th & Tuesday 15th
Bins | Hull CC | 222 |  |  | bins as required |  | received quote 16/06
backstage toilets | add plant | 300 |  |  | 6 x single plastics |  | received quote 07/06
service | add plant | 240 |  |  | 2 x service |  | received quote 07/06
Audience toilets | add plant | 860 |  |  | 14 x single plastics and 2 x wheelchair accessible units |  | received quote 07/06
servicing | add plant | 250 |  |  | 1 x service |  | received quote 07/06
del/coll | add plant | 120 |  |  |  |  | received quote 07/06
consumables | ??? | 100 |  |  | tape, cable ties etc
MISCELLANEOUS SUB-TOTAL |  |  |  | 2792
STEWARDING
stewarding and security | Prestige | 8322 |  |  | stewarding, as spreadsheet | inc lost kids
STEWARDING SUB-TOTAL |  |  |  | 8322
H&S
Fire extinguishers | TGE | 100
Show first aid | Heart Medical | 1334 |  |  | for both shows |  | received quote 03/06
rehearsal first aid | Heart Medical | 168 |  |  | for dress rehearsal |  | received quote 03/06
H&S SUB-TOTAL |  |  |  | 1602
TM
TM | centurion | 550 |  |  | To close as per event plan, plus 2 x advance warning signs |  | received quote 27/06
TM SUB-TOTAL |  |  |  | 550
FEES
Handling fee | TGPS | 2322.29
FEES SUB-TOTAL |  |  |  | 2322.29
TOTALS Ex Contingency, Ex VAT |  | 48768.09
Contingency |  | 2438.4045 |  |  | 5% contingency
TOTALS inc Contingency - EX VAT |  | 51206.4945
TOTAL inc VAT |  | 61447.7934

## TGE Fees
Item | Cost ex vat | Description | Notes
Production Prep time | 1250 | 5 Days @ £250 per day
H&S prep time | 1250 | 5 Days @ £250 per day | Not including meetings
Site/production manager | 3150 | 9 Days @ £350 per day | Monday - Tuesday
on site H&S | 0 | 2 Days @ £420 per day | Gareth to do
Meetings | 500 | 2 meetings @ £250 | ESAG plus one other
mileage | 240 | 4 Round trips of 150 miles @ £0.40 per mile
accomodation | TBP | ? Rooms for ? Nights
PD's | 275 | charged at £25pppd | 11 man days
TGE TOTAL Ex VAT | 6665
In addition, Hull 2017 will provide and pay for:
Hotel accommodation for Site / Production Manager and Safety Manager as required over the build / event period