|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Katie Cussons/ Hull Children’s University Looked-after Care Programme |
| **Name of Project** | Children in Care Visual Arts Celebration |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| June 13th 2016 |  | **Meeting with Chris Williams** regarding the planning and organisation of the Digital Art Modules |  |  |
| June 29th 2016 |  | **Team meeting** with SOVA, Family Assessment Unit, Schools and College Liaison Service and Young Voices Influencing Care regarding the planning and management of the individual programmes and how they will be displayed on the event. |  |  |
| November/December 2016  January 1st 2017 | January 2017 | **Gain referrals** of young people who would like to be involved in the activities.  **Deadline for referrals** |  |  |
| January 2017 (date tbc) |  | **Final meeting with Chris Williams** regarding Digital Art Modules |  |  |
| 22nd February | 23rd February | **Digital Art Modules**/ through the use of iPads, young people will create and narrative short films of what Hull means to them using images and short clips they have taken. |  |  |
| May 2017 |  | **Team meeting with Virtual Team regarding the visual arts Celebration**/ designate roles and responsibilities |  |  |
| July 2017 (Dates TBC) | July 2017 (Dates TBC) | **Pre visits to young people for the London visit and Dramajam.** |  |  |
| 1st August 2017 | 1st August 2017 | **London**: Pineapple Studios and West End performance visit/ opportunity for the young people to meet actors/dancers within the sector and gain some inspiration their play. The young people will then have the opportunity to watch a live West end show. |  |  |
| June 2017 |  | **Final Meeting with Hull Truck** to confirm names |  |  |
| Summer 2017 (5 days) | Dates TBC | **Dramajam** with Hull Truck/ a play in a week of what Hull means to them. The play will then be showcased to carers, professionals and relatives. |  |  |
| September/November (date TBC) |  | **Final Meeting regarding the Visual Arts Celebration** |  |  |
| November 2017 (Date tbc) | November 2017 (Date tbc) | **Children in Care celebration event/Visual Arts Celebration**: celebration of all work completed by young people within the different programmes. |  |  |
| **Please note: Additional activities will also be held throughout the year by SOVA, Family Assessment Unit (Hull University), Kidz (TBC) and Young Voices Influencing Care Team (Hull City Council). All the work from these teams will come together at the Celebration**. |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances