## Timeline
April
wk 3 April
wk 10 April
wk 17 April |  | Start writing Guild consitiation
wk 24 April | Confirm crate contents for heralding | Confirm all artsitic team
Confirm Guildhall / Info point
May
wk 1 May | Guild Liaison Officer starts | Contract all team/assocaites
wk 8 May | Crate found photo call with Margaret at Allotments
wk 15 May | Heralding / Press
wk 22 May | Open Public Guild recruitment
Detail plan for final performance
wk 29 May | Guild recruitment continues
June
wk 5 June | Guild recruitment continues | lock down devising schedule
wk 12 June | Guild recruitment continues
wk 19 June | Devising begins | Guild attire starts to be seen in Longhill
Guild recruitment continues
wk 26 June | Devising
Guild recruitment continues to 30 June
July
2017-07-01 | Rehearsals
2017-07-02 | Rehearsals
2017-07-03 | Rehearsals
2017-07-04 | Rehearsals
2017-07-05 | Rehearsals
2017-07-06 | Rehearsals
2017-07-07 | Rehearsals
2017-07-08 | Teaser moments begin
2017-07-09 | Rehearsals / teasers
2017-07-10 | Rehearsals / teasers
2017-07-11 | Rehearsals / teasers
2017-07-12 | Rehearsals / teasers
2017-07-13 | Rehearsals / teasers
2017-07-14 | Dress rehearsal
2017-07-15 | Final Performance & Fire

## Budget
Artistic Expenditure | No | rate | Wks/Days | Sum |  | Removed for Mandy's Budget
Artistic Directors: planning and development | 2 | 200 | 15 | 6000
Delivery & creation | 2 | 200 | 30 | 12000
Design/Artist | 1 | 1500 |  | 1500
Mandy Dike / Fire |  |  |  | 0 |  | 2500
Tom Roden / Movement Director - Choreographer | 1 | 2500 |  | 2500
Paul Dale Vickers / Music Director | 1 | 2500 |  | 2500
Video Documenter | 1 | 3500 |  | 3500
Production Manager | 1 | 750 | 3 | 2250
Guild Liaison Officer | 1 | 500 | 7 | 3500
Sub Total |  |  |  | 33750
Production Costs
Materials |  |  |  | 5000
Print/Postcards/Posters |  |  |  | 1000
Jackets/Badges/Guild attire | 100 | 75 |  | 7500
Travel
Artistic Director: Gary | 1 | 60 | 25 | 1500
Artistic Director: Gregg | 1 | 200 | 10 | 2000
Other Artists | 4 | 80 | 5 | 1600 |  | 400
Other team members | 2 | 80 | 6 | 960
Accommodation |  |  |  |  | provided locally
Subsistence
Artistic Directors | 2 | 23.4 | 40 | 1872
Other Artists | 4 | 23.4 | 18 | 1684.8 |  | 421.2
Other team members | 1 | 23.4 | 21 | 491.4
General refreshments/Hospitality/consumables |  |  |  | 1000
Sound/Video/LX Equipment |  |  |  | 3000
Sub Total |  |  |  | 27608.2 |  | 3321.2
Overheads
Project Management and Co-Ordination | 1 | 200 | 45 | 9000
Producer's travel | 1 | 160 | 8 | 1280
Producer subsitence | 1 | 23.4 | 16 | 374.4
Contribution to offce costs |  |  |  | 500
Sub Total |  |  |  | 11154.4
Total |  |  |  | 72512.6 |  | 3321.2
Contingency @ 5% |  |  |  | 3625.63
GRAND TOTAL |  |  |  | 76138.23 |  | 3321.2