## places des anges
Item | Supplier | 1 Show Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | Order address | Telephone | email | Order wording | Order cost exVAT | Insurance values
FEES
Handling fee | TGPS | 1500 |  |  | Handling fee
FEES SUB-TOTAL |  |  |  | 1500
CREW
get-in/out crew | YEC | 3705 |  |  | 4 crew for 4 hrs Mon, 6 crew Tues, Weds and 8 crew Sun | inc. crew boss rate and travel | received quote 29/02
gen crew | YEC | 1170 |  |  | 2 men Thurs, Fri, Sat | general duties - fencing, power etc | received quote 29/02
Follwspot crew | YEC | 1680 |  |  | 8 crew for 3 x 4 hour calls @ £70 per call - tech, dress & 2 shows | ideal student role | received quote 29/02
Blower crew |  | volunteers |  |  | 10 Crew for set-up, Dress & 1 show | tech, dress and 2 x shows 4 hr call only Volunteers?
angel crew |  | volunteers |  |  | 2 crew to assist with Angel - dress & 2 shows | Volunteers?
crowd control |  | volunteers |  |  | 12 people to assist company moving thru crowd | Volunteers or Stewards?
CREW SUB-TOTAL |  |  |  | 6555
PA HIRE
main PA | 3d | 5600 |  |  | 2 x show days & 2 x rehearsal days |  | received quote 02/03
delays | 3d | 1200 |  |  | for gardens |  | received quote 02/03
rehearsal pa | 3d | 300 |  |  |  |  | received quote 02/03
Pa towers | 3d | 1000 |  |  | inc decks for delays |  | received quote 02/03
Pa crew | 3d | 1800 |  |  |  |  | received quote 02/03
crew transport | 3d | 144 |  |  |  |  | received quote 02/03
crew accomodation | 3d | 195 |  |  | charged at £65 per night | You could provide if cheaper | received quote 02/03
PA delivery | 3d | 320 |  |  |  |  | received quote 02/03
PA HIRE SUB-TOTAL |  |  |  | 10559
LIGHTING HIRE
Lighting | HSL | 3505 |  |  | 27 x G-spots and 10 x p2's |  | received update29/03
F/spots | TSS | 4120 |  |  | 8 x f/spots @ £315 per week |  | received update29/03
Lighting desk | TSS | 690 |  |  | Grand Ma2 Lite | inc delivery | receibved quote 31/03
cable allowance | HSL | 401.9 |  |  | to cover cabling required |  | received quote
wireless DMX | HSL | 368 |  |  |  |  | requested updated quote
DDA cable ramp | IDE | 400 |  |  | 80 panels | to cover blower cable | received quote 04/5
comms - O1 | Warehouse |  | 1321 |  | radio comms | 10 x headsets | received quote 08/03
comms - O2 | Stage electrics |  | 554 |  | radio comms | 8 x wireless headsets & 4 x wired | received quote 31/03
Comms | 3d | 300 | 300 |  | 10 sets of wired comms |  | received update 29/03
Lighting delivery | HSL | 500 |  |  | 17t |  | received update 29/03
LIGHTING HIRE SUB-TOTAL |  |  |  | 10284.9
POWER & DISTRO
Main Generators | generator power | 590 |  |  | 2 x 200KVA sync sets | inc cabling | received quote 25/02
fuel tank | generator power | 30 |  |  | 2000l tank |  | received quote 25/02
police station backstage generator | generator power | 165.72 |  |  | 40KVA road tow |  | received quote 25/02
fuel tank | generator power | 28.57 |  |  | towable fuel bowser |  | received quote 25/02
Guildhall generator | generator power | 100 |  |  | 40KVA | to get 32-3 up tower | received quote 25/02
police station show generator | generator power | 100 |  |  | 40KVA |  | received quote 25/02
Round tower generator | generator power | 100 |  |  | 40KVA |  | received quote 25/02
Guildhall cabling | IDE | inc below |  |  | 100m 63-3 & distro | maybe start at 63-3 | received quote 04/05
distro | IDE | 740 |  |  | distro as required |  | received quote 04/05
cabling | IDE | 474 |  |  | 3 phase cabling as required |  | received quote 04/05
Delivery | IDE | 320 |  |  |  |  | received quote 04/05
7909 sign off |  | 300
Fuel | generator power | 1400 |  |  | ESTIMATE | charged after event | received quote 25/02
Delivery | generator power | 1180 |  |  |  |  | received quote 25/02
POWER & DISTRO SUB-TOTAL |  |  |  | 5528.29
STRUCTURES
Disabled viewing platform | 3d | 0 |  |  | Don't need, use roped off area by FOH |  | received qote 02/03
F/spot platforms | 3d | 200 |  |  | 5 no. 8x8 @ 2m |  | received updated quote 31/03
FOH position | 3d | 300 |  |  | 4m x 2m @ 1m | uncovered for dress & shows? | received updated quote 31/03
staging delivery | 3d | 1000 |  |  |  |  | received qote 02/03
build crew | 3d | 1496 |  |  |  |  | received qote 02/03
FOH cover | TGE | 50 |  |  | 3m pop-up with ballast | delivered Weds 29th, de-rigged with others | received quote 09/02
tech marquee | TGE | 50 |  |  | 3m pop up
Staircase | Acorn |  | 8800 |  | access staircase for police station |  | need to get more quotes
Staircase | B & A | 2895
STRUCTURES SUB-TOTAL |  |  |  | 5991
Item | Supplier | 1 Show Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | Order address | Telephone | email | Order wording | Order cost exVAT | Insurance values
MISCELLANEOUS
skips | transwaste Ltd | 200 |  |  | 1 large skip | for college carpark | received quote 03/03
ballast | transwaste Ltd | inc above |  |  | 16t ballast, in skip |  | received quote 03/03
ballast | JP concrete | 867 |  |  | 8 x 1t concrete blocks | inc delivery | received quote 02/03
Helium | BOC | 705 |  |  | 25m3 helium | 3 x L size @ £235 per bottle
Delivery | BOC | 53 |  |  | delivery and collection of bottles
street lighting | KWL | 868 |  |  | charge to turn off street lights |  | quote received 24/03
radio Comms | Hull Events team | FOC
extra comms | 900 communications | 131.14 |  |  | 10 x noise cancelling headsets & 20 x fist mics |  | received quote
Artistic lodge | Hull Events team | FOC |  |  | dressing room/base for company for duration of stay. c/w mirrors furniture, fridges etc | use 1 of the buildings Helen talked about using as a control room
catering eqpt |  | 0 |  |  | fridges, urns etc for lodge | inc mirrors & furniture
chairs | ?? | 200 |  |  | 50 x chairs for accessible area | inc delivery | need to get quote
Parking costs | Hull CC | 470 |  |  | to suspend all 47 bays on Guildhall road |  | cost from Helen
pond/air con covering |  | 450 |  |  | 10 rolls of debris mesh to cover pond(s) | Look at rigging
backstage/build toilets |  | 100 |  |  | 2 x plastics behind police station
Public toilets |  | 660 |  |  | 10 x plastics and 2 x disabled | delivered Saturday am
servicing |  | 40 |  |  | service Thursday
delivery collection |  | 100
Cleansing | council | 754.94 |  |  | Show & FOH cleansing after show and after get-out |  | quote received from Helen
MISCELLANEOUS SUB-TOTAL |  |  |  | 5599.08
PLANT & BARRIERS
Forks |  | 250 |  |  | 10.5m telehandler | 1 week | received quote 05/05
delivery |  | 260 |  |  | £130 e/w |  | received quote 05/05
barriers | Event solutions | 345 |  |  | 230 Fixed leg crowd barriers | £1.50 per panel | received quote 06/04
Fencing | Event solutions | 60 |  |  | 40 Heras sets | £1.50 per panel | received quote 06/04
Delivery/collection | Event solutions | 300 |  |  | for above | £150 e/w | received quote 06/04
PLANT & BARRIERS SUB-TOTAL |  |  |  | 1215
STEWARDING
Stewarding | Prestige | 6965 |  |  | as per spreadsheet | upped numbers 06/05 | sent update 6/5
security | Prestige | inc above
STEWARDING SUB-TOTAL |  |  |  | 6965
TM
road closures | council | 0
TM |  | 2350 |  |  | advance signage, 1 man Tues, Weds, Thurs & Fri, 2 men sat Sun |  | received quote 24/03
TM SUB-TOTAL |  |  |  | 2350
H&S
structural engineer | Star Events | 1 |  |  | star providing FOC
Rigging check | Star Events | 0 |  |  | star providing FOC
insurance | HULL17
Medical | St Johns | 1800 |  |  |  |  | called 14/04
Lost kids provision | Prestige | 126 |  |  | 2 people to look after lost kids |  | received 06/07
Fire extinguishers | TGE | 100 |  |  | Extinguishers as required
H&S SUB-TOTAL |  |  |  | 2027
TOTALS Ex Contingency - EX VAT |  | 58574.27
CONTINGENCY | VARIOUS | 3425.73
TOTALS inc Contingency - EX VAT |  | 62000 |  | 58574.27 | [7 empty] | 0 | 0
TOTALS - INC VAT |  | 74400

## TGE Fees
Item | Supplier | Cost ex vat | Description | Notes
Production Prep time | TGE | 1755 | 9 Days @ £195 per day | 1 day to be charged to a separate budget
H&S prep time | TGE | 780 | 5 Days @ £195 per day | Not including meetings
Tim provisional site visit | TGE | 0 | 1 day @ £195 | Charged to a separate budget
Adam site visits | TGE | 0 | 2 Days @ £195 per day | Charged to a separate budget
meetings | TGE | 800 | 8 Meetings charged at £100 meeting
Site/production manager | TGE | 2450 | 7 Days @ £350 per day | Monday - Sunday
on site H&S | TGE | 840 | 2 Days @ £420 per day | dress rehearsal & show days
mileage | TGE | 480 | 8 Round trips of 150 miles @ £0.40 per mile
accomodation | TGE | TBP | ? Rooms for ? Nights
Lighting crew | TGE | 2470 | lighting crew charged @ £190 pppd | 2 men Weds, 4 men Thurs, 2 men Fri, 1 man Sat, 4 men Sn
Light crew PD's | Tge | 260 | charged at £20pppd | 13 man days
TGE TOTAL Ex VAT |  | 9835
In addition, Hull 2017 will provide and pay for:
Hotel accommodation for Site / Production Manager and Safety Manager as required over the build / event period
Catering or per diems (depending on arrangements) for Site / Production Manager, Safety Manager