## Workplan
Hulll 2017 Programme Fund
Project Management
Activity Detail | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01
Programme Fund Key Milestones
Launch for Prog Fund Guidelines | bar: 2016-01-01
Roadshows | bar: 2016-04-01 to 2016-05-01
Application Window | bar: 2016-04-01 to 2016-05-01
Application Assessment | bar: 2016-06-01
Project Selection | bar: 2016-07-01
Project Confirmation Contracting | bar: 2016-07-01 to 2016-08-01
Projects Announced | bar: 2016-09-01
Project Activity Preparation | bar: 2016-07-01 to 2017-11-01
Project Delivery | bar: 2017-01-01 to 2017-12-01
Project Monitoring | bar: 2016-07-01 to 2017-12-01
Project Reporting | bar: 2017-02-01 to 2018-01-01
Project Evaluation | bar: 2017-02-01 to 2018-02-01
System Architecture
Guidelines Technical | bar: 2015-11-01 to 2015-12-01
Guidelines Copy | bar: 2015-11-01 to 2015-12-01
Guidelines Design & Print | bar: 2015-11-01 to 2015-12-01
Evaluation Requirements | bar: 2015-12-01
Targets & Outcome Framework Design | bar: 2015-12-01
Evaluation Guidelines for grant recipients | bar: 2015-12-01
Application Form Design | bar: 2016-01-01 to 2016-02-01
Application Form Realisation Online | bar: 2016-02-01 to 2016-03-01
Application Form Live | bar: 2016-04-01 to 2016-05-01
Monitoring Process of Grant Recipients | bar: 2016-01-01 to 2016-02-01
Reporting Forms Design | bar: 2016-01-01 to 2016-02-01
Final Report Form Design | bar: 2016-01-01 to 2016-02-01
Grant Offer Letter Sign Off | bar: 2016-02-01 to 2016-03-01
Grant Agreement Legal Sign Off | bar: 2016-02-01 to 2016-03-01
Grant Agreement Financial System Sign Off | bar: 2016-02-01 to 2016-03-01
MarComms
Guidelines Publishing | bar: 2016-01-01 to 2016-04-01
FAQs for Guidelines | bar: 2016-01-01 to 2016-04-01
Programme Fund Comms - Launch | bar: 2016-01-01
Programme Fund Comms - Roadshows | bar: 2016-02-01 to 2016-03-01
Programme Fund Comms - Process Summary | bar: 2016-06-01
Programme Fund Comms - Projects Announced | bar: 2016-09-01
Public Engagement Campaign - Roadshows
Venue Identification | bar: 2016-01-01 to 2016-02-01
Venue Booking | bar: 2016-01-01 to 2016-02-01
Roadshow Team confirm & book | bar: 2016-01-01 to 2016-02-01
Programme Fund Display Materials | bar: 2016-02-01
Programme Fund Presentation PP | bar: 2016-02-01
Roadshow Public Booking | bar: 2016-02-01 to 2016-03-01
Budget & Administration
Confirm Hull 2017 Budget | bar: 2015-11-01 to 2015-12-01
Confirm City Arts Grants Budget | bar: 2015-11-01 to 2015-12-01
Programme Fund Administrator Function
Roadshow Co-ordination & Delivery | bar: 2015-12-01 to 2016-03-01
Fund General Enquiry Management | bar: 2016-01-01 to 2016-05-01
Application Receipt & Processing | bar: 2016-04-01 to 2016-05-01
Application Assessments | bar: 2016-05-01 to 2016-06-01
Application Shortlisting | bar: 2016-06-01
Application Selection Panel Co-ordination | bar: 2016-02-01; 2016-04-01; 2016-06-01
Successful Project Offers & Contracting | bar: 2016-06-01 to 2016-07-01
Rejected Project Communications - Disappointment Mgt | bar: 2016-07-01 to 2016-08-01
Project Monitoring | bar: 2016-10-01 to 2017-12-01
Project Final Report Collation | bar: 2017-02-01 to 2018-01-01
Project Evaluation Collation | bar: 2017-03-01 to 2018-02-01

## Budget
Creative Communities Programme
Budget Overall | 365000 | Notes
Grant Fund | 322000
Marketing - lifetime of project | 20000 | NB to re-confirm total with Phil B; includes translation services
Fluid Review | 10000 | Fluid Review - 2 yrs @ £4612 approx pa
Admin | 10500 | 6 mths - admin support @ £18k + oncosts
Admin Costs | 2500
Total | 365000