## PID
Project name | Caravan of Love
Last updated | 2016-01-18 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience |  | 120000
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | Y
[8 empty] | national |  | N
Dates | [7 empty] | international |  | N
Project start date | 2016-04-01 |  | Project live date |  | 2017-01-12 |  |  | children (<16) |  | N
End of Live date | 2017-01-15 |  | End of eval. date |  | 2017-03-31 |  |  | young people (16-25) |  | N
[8 empty] | families |  | Y
Categories | [7 empty] | older people (60+) |  | N
Type | Hull 2017 Production |  |  | Strand |  | Caravan of Love |  | self-identify as disabled |  | N
Season | Made in Hull |  |  | Digital requirements |  | Very high |  | BME |  | N
[8 empty] | NEET |  | N
Finance | [6 empty] | # temporary jobs created |  | tbc
Total project budget |  | 1000000 |  |  |  |  | # freelance contracts created |  | 15<
Hull 2017 contribution |  | 1000000 |  |  |  |  | # participation opportunities
Analysis/project code(s) |  | tbc |  |  |  |  | of which for school age
[7 empty] | # commissions |  | 5<
[7 empty] | Objective |  | Met? | Notes
Create a new archive of Hull stories
People | [6 empty] | Invite every Hull resident to the live performances
Project Lead | Martin Green |  |  | Volunteering lead |  | Shaun Crummey
Producer | TBC (Chris Clay interim) |  |  | Education lead |  | Ian Read | Create and deliver a spectacular opening event
Assistant Producer | TBC |  |  | Marketing lead |  | Laura Smith
Production Manager | TBC |  |  | Community Eng lead |  | James McGuire | Generate National media coverage & interest
|  |  |  | Evaluation lead |  | Elinor Unwin
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
Hull 2017 will be lead producer on this project working with partners from Hull University, the History Centre, the Libraries Service, Hull Culture & Leisure and the Yorkshire Film Archive. We will recruit a team of freelance creatives and production staff to create and deliver the project under the guidance of senior members of the Hull 2017 team, Production resources and infrastructure will be procured directly by Hull 20217. | [6 empty] | The project's live element will be a spectacular 4 day event to which every Hull resident is invited. It will also provide an opportunity for media and Vip engagement and will mark the official start of Hull 2017. Performances will be Jan 12th - 15th 2017 and will be free.
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
The archiving element of the project will be delivered by partners through existing relationships. Many of these elements will be providing as VIK and will therefore not be required to go through the procurement process. Creatives and artists will be exempt from procurement as these will be curatorial decisions. Production infrastructure will be subject to procurement and most contracts will fall under the light touch regime or will be below the OJEU thresholds, so the majority of contracts will be procured using procedure C, E or F. All procurement will be governed by the Hull 2017 procurement policy. | [6 empty] | The project will enagage with residents across Hull during the story gathering period. This will take place for several months throughout 2016 during roadshows which will visit all areas of the city. A complementary programme could be run in schools across the city.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
All partners are currently in a period of project development and scoping, no contracts have been issued yet. The main partners are; Hull History Centre (Martin Taylor & Simon Wilson); Hull Culture & Leisure (Jessica Leathley & Jane Avison); Hull University (Rosemary Wall) & Yorkshire Film Archive (Sue Howard). An offer has been made to a creative director and contract negotiations are ongoing. | [6 empty] | The project will create a new archive of stories of Hull, which will be available to all. This will add to and complement exiting archives held by the History Centre and University.
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
This project wil offer many volunteer opportunities, numbers and roles will be defined as the project develops, ket opportunities will be in the following areas: Assisting with the gathering of stories and archiving Working backstage on the live performance element of the project Performing as volunteer cast Stewarding and audience management for the live performances Artist & guest liaison for the live performances | [6 empty] | The first and opening event of our year as UK City of culture, and the first of the season Made in Hull will be a large scale and comprehensive celebration of the city, and a statement of intent of the way we intend to (re)position the city, engage in meaningful ways with its communities, produce innovative and inspiring major events and leave a legacy from everything we do. Caravan of Love references both a song by an internationally famous Hull band and just one of the many things Hull makes and exports to the world, caravans. It is split into three parts; Discovery, Creation and Enactment producing a year-long programme of activity where the sourcing and archiving of the material that makes the event is as important as the event itself. Pragmatically the event lasts for four days and some content will be on hourly cycles. This is to at once challenge what an ‘opening event’ should and can be but also to ensure that we can accommodate the entire population of the city and additional visitors should they be inspired to attend. We will also host a formal moment for press and stakeholders, sponsors and funders.
Version control
Date | Changes and/or approvals
2016-01-19 | Greenlit at Board
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize