|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Sirius Academy West |
| **Name of Project** | Pickering Park ‘Park Life’ Performance |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| present | November 2016 | Creative Team at Sirius Academy to begin planning including identifying Professional Practitioner and Student Participants. |  |  |
| November 2016 | December 2016 | Development work with Professional Practitioner to agree framework for the project. |  |  |
| January 2017 | March 2017 | 8 Research, exploratory and devising workshops with student participants |  |  |
| March 2017 | April 2017 | Professional Practitioner works with Creative Team at Sirius to finalise performance structure and content from the students workshop material. |  |  |
| April 2017 | June 2017 | 10 Art, Design and photography workshops with Student Participants to work on marketing & poster design, production & costume design and original works of public art to be incorporated into the performance. |  |  |
| April 2017 | July 2017 | 10 Rehearsals |  |  |
| April 2017 | July 2017 | Marketing, press and PR |  |  |
| 10th July (tbc) | 12th July (tbc) | 2 Technical and dress rehearsals |  |  |
| 13th July 2017 (tbc) | 15t July 2017 (tbc) | Production |  |  |
| July 2017 | September 2017 | Evaluation Report |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances