## Sheet1
THE LAST BALLAD OF LILLIAN BILOCCA
LAST UPDATED 11.07.17
W/C | ACTIVITY | REHEARSAL SCHEDULE | LOCATION | TIMES | TEAM AVAILABILITY | GUILDHALL | NOTES
2017-05-22
2017-05-29 |  | Full creative team visit | Hull | Full day
Mon 5 Jun 2017
2017-06-12
2017-06-13
2017-06-14
2017-06-15
2017-06-16 |  | Venue site-visit & walk-around / Research visit / Professional company auditions | Hull / Hull Truck | 12pm - overnight / 2pm - 6pm | Sarah & Imogen AV. Jon NA during the day |  | CONFIRMED
2017-06-17 |  | Community Company catch up | Station hotel | 9am - 12pm | Sarah, Imogen, Jon, Lindsey, Harriet, James & Ruth |  | CONFIRMED
2017-06-18
2017-06-19
2017-06-20 |  | Casting of Professional Cast Confirmed | London | 11am - 4pm |  |  | CONFIRMED
Weds 21 June 2017
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26 |  | Community Company - targeted call out |  |  | Amanda NA
2017-06-27 |  |  |  |  | Amanda NA
2017-06-28 |  | Casting of Professional Cast | Manchester/Hull |  | Amanda NA |  | TBC
2017-06-29 |  |  |  |  | Amanda NA
2017-06-30 |  |  |  |  | Amanda NA
2017-07-01 |  |  |  |  | Amanda NA
2017-07-02 |  |  |  |  | Amanda NA
Amanda NA / Sarah NA
2017-07-04 |  | Casting of Professional Cast (am) |  |  | Amanda NA / Sarah NA |  | TBC
2017-07-05 |  |  |  |  | Amanda NA / Sarah NA
2017-07-06 |  |  |  |  | Amanda NA / Sarah NA
2017-07-07 |  |  |  |  | Amanda NA / Sarah NA / Jon NA
2017-07-08 |  | Community Company auditions |  |  | Sarah NA / Imogen & Jon to lead
2017-07-09 |  |  |  |  | Sarah NA / Imogen NA
2017-07-10 |  |  |  |  | Imogen NA until 22 Aug / Sarah NA
2017-07-11 |  |  |  |  | Sarah NA / Imogen NA
2017-07-12 |  |  |  |  | Sarah NA / Imogen NA
2017-07-13 |  |  |  |  | Sarah NA / Imogen NA
2017-07-14 |  |  |  |  | Sarah NA / Imogen NA
2017-07-15 |  |  |  |  | Sarah NA / Imogen NA
2017-07-16 |  |  |  |  | Sarah NA / Imogen NA
2017-07-17 |  |  |  |  | Sarah NA / Imogen NA
2017-07-18 |  |  |  |  | Sarah NA / Imogen NA
2017-07-19 |  |  |  |  | Sarah NA / Imogen NA
2017-07-20 |  |  |  |  | Sarah NA / Imogen NA
2017-07-21 |  |  |  |  | Sarah NA / Imogen NA
2017-07-22 |  |  |  |  | Sarah NA / Imogen NA
2017-07-23 |  |  |  |  | Sarah NA / Imogen NA
2017-07-24 |  |  |  |  | Imogen NA
2017-07-25 |  |  |  |  | Imogen NA
2017-07-26 |  |  |  |  | Imogen NA
2017-07-27 |  |  |  |  | Sarah NA / Imogen NA
2017-07-28 |  | Final model meeting | Hull |  | Imogen NA |  | CONFIRMED
2017-07-29 |  |  |  |  | Imogen NA
2017-07-30 |  |  |  |  | Imogen NA
2017-07-31 |  |  |  |  | Sarah NA / Imogen NA
2017-08-01 |  |  |  |  | Imogen NA
2017-08-02 |  |  |  |  | Sarah NA / Imogen NA
2017-08-03 |  |  |  |  | Sarah NA / Imogen NA
2017-08-04 |  |  |  |  | Imogen NA
2017-08-05 |  |  |  |  | Imogen NA/ Sarah & Jon to lead
2017-08-06 |  |  |  |  | Imogen NA / Sarah & Jon to lead
2017-08-07 |  |  |  |  | Sarah NA / Imogen NA
2017-08-08 |  |  |  |  | Imogen NA
2017-08-09 |  |  |  |  | Imogen NA
2017-08-10 |  |  |  |  | Sarah NA / Imogen NA
2017-08-11 |  |  |  |  | Sarah NA / Imogen NA
2017-08-12 |  |  |  |  | Sarah NA / Imogen NA
2017-08-13 |  |  |  |  | Sarah NA / Imogen NA
2017-08-14 |  |  |  |  | Sarah NA / Imogen NA
2017-08-15 |  |  |  |  | Sarah NA / Imogen NA
2017-08-16 |  |  |  |  | Sarah NA / Imogen NA
2017-08-17 |  |  |  |  | Sarah NA / Imogen NA
2017-08-18 |  |  |  |  | Sarah NA / Imogen NA
2017-08-19 |  | Community Company auditions |  |  | Sarah NA / Imogen NA
2017-08-20 |  |  |  |  | Sarah NA / Imogen NA
2017-08-21 |  |  |  |  | Sarah NA / Imogen NA
2017-08-22 |  |  |  |  | Sarah NA / Imogen NA
2017-08-23 |  |  |  |  | Sarah NA / Imogen returns
2017-08-24 |  |  |  |  | Sarah NA
2017-08-25 |  |  |  |  | Sarah NA
2017-08-26 |  |  |  |  | Sarah NA
2017-08-27 |  |  |  |  | Sarah NA
2017-08-28 |  |  |  |  | Sarah NA
2017-08-29 |  |  |  |  | Sarah NA
2017-08-30 |  | Hull 2017 Season Launch |  |  | Sarah NA
2017-08-31 |  |  |  |  | Sarah NA
2017-09-01 |  |  |  |  | Sarah NA
2017-09-02 |  |  |  |  | Sarah NA
2017-09-03 |  |  |  |  | Sarah NA
2017-09-04 |  |  |  |  | Sarah NA
2017-09-05 |  |  |  |  | Sarah NA
2017-09-06 |  |  |  |  | Sarah NA
2017-09-07 |  |  |  |  | Sarah NA
2017-09-08 |  |  |  |  | Sarah NA
2017-09-09 |  | Community Company auditions |  |  | Sarah NA
2017-09-10 |  |  |  |  | Sarah NA
2017-09-11 |  |  |  |  | Sarah NA
2017-09-12 |  |  |  |  | Sarah NA
2017-09-13 |  |  |  |  | Sarah NA
2017-09-14 |  |  |  |  | Sarah NA
2017-09-15 |  |  |  |  | Sarah NA
2017-09-16 |  |  |  |  | Sarah NA
2017-09-17 |  |  |  |  | Sarah NA
2017-09-18 |  |  |  |  | Sarah NA
2017-09-19 |  |  |  |  | Sarah NA
2017-09-20 |  |  |  |  | Sarah NA
2017-09-21 |  |  |  |  | Sarah NA
2017-09-22 |  | Community Company - Workshop | TBC | 6pm - 8pm | Sarah NA / Jon to lead
2017-09-23 |  | Community Company - Workshop | TBC | 10am - 12pm | Sarah NA / Jon to lead
2017-09-24 |  |  |  |  | Sarah NA
2017-09-25
2017-09-26 |  |  |  |  | Sarah NA
2017-09-27
2017-09-28 |  |  |  |  | Sarah NA
2017-09-29 |  | Community Company Workshop |  | 6pm - 8pm | Jon to lead
2017-09-30 |  | Community Company Workshop |  | 10am - 12pm | Sarah NA / Jon to lead
2017-10-01 |  | Adrian performing in Hull |  |  | Sarah NA
2017-10-02 | Rehearsal Week 1 | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-03 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-04 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-05 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-06 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
|  | Community Company - Evening workshop | TBC | 6pm - 8pm | Jon to lead
2017-10-07 |  | Community Company - Workshop | TBC | 10am - 12pm | Jon to lead
2017-10-08
2017-10-09 | Rehearsal Week 2 | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-10 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-11 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-12 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-13 |  | Professional Cast rehearse in Manchester | Manchester |  | Jon AV
2017-10-14
2017-10-15
2017-10-16 | Rehearsal Week 3 | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm |  |  | Composer / MD rehearse in Hull (2 Days)
|  | Community Company - Evening workshop |  | 6pm -8pm | Jon to lead
2017-10-17 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Company - Evening workshop |  | 6pm - 8pm | Jon to lead
2017-10-18 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Company - Evening workshop |  | 6pm - 8pm | Jon to lead
2017-10-19 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Company - Evening workshop |  | 6pm - 8pm | Jon to lead
2017-10-20 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Company - Evening workshop |  | 5:30pm - 7:30pm | Jon to lead |  | Meet and greet professional cast & community company ??
2017-10-21 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm
|  | Community Company - Evening workshop |  | 10am - 12pm | Jon to lead
2017-10-22 |  | Day off |  | No Call
2017-10-23 | Rehearsal Week 4 | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Cast Rehearsals | Holy Apostle | 6pm - 8pm | Jon to lead
2017-10-24 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Cast Rehearsals | Holy Apostle | 6pm - 8pm | Jon to lead
2017-10-25 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Cast Rehearsals | Holy Apostle | 6pm - 8pm | Jon to lead
2017-10-26 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Cast Rehearsals | Holy Apostle | 6pm - 8pm | Jon to lead
2017-10-27 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm; 6 - 9pm
|  | Community Cast Rehearsals | Holy Apostle | 6pm - 8pm | Jon to lead
2017-10-28 |  | Professional Cast rehearse in Hull | Holy Apostle | 10am - 5pm
2017-10-29 |  | Day off - no call
2017-10-30 | Tech Week | Professional Cast rehearse in Hull | Reh Sp 2 | 10am - 5pm; 6 - 9pm |  | Technical Work | Composer/MD rehearse in Hull (full week)
|  | Joined by Community Cast | Reh Sp 2 | 10am - 6pm
2017-10-31 |  | Technical Rehearsals: Professional Cast | Reh Sp 2 - AM Guildhall - PM | 10am - 5pm; 6 - 9pm |  | Tech Sessions
|  | Joined by Community Cast | Guildhall | 2pm - 9pm
2017-11-01 |  | Technical Rehearsals: Professional Cast | Guildhall | 10am - 5pm; 6 - 9pm |  | Tech Sessions
|  | Joined by Community Cast | Guildhall | 2pm - 9pm
2017-11-02 |  | Technical Rehearsals: Professional Cast | Guildhall | 10am - 5pm; 6 - 9pm |  | Tech Sessions
|  | Joined by Community Cast | Guildhall | 2pm - 9pm
|  | Full Band Call | Guildhall | 10am - 5pm; 6 - 9pm
2017-11-03 |  | Dress Rehearsal - Full Company Call (Cast, Band, Community) | Guildhall | 1pm - 5pm |  | Tech Session AM
|  | Performance PREVIEW 1 @7:30pm | Guildhall | 7.30pm
2017-11-04 |  | Full Company Call | Reh Sp 2 | 1pm - 3pm |  | Technical Work
|  | Performance PREVIEW 2 @ 3:30pm | Guildhall | 3.30 - 6pm
|  | Performance PREVIEW 3 @ 7:30pm | Guildhall | 7pm - 10pm |  |  | Astronomical twilight 5:31pm
2017-11-05 |  | Day off - no call
2017-11-06 | Performance W1 | Tech Work | Guildhall |  |  | Technical Work
No call Professional cast, community cast, band.
2017-11-07 |  | Technical Rehearsals: Professional cast and community cast | Guildhall | 2pm - 5pm ; 6pm - 9pm
2017-11-08 |  | Technical Rehearsals: Professional cast and community cast | Guildhall | 2pm - 5pm
|  | Performance PREVIEW 4 @ 5:30pm | Guildhall | 5pm - 8pm
|  | Performance PREVIEW 5 @ 8:30pm | Guildhall | 8pm - 11pm
2017-11-09 |  | Performance PRESS NIGHT @ 7:30pm | Guildhall | 7pm - 10pm
2017-11-10 |  | Performance 1 @ 5:30pm | Guildhall | 5pm - 8pm
|  | Performance 2 @ 8:30pm | Guildhall | 8pm - 11pm
2017-11-11 |  | Performance 3 @ 3:30pm | Guildhall | 3pm - 6pm
|  | Performance 4 @ 7:30pm | Guildhall | 7pm - 10pm
2017-11-12 |  | Day off - no call
2017-11-13 | Performance W2 | Day off - no call
2017-11-14 |  | Day off - no call
2017-11-15 |  | Performance 5 @ 5:30pm | Guildhall | 5pm - 8pm
|  | Performance 6 @ 8:30pm | Guildhall | 8pm - 11pm
2017-11-16 |  | Performance 7 @ 7:30pm | Guildhall | 7pm - 10pm
2017-11-17 |  | Performance 8 @ 8:30pm | Guildhall | 8pm - 11pm
2017-11-18 |  | Performance 9 @3:30pm | Guildhall | 3pm - 6pm
|  | FINAL Performance 10 @ 7:30pm | Guildhall | 7pm - 10pm
2017-11-19 |  | Get-Out
2017-11-20 |  | Get Out
2017-11-21 |  | Get Out
2017-11-22 |  | Get Out
2017-11-23 |  | Get Out
2017-11-24 |  | Get Out
2017-11-25 |  | Get Out
2017-11-26 |  | Get Out
Formulas:
W/C = SUM([W/C, row above]+7)