## Risk register
[6 empty] | Inherent |  |  |  | Residual
Risk ref | Risk type | Risk | Potential impact | Risk owner | Risk manager | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Date logged | Status
1.01 |  | What might happen | The consequences |  |  | 3 | 5 | 15 | What has happened, and what else is planned, to reduce either likelihood or impact, or both | 2 | 4 | 8 | 2016-07-26 | Open
| Staffing | Long term Illness of the facilitators or core staff. | We may require to train staff and additional people to fill in this role at the last moment and there would be a cost implication to this as well as a reputational risk aspect.. |  |  | 2 | 4
|  | Public holidays and holidays for staffing or CD working on another project | Not enough staff to cover the daily activities or no actives offered on key holidays. This is a budgetary challenge on the operations regarding the lifetime of the project. |  |  | 4 | 5 |  | Set up as part of critical path holiday and sensitive dates.
|  | Staff leaving. | product is compromised and does not hold the wow factor that the first event should achieve, thus a knock on effect to the project |  |  | 4 | 3 |  | this will be budget related but we are again working on planning and creative simultaneously to try to mitigate this.
| Content | Artist interest or engagement is too late and stops meaningful briefs being written and answered. | Limited or no interpretation reduced experience for audiences, doesn't meet creative directors requirements, doesn’t meet individual commissioned artist expectations |  |  | 1 | 1 |  | Budget is in line with forcast but there is no flex in this. | 1 | 2 |  |  | Closed
|  | Interpretation: the team are unable to deliver interpretation, due to timeframe and staff numbers. tight deadline and current status of project- | Diminishes visitor experience at what is potentially disruptive during Christmas period. |  |  | 2 | 2 | [6 empty] | Closed
|  | Installation of sculpture - negative impact on viewing visitor experience. Due to timings of Sculpture installation | We need guarantees this can be done in the time frame and to the inch of what the plans are showing as this will be very detrimental and could stop the main sight being able to be shown for Made in Hull as this I true Projection mapping across multiple buildings. and digitization changes alone will take 12 hrs. or more for changes. | NH and SM | CC | 1 | 1 |  | Resolved | 1 | 1 |  |  | Closed
|  | The Content could be effected by budget |  |  |  | 4 | 5 |  | we have started to work with artists on this but it is still a risk at present. We have removed 2 artists already to free some monies up to help support other ideas. | 3 | 4
|  | No projection allowed within key locations. | This will impact of the experience especially in the busy times and any Lates we may wish to place on. |  |  | 4 | 4 |  | We have acceptance from the Deep, we are working on the other locations to gain permissions. Oriel house said no so a new location has been found. | 2 | 3 |  |  | Closed
|  | No sound scape within area. | Reputational risk and failure to establish our brand values and be recognised in a wider market. |  |  | 2 | 4 |  | mitigated. | 2 | 2 |  |  | Closed
|  | The content is not representative of the vision | An opportunity missed to attract and broader and more diverse audience profile that would then be engaged by our KPI's for Kew as a whole. Missed future opportunities as we did not demonstrate our credentials within a sector. |  |  | 4 | 4 |  | sigbn off has oiccured in most cases with others being signed off on the week of the 19th, but all have progressed in line with the vision. | 1 | 4 |  |  | closed
|  | The content is not targeted to the diverse audience profiles and does not encapsulate all those who visit over the year with the audience profiles we want to attract. | Loss of information and the 360 degree experience that the piece can offer as well as a missed opportunity to showcase kews technology in relation to other attraction sites during the event. |  |  | 4 | 5 |  | Strategy including AP has been produced by NH as distributed to PR, Marketing, Digital and other FA's who require it. | 2 | 2 |  |  | Closed
|  | No Wi fi in the surrounding area |  |  |  | 5 | 4 |  | we have decided due to budget not to look ayt this for the event | 1 | 1 |  |  | Closed
|  | Limited timeframe will impact on programming. Due to the short timeframe for pulling together a programme and therefore reliance on existing materials |  |  |  | 5 | 4 |  | Fruit is the only outstanding item but Lindsey has a programme and is working with Fruit to get these on sale. All commisioned bar the Film night. | 4 | 2
| Operations and Logistics | Inability to find and employ support staff for tours | diminished audience expereience. |  |  | 3 | 3 |  | this has been completed. | 3 | 3 |  |  | closed
|  | Crowd management issues within the street on busy periods and limited staffing dedicated to the venue. | Reputational Risk, Accident or public order challenges. |  |  | 4 | 5 |  | We will inform the police and make the whole schedule available to Emerg services. Conversations with the Police and SAG have begun and will continue. | 3 | 4
|  | There is a danger of persons climbing the structures placed in | Reputational Risk, Accident or public order challenges. |  |  | 2 | 5 |  | all structures will be minded. |  |  |  |  | Closed
|  | In wet or adverse weather so we may need to be closed. | Reputational Risk, Accident or visitors miss the experience during their visit. |  |  | 4 | 4 |  | We will look at long term forecasts and if we do need to close we will advertise this on our web sites and through social media. A policy on this is being written by GC. | 3 | 3
|  | Crowd management issues because of numbers being considerably higher than expected or in one area it becomes too crowded. | Over crowding, Reputational Risk, Accident or public order challenges resulting in the closure of certain parts of the trail |  |  | 4 | 5 |  | security and VH on hand to help crowd control as well as Police. It is the streets with no barriers so this is a public order concern only. | 3 | 3
| Technical | The IT or power equipment could fail on the open nights with no back up available | Back up sound recording would need to be activated. Loss of live experience and investigations with lengthy and costly repairs needing to be undertaken |  |  | 3 | 4 | [6 empty] | Closed
|  | Projection, Lighting and Sound could go wrong within the week period. | Loss if experience to Visitors and the Hive needing to be closed for repairs. |  |  | 3 | 5 |  | we have back up projectors to mitigate this.
|  | cleaning of the streets over night to ensure the area is maintained and is not adversely effected or causes an H&S issue. |  |  |  | 3 | 5 |  | we will order this and again talk to the council about the areas we are utilizing.
| Staff and Project Organisation | There are no medics budgeted for on non opening hours | increse to amberlance response times |  |  | 2 | 3 |  | We need to change this and have asked GC to scope and come back to us. On the premis of 2x first aid medics and a bike. This has been approved at city level. |  |  |  |  | Closed
| Commercial and sponsorship | There is currently no Sponsor for the opening project | we don’t have live performance at present and limited funds for Fruit, |  |  | 4 | 3 | [6 empty] | Closed
| Licensing & Budgeting | Live performance license denied. | No live acts or late activities |  |  | 3 | 4 |  | Tech team have licenced materials and Legal team with NH have licenced all archive footage. |  |  |  |  | Closed
|  | Late opening are not covered within the budget and the costs out way any revenue. | No live acts or late activities |  |  | 5 | 4 |  | we have the option to remain open for 1 additional hour should we be very busy and need to make that call at 7pm each night. | 1 | 1 |  |  | Closed
|  | planning license denied. | No activities |  |  | 3 | 5 |  | Licensing is being sort for all sights now by CC. |  |  |  |  | Closed
|  | Transport plan denied | [11 empty] | Closed
Note on G2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on H2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on J58: Crawford James: HD: To flag - are we running credit checks on partners? Currently not on CCP.
Note on K2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on L2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe

## Options
Risk types | Status | Risk levels
| Closed | Low (<10)
| Open | Medium (10-15)
High (16-25)