## Sheet1
Made in Hull - Marketing overview
|  |  | Dec |  |  |  | Jan
Activity | Production Notes | Size/Dimensions | 5th | 12th | 19th | 26th | 2nd | COST | Notes
Newspaper advertising
Yorkshire Post | Thurs 15th / Wed 28th Dec | 1/2 page - 270mmx 324mm |  | * |  | * |  | 2196
Yorkshire Evening Post | Thrs 22nd/ Fri 30th Dec | 1/2 page - 170mm x 265mm |  |  | * | * |  | 1548
York Press | Thurs 8th/ Wed 28th Dec | 1/2 page - 160mm x 259mm | * |  |  | * |  | 1050
Holderness Gazette | Thurs 29th Dec | 1/2 page - 170mm x 265mm |  |  |  | * |  | 150
Bridlington Free Press and Scarborough EN | Thurs 5th Jan | 1/2 page - 170mm x 265mm |  |  |  |  | * | 480
East and North Yorkshire Times | Monthly - Dec Issue | 1/2 page - 170mm x 265mm | * |  |  |  |  | 250
Pock Post | Thurs 29th Dec | 1/2 page - 170mm x 265mm |  |  |  | * |  | 220
[8 empty] | 5894 | Bluestorm for all above - PO raised originally for £9707
Hull Daily Mail
HDM | Tues 3rd Jan | 1/2 page - 170mm x 270mm |  |  |  |  | * | 300
Beverley Advertiser | Fri 30th Dec | Full page - 340mm x 270mm |  |  |  | * |  | 188
HDM website | HPTO Wed 21st Dec | See sep doc |  |  | * |  |  | 500
Grimsby & Scun Telegraph | Thurs 5th Jan | Full page - 340mm x 270mm inclu digital |  |  |  |  | * | 525
[8 empty] | 1513 | To be journaled against spend with HDM
Media management
Management of research and revised matrix | [7 empty] | 360 | Bluestorm PO raised (as per of £9707 - see above)
Outdoor advertising
HCC | Various - 26 locations city-wide | 6-sheets - 20th Dec - 3rd Jan |  |  | * | * |  | 800 | BOOKED SEPARATELY - NOT TO COME OUT OF BUDGET
Creative charges
Time for design of wayfinding map, press adverts and various posters |  |  |  | * | * | * |  | 1600 | Process Black- PO raised but under marketing freelance as part of wider £3200 PO in marketing "freelance" budget. Need to reconfigure.
Wayfinding maps
Wayfinding maps - PRINT | 100,000 x wayfinding maps. 12pp DL fold out to A3. Full colour on 130gsm. Delivery to Danish 1. | A3 flat size (12pp DL) |  |  |  |  | * | 3830 | Bluestorm - PO raised
Wayfinding maps - PRINT | 25,000 x additional wayfinding maps. Same spec. Delivery to x 3 addresses. | A3 flat size (12pp DL) |  |  |  |  | * | 1484 | Bluestorm - PO raised
Wayfinding maps - PRINT | x 100 large format A2 copies of wayfinding map | A2 flat size (12pp A4) |  |  |  |  | * | 334 | From access budget code - PO Raised
Wayfinding maps - PRINT | x 50,000 additional maps distributed to 10 key places in Hull & E Riding | A3 flat size (12pp DL) |  |  |  |  | * | 1850 | From campaigns budget code - PO raised
Wayfinding maps - DELIVERY | 20,000+ copies for inclusion in Grimsby and Scunthorpe Telegraph w/c 29th Dec | A3 flat size (12pp DL) |  |  |  | * |  | 1188 | From campaigns budget code - PO raised
5314
Residential comms
Residential letter for 1666 addresses in city centre | Sending second class post. Including envelopes, print and fulfilment. Delivered w/c 19th Dec. | Normal DL letter size | [5 empty] | 1100 | Bluestorm - PO raised
Interpretation Boards
Project management support | Final checking of interp boards and hoardings for print | Various |  |  | * |  |  | 250 | Bluestorm - PO raised
Interp/ hoardings | As per master spreadsheet | Various |  |  |  |  | * | 6905 | John E Wright - PO raised
Interp/hoardings | QVS and hides production | Various |  |  |  |  | * | 6668 | John E Wright - PO raised - £7230
Interp/hoardings | Extras: fittings, new boards, black vinyls etc. | Various |  |  |  |  | * | 1000 | John E Wright - PO raised
Interp/hoardings | [7 empty] | 437 | CHECK - billed as part of £7230?
Interp/hoardings | 20 x foamex boards, stencils, fruit frame | Various |  |  |  |  | * | 1464 | Image Data - PO raised
Interp/hoardings | Additional cost for Andy's time and materials on NYE | Various |  |  |  |  | * | 250 | John E Wright - PO raised
16974
Social media
DAVID TO ADVISE ON SPEND
Other
Posters | Do not enter, artists room etc. x 17 A3 laminated |  |  |  |  | * |  | 42.5 | Kall Kwik - PO raised