**CREATIVE COMMUNITIES PROGRAMME**
**END OF PROJECT REPORT**

**GENERAL INFORMATION**

|  |  |
| --- | --- |
| **PROJECT NAME:** | Born into a city of culture |
| **PROJECT LEAD:** | Sallie Ward |
| **REPORT DATE:** | 13th November 2017 |

**INTRODUCTION**

Everyone who receives a grant from the Creative Communities Programme must complete this End of Project Report. Please read it straight away – you will need to collect the information throughout the lifetime of your project.

Please refer to your Agreement, and any changes you agreed with us, when you complete this Report.

This End of Project Report tells us:

* What has happened during your project as a whole;
* Your final income and expenditure figures;
* What you have learned from the project, how you have adapted to these learnings, and what you plan to do with this learning in future.

We will send you a separate online survey about your experience of the Creative Communities Programme as a grant recipient. We will process the information you give us to understand:

* The outcomes and impacts of our grant and support on your organisation;
* The effectiveness of our services and grants administration; and
* What key things the city needs to be aware of in future, when supporting community level arts and culture projects.

We also use this information to report to our funders.

Please email this activity report to: creativecommunities@hull2017.co.uk

1. **PROJECT REPORT**

Please provide a brief update (3 or 4) sentences on each of the following areas to let us know how your project went, what you’ve learnt and how well we supported you.

**EVENT PLANNING AND PROJECT MANAGEMENT**

The project ran over a full year and has been received by the public in a very positive light.

We still got 400 footprints in each month and the participation has been continuous throughout the year

The midwives on the wards have participated in the project and ensured the footprints were taken prior to the babies leaving hospital.

Jenko were very supportive in ensuring the panels were fitted each month and all the footprints scanned in very efficiently

**MARKETING AND COMMUNCIATIONS, PARTICIPATION AND LEARNING**

We used the hospital facebook page to let the public know when each new panel was fitted and the response was overwhelming

Look North and Radio Humberside have given excellent publicity to the project we have even been invited to their Christmas party !

We learnt that social media was the best way to promote the project and all the positive publicity has been excellent for the hospital.

**RISK MANAGEMENT**

At the beginning of the year we had not accounted for the fact that the midwives would be generous and repeat footprints if not quite perfect and we were in danger of running out of funds as they were using all our supplies

We commissioned a set of commerative postcards which have been hugely popular and sold them at a £1 each. This has helped us to self fund the shortfall and ensure the project continued to the end.

**BUDGET**

In this section we ask for a final summary of the income and expenditure of your activity to date.

Pleasecomplete the Budget Template provided. The template includes instructions on how to complete it.

**Please use the space below for any comments and supporting information.**

**Specific Requirements - VAT**

If you are registered for VAT, your expenditure figures should not include VAT that you can claim back. If you are not registered for VAT, your figures should include VAT. You may need to get advice from your own accountant or the relevant tax office. For information about VAT and other taxes, contact HM Revenue and Customs (HMRC) through their website at [www.hmrc.gov.uk](http://www.hmrc.gov.uk)

**B. MONITORING & EVALUATION REPORT**

1. **Event Delivery**

**How did you do on reaching the targets laid out for project activity?**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **ORIGINAL TARGET\*** | **REVISED TARGET\*** | **TOTAL\*** |
| **PROJECT VENUE/LOCATION** |  |
| HU1 – HU9 |  |  |  |
| Not HU1 – HU9 |  |  |  |
| **ACTIVITY** |  |
| Number of performances |  |  |  |
| Number of exhibition days | 365 | 365 | 365 |
| Number of commissions\* | 1 | 1 | 1 |
| Number of sessions for education, training or taking part\* | 0 | 0 | 0 |
| Number of accessible activities |  |  |  |

**\*Original target: target(s) listed within your contract
\*Revised target: new suggested targets now that your project planning and delivery is underway
\*Total: final figures for the project as a whole
\*Commissions: a commission is defined as the hiring or payment to an artist / artistic company to create an art work or performance. A commission can be wholly or partly funded by you / your organisation.
\*Sessions for education, training or taking part: includes guided sessions, learning sessions, skills development workshops, formal training of volunteers, practical workshops, all other community/public facing workshops.**

If your project incorporated heritage, please briefly say how you developed, presented and / or told people about heritage or historical content, e.g. using heritage buildings or sites, collecting oral history (stories and memories), displaying historical artworks or collections, working with museums or archives, sharing or presenting historical stories or events.

1. **Project Delivery Team**

**Who was involved in delivering your project? Please include yourself, employees and any freelancers that you contracted for this project.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL NO. INDIVIDUALS**  | **TOTAL NO. OF DAYS WORKED** | **TOTAL NO. OF HU1-HU9 RESIDENTS** | **TOTAL NO. OF DAYS WORKED BY HU1-HU9 RESIDENTS** |
| **CATEGORY OR ROLE** |
| Project Manager(s) | 1 | Full time |  |  |
| Artists | 1 | monthly |  |  |
| Production/exhibition staff |  |  |  |  |
| Other staff | 200 | 365 |  |  |
| Volunteers | 4 | various |  |  |

**Using the equal opportunities form provided in the Toolkit, please complete the Total column within the tables below for all people involved in the Delivery Team for your project. We recommend that you ask all members of the project Delivery Team to complete this form at the start of the project, and include it as part of the contracting process for any new staff or freelancers going forward.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL** |  |  | **TOTAL** |
| **AGE GROUPS – DELIVERY TEAM** |  | **DISABILITY/LONG TERM ILLNESS – DELIVERY TEAM** |
| 16-17 years |  |  | Yes |  |
| 18-19 years |  |  | No |  |
| 20-24 years |  |  | Prefer not to say |  |
| 25-29 years |  |  | **CONDITIONS – DELIVERY TEAM** |
| 30-34 years |  |  | Learning disability |  |
| 35-39 years |  |  | Long-term illness/condition |  |
| 40-44 years |  |  | Sensory impairment |  |
| 45-49 years |  |  | Mental Health condition |  |
| 50-54 years |  |  | Physical impairment |  |
| 55-59 years |  |  | Cognitive impairment |  |
| 60-64 years |  |  | Other |  |
| 65-69 years |  |  |  |  |
| 70-74 years |  |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say |  |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL** |  |  | **TOTAL** |
| **GENDER - DELIVERY TEAM** |  | **ETHNICITY – DELIVERY TEAM** |
| Male |  |  | Welsh/English/Scottish/Northern Irish/British |  |
| Female |  |  | Irish |  |
| Transgender |  |  | Gypsy or Irish Traveller |  |
| Other |  |  | Any other White background  |  |
| Prefer not to say |  |  | White and Black Caribbean |  |
|  |  |  | White and Black African |  |
|  |  |  | White and Asian |  |
|  |  |  | Any other Mixed/multiple ethnic background  |  |
|  |  |  | Indian |  |
|  |  |  | Pakistani |  |
|  |  |  | Bangladeshi |  |
|  |  | Chinese |  |
|  |  |  | Any other Asian background |  |
|  |  |  | African |  |
|  |  |  | Caribbean |  |
|  |  |  | Any other Black/African/Caribbean background  |  |
|  |  |  | Arab |  |
|  |  |  | Any other ethnic group  |  |
|  |  |  | Prefer not to say |  |

**Thinking about your project as a whole, what would you say have been the main successes and challenges for you and your project delivery team (approximately 500 words):**

**This can include formal and informal feedback given to you by staff and / or your own observations. You can use notes or minutes from project team meetings; informal conversations; emails; etc. to inform this.**

Our success was community engagement and a really positive public response. We feel honored to have contributed to the city of culture year and what better way to start than at the very beginning of life.

Our challenge was making sure the babies had their prints taken no matter how busy we were and organizing to do them for any we had missed.

Our main challenge was financial as the resources we used were in danger of running out due to the generosity of the midwives often doing more than one footprint in the beginning. We overcame this by producing some postcards of the artwork and selling them for a £1 each to further fund the wipes needed to produce the footprints.

The main thing I have learnt is the processes of payment through the hospital system of suppliers and the kindness of the suppliers tolerating this slow and unwieldy process.

I personally have loved this project and the fact we have created something that will be a lasting memory for so many families and we would love to think of some way of continuing this very positive outcome.

1. **Audiences & Participants**

**How many people, in total, attended or participated in the project as a whole?**

|  |  |  |
| --- | --- | --- |
| **TYPE OF ENGAGEMENT** | **TOTAL** | **% FROM HU1-HU9** |
| Number of audience members\* | 1,000s coming through foyer | As other column |
| Number of participants\* | Approx. 5,000 | Approx. 3,500 |
| **TOTAL BENEFICIARIES** |  |  |

**\*The % can be taken from the results of your audience and participant surveys or box office reports
\*‘Audience members’ includes people going to an exhibition or performance, and people getting access to work that is printed, recorded, broadcast or on the internet.**
**\*‘Participants’ means those doing the activity.**

**Please complete the Total column within the tables below. You should collect this information using the Audience Survey (which will be designed with support from the Hull 2017 team) and / or via the Participant Equal Opportunities Form provided in the Toolkit.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL** |  |  | **TOTAL** |
| **AGE GROUPS – AUD. & PART.** |  | **DISABILITY/LONG TERM ILLNESS – AUD. & PART.** |
| 0-2 years | 5,000 |  | Yes |  |
| 3-5 years |  |  | No |  |
| 6-10 years |  |  | Prefer not to say |  |
| 11-15 years |  |  | **CONDITIONS – AUD. & PART.** |
| 16-17 years |  |  | Learning disability |  |
| 18-19 years |  |  | Long-term illness/condition |  |
| 20-24 years |  |  | Sensory impairment |  |
| 25-29 years |  |  | Mental Health condition |  |
| 30-34 years |  |  | Physical impairment |  |
| 35-39 years |  |  | Cognitive impairment |  |
| 40-44 years |  |  | Other |  |
| 45-49 years |  |  |  |  |
| 50-54 years |  |  |  |  |
| 55-59 years |  |  |  |  |
| 60-64 years |  |  |  |  |
| 65-69 years |  |  |  |  |
| 70-74 years |  |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say |  |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL** |  |  | **TOTAL** |
| **GENDER - AUDIENCES** |  | **ETHNICITY – AUDIENCES** |
| Male |  |  | Welsh/English/Scottish/Northern Irish/British |  |
| Female |  |  | Irish |  |
| Transgender |  |  | Gypsy or Irish Traveller |  |
| Other |  |  | Any other White background  |  |
| Prefer not to say |  |  | White and Black Caribbean |  |
|  |  |  | White and Black African |  |
|  |  |  | White and Asian |  |
|  |  |  | Any other Mixed/multiple ethnic background  |  |
|  |  |  | Indian |  |
|  |  |  | Pakistani |  |
|  |  |  | Bangladeshi |  |
|  |  | Chinese |  |
|  |  |  | Any other Asian background |  |
|  |  |  | African |  |
|  |  |  | Caribbean |  |
|  |  |  | Any other Black/African/Caribbean background  |  |
|  |  |  | Arab |  |
|  |  |  | Any other ethnic group  |  |
|  |  |  | Prefer not to say |  |

**Thinking about your project as a whole, what would you say have been the main successes and challenges for your audience members / participants:**

**This can include formal and informal feedback given to you by staff and / or your own observations. You can use comments books; informal conversations; emails; etc. to inform this. It must also include any findings from your Audience/Participant Survey (A Question Bank is provided for the Audience/Participant Survey, from which you will build your own project questionnaire with support from Hull 2017 staff).**

1. **Online Engagement**

 **How did your project impact upon your online presence?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL PAGE VIEWS** | **UNIQUE PAGE VEIWS** |
| Website views relating to project |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **LIKES/FOLLOWERS AT START** | **LIKES/FOLLOWERS AT END** | **IMPRESSIONS ON POSTS RELATING TO THE PROJECT** | **ENGAGEMENTS WITH POSTS RELATING TO THE PROJECT** |
| Facebook |  |  |  |  |
| Twitter |  |  |  |  |
| Instagram |  |  |  |  |
| Other |  |  |  |  |

**DEFINITIONS**

* **Followers include:** Facebook Page Likes / Profile Friends; Twitter Followers; YouTube Subscribers; etc.
* **Impressions:** impressions (“views”) of Facebook posts linked to CCP project; impressions (“views”) of Twitter tweets linked to CCP project; views of YouTube videos linked to CCP project; etc.
* **Engagements:** Facebook posts, likes, shares, comments; Twitter tweets, retweets, likes; YouTube shares, comments; etc.

**In the boxes below, please share a selection of audience comments or quotes from social media made about your project. Please provide different examples to those in your Project Update Report:**

1. **Partners**

**How many partners were involved with the project?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL BASED IN** **HU1 – HU9** | **TOTAL BASED OUTSIDE** **HU1 – HU9** |
| **PARTNER TYPE**  |
| Artistic partner (e.g. theatre, art gallery, music venue) |  |  |
| Heritage partner (e.g. museum, archive) |  |  |
| Funder (e.g. Arts Council England, business, private trust) |  |  |
| Public Sector partner (e.g. libraries, GPs) |  |  |
| Voluntary sector partner (e.g. community group, charity) |  |  |
| Education (e.g. school, college, university) |  |  |
| Other |  |  |
| **PARTNERSHIP STAGE** |
| Number of new partnerships established via this project |  |  |
| Number of existing partners involved in this project |  |  |

**Thinking about your project as a whole, what would you say have been the main successes and challenges for your partners:**
**This can include formal and informal feedback given to you by staff and / or your own observations. You can use notes or minutes from partner meetings; informal conversations; emails; etc. to inform this.**