## PID
Project name | Slung Low: The Flood
Last updated | 10.03.2016 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience
Project plan | Draft |  | Risk management plan |  |  | Pending |  | Hull residents |  | Y
Budget | Draft |  | Marketing & comms plan |  |  | Pending |  | regional |  | Y
[8 empty] | national |  | Y
Dates | [7 empty] | international |  | Y
Project start date | 2016-04-18 |  | Project live date |  | 2017-02-01 |  |  | children (<16)
End of Live date | 2017-10-31 |  | End of eval. date |  | TBC |  |  | young people (16-25) |  | Y
[8 empty] | families |  | Y
Categories | [7 empty] | older people (60+)
Type | Hull 2017 Commission |  |  | Strand |  | Slung Low |  | self-identify as disabled
Season | Made in Hull |  |  | Digital requirements |  | Very high |  | BME
NEET
Finance | [6 empty] | # temporary jobs created
Total project budget |  | 400000 |  |  |  |  | # freelance contracts created
Hull 2017 contribution |  | 400000 |  |  |  |  | # participation opportunities
Analysis/project code(s) | [6 empty] | of which for school age
# commissions
[7 empty] | Objective |  | Met? | Notes
To produce a high quality, large scale outdoor/site sepcific performance.
People | [6 empty] | To engage a large community cast.
Project Lead | Slung Low |  |  | Volunteering lead
Producer | Katy Fuller |  |  | Education lead |  |  | To produce an online story and film and tour this around the city.
Assistant Producer | Martin Atkinson |  |  | Marketing lead
Production Manager |  |  |  | Community Eng lead
Evaluation lead
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
Slung Low will be ultimately responsible for the delivery of this project. Hull2017 will assist in terms of marketing and comms assistanace and venue support. However, all production elements will be provided by Slung Low as outlined in the budget. James Phillips is writing the script and Alan Lane is directing. | [6 empty] | 27 Feb - 5 March 2017: Video Prologue: Released and projected on to the Slung Low Caravan at 7 different locations in the city. Very short film, on loop for an hour at these locations, listened to on Slung Low headphones. Not ticketed. Free. 12 - 16 April 2017: Performance of Part 1 for 400-600 people. Ticketed but free. This might extend by a week if demand requires it to. July and early August 2017: Slung Low enbark on releasing more digital content through Facebook profiles and online narratives. All digital, no physical production or tickets required. End of Spetember/October 2017: Final performance of The Flood. Date not yet confirmed.
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
Procurement should be excluded for a large part of the project budget because "the procurement is a unique work of art or artistic performance." Elements of the process might require procurement once we establish the infrastructure for performance. | [6 empty] | 100 community cast will be recruited for part 2 of The Flood in September/October. Recruitment will start at the beginning of May with participatory sessions starting at the beginning of June 2017.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
Slung Low: Joanna Resnick - joanna.slunglow@gmail.com; Laura - lauraslunglow@gmail.com
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
1 March - April 16 2017: 10 volunteers to assist with rehearsals and making. April 10 - 16 2017: Performances will be Wednesday 12 April - Sunday 16 April 2017 and 25 volunteers per performance over these evenings Front of House to make sure audience members know where they are going. The 10 & 11 April are likelty to be rehearsals and it would be useful if volunteers could make both or one of these days. | [6 empty] | In Hull a young woman has been waiting outside the Great House of the Lady Mayor- guardian of the status quo- everyday since the rains began. She does not know her own name. She sees visions. She dreams of the end of the world, of a city sinking. She has the word Gloriana tattooed on her left arm. Is she an immigrant, one of the great wave crashing onto British shores as the result of foreign wars? A runaway? A protestor with a particular, hidden agenda? Slung Low present this World Premiere of The Flood, a site specific and online performance. The Flood: Part One will take place on Wednesday 12 April - Sunday 16 April 2017. After this you can follow the story online. The story will culminate in The Flood: Part Two, a large scale site specific performance, with a cast of over 100 performers.
Version control
Date | Changes and/or approvals
12.04.2016 | Martin A
Note on Q17: Direct employee of Hull 2017 or partner organisation
Note on Q18: Including creative teams etc
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize