|  |  |  |  |
| --- | --- | --- | --- |
|  | **Greatfield 60 Years On – Production Schedule** | | |
| **Dates** | **Activity** | **STATUS** | **NOTES** |
|  |  | COMPLETE / ON-TIME / BEHIND |  |
| Aug. – Dec. 2016 | Planning for and delivery of **community TV production course** in partnership with Estuary TV |  | We were unsuccessful with an external application for this aspect of the project. We are currently looking at alternatives. WEA appears to be the best option. Estuary TV have support us with new reporting. |
| January 2017 | Opening of pop-up-gallery. Launch event and promotion of **Greatfield 60 Years On** including introducing plans for a community garden and other environmental works for Greatfield.  First community TV shorts screenings. Start weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 1**  –About Greatfield famous son Mick Ronson | Complete | Launch event (27th January 2017) Gallery open with **Beginnings exhibition** and good response to the first exhibition. Garden project begin at 2 venues on the estate. ‘Creativity Begins at Home’ (now ‘Crafty Cuppa’), ‘Family Fun’ and ‘Greatfield Quilt’ sessions happening weekly.  ‘Turn and Face the Strange’ Mick Ronson Story-gathering workshop took place on 10th Feb also ‘This is Your Life’ oral history workshop (20th Feb). |
| February 2017 | Begin to build curated collection of Greatfield photographs to be displayed at the pop-up gallery.  Weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 2** | Complete | ‘Greatfield Wall’ of donated photographs it looking amazing already.  Teatime Talk – ‘Afternoon at the Soaps’ Marvin Close. |
| March 2017 | **Recruitment of volunteers and participants** for ‘Art in a Cart’ workshops.  Workshop planning/materials purchased.  TV shorts screenings. Weekly ‘Creativity begins at Home’ workshops  **Teatime Talk 3** | Complete but no ‘TV shorts’ screening or teatime talks | Art in a Cart recruitment and schedule produced. Materials bought and ‘cart’ created.  Weekly sessions continue.  New session ‘Big Local pop-in’ to start 15th March 2017 and take place every Wednesday. |
| April - May 2017 | Delivery of **‘Art in a Cart’ workshops** at sites around Greatfield throughout April and May. Exhibition of ‘Boxes of Beauty and Hope’ at the pop-up gallery. Weekly ‘Creativity begins at Home’ workshops  Teatime Talk 4-5 | Complete but only 1 x tea time talk | **‘In Your Words’ multimedia presentation opens 24th April**  10 x Art on a Art sessions delivered at venues across the area . 134 workshop participants.  **‘Boxes of Beauty and Hope exhibition opened on 22th May.**  Crafty Cuppa workshops continue but move to St Stephens Neighbourhood Centre  Weekly Greatfield Quilt sessions continue and Greatfield Choir now meeting regularly at St Hilda’s  ‘Lest We Forget’ Hull Community Theatre performance (Teatime talk) |
| June 2017 | **‘Freedom from Worry’ carnival costume** **workshop**s delivered with local schools and community groups.  TV shorts screenings. Weekly ‘Creativity begins at Home’ workshops  Teatime Talk 6 | Complete  No teatime talk | Crafty Cuppa workshops continue but move to St Stephens Neighbourhood Centre  School carnival workshops begin  Photography workshop 8th June (WEA) |
| July – September 2017 | **Planning, preparation and promotion** of Street Party event  **Street Party** with screenings, family activities, carnival costume parade and dance performances.  Weekly ‘Creativity begins at Home’ workshops  Teatime Talk 7-9 | Complete but no tea time talks as church is closed during the summer holidays | ‘**Creative Aspirations’ exhibition** opens 3rd July and runs until 2nd August  2 x ‘mini’ carnival’ events at primary schools  Street party planning and delivery (15th July) with carnival arts and choir performance  Planning for ‘Nature’ and ‘Greatfield Brides and Grooms’ exhibition  Planning for end event  3 x Teatime talks planned before December  Gallery to reopen on 4th September with ‘Nature’ exhibition.  ‘Greatfield Bride and Grooms’ to open on 30th September  WEA course in photography and film making to start if there is take up |
| October - December 2017 | **End party will act as official launch** of new community garden/environmental works for Greatfield including new permanent artworks/art trail.  Weekly ‘Creativity begins at Home’ workshops.  **Exhibition of photography** done through the year.  TV shorts screenings  **Teatime Talk 11-12** |  |  |
| January – February 2018 | **Evaluation** of Greatfield 60 Year On including continuation plans. |  |  |