**update 20th July 2016**

**Creative**

James is currently writing first draft.

Core Slung Low creative team of composer, choreographer, sound designer, designer and writer have all been booked. Other recruitment will take place throughout Autumn and early 17.

A research assistant has been commissioned to undertake a series of research tasks to support James in his first draft completion.

**Production**

Safety Boat Training is planned for Autumn.

**Crew/Casting**

Stage managers are pencilled and undergoing a skills refresher courses

**Locations**

We've hired and tasked an Associate Producer to explore and report on potential sites, headquarters and accommodation.

Further exploratory visits in Hull are scheduled for mid August and early September.

**Marketing**

Copy has been supplied

**Financial**

N/A

**Digital**

Work on an application to Space is underway. Awaiting info from Hull17 on audiences to submit.

Through to feasibility round of BBC Live programme.

**Other**

A research trip to Calais' refugee camp is scheduled for 21st July with members of the core creative team.