**LOGG**

**On site days**

FULL DAY 29th August – Joshua get-in

FULL DAY 30th August – Joshua get-in

FULL DAY 31st August – Joshua live. Scottee get in begins

FULL DAY 1st September - Scottee get-in

(2nd September – Scottee live. Half day) possibly not needed

(4th September – Scottee get-out) – prob not needed.

FULL DAY 5th September – Joshua get-out. Plus get-in of interior rig for Mcguires.

HALF DAY 7th September – McGuires get-in. If they get here on time. Half-day

HALF DAY 8th September – Mcguires get-in. Half-day

HALF DAY 9th September – McGuires live. Try for half day

HALF DAY 10th September – Mcguires live. Try for half day

HALF DAY 11th September – Mcguires Live, then get-out. Try for half day

FULL DAY 22nd September – Periplum prep day?

HALF DAY 23rd September – Periplum live. Half day

FULL DAY 27th September – accomm only?

FULL DAY 28th Sept – Dominic at market. Thor. Periplum prep

FULL DAY 29th Sept – Dominic and Thor (full get-in). Periplum live too.

(30th Sept- probably not needed)

FULL DAY 1st October – Thor get-out

FULL DAY 2nd – possible Periplum culmination

This adds up to 11 days 6 half days.

11 X £350 = £3850

6 X £200 = £1200

**Office/meeting days**

Meeting on 10th

Meeting 15th

Meeting / working in Hull day 17th

Meeting / working in Hull day 24th

5 additional office days

= 9 days @ £250 = £2250

TOTAL = £7300

+

PDs @ £20? For 12 days = £240

Mileage 11 return journeys = attempt to get this thrown in with the fee. Otherwise £660.

On top of this I would need accommodation for 11 nights