## Budget
Thursday 7 December
Budget
Venues
Fruit | 500
Hull Minster | 450
Warehouse | 400
Vue |  | in film budget
Content
For Luke
Production
Aidan
Estimate | 10000
Marketing
Design flyers for delegates | 500
Capture on the day (Photographer) | 600
Flyer design/print | 350
Intercity advertising (Poster sites) | 1000
EDM (with data from others) | 500
Other | 1500
Catering
Breakfast | 600 | £3 x 200
Lunch | 2000 | £10 x 200
Total | 18400
Total Budget | 35000 | Dependant on what Luke has spent already
Remaining | 16600

## Timeline
Timeline
2017-07-24
2017-07-31 | Venues confirmed
2017-08-07 | 1/3 of partners in place/Sessions confirmed.
2017-08-14 | Website complete on Hull2017 site
List of key attendees drawn up
2017-08-21 | Budget complete
2017-08-28
2017-08-30 | Hull 2017 Programme Announcement
At least half of the sessions announced and partners in place
Invites land to key attendees
Tickets on sale
2017-09-04
2017-09-11
2017-09-18
2017-09-25
2017-10-02 | Guardian or Boiler or Vice Panels announced in the Guardian.
2017-10-09
2017-10-16
2017-10-23
2017-10-30 | Full programme for Substance announced. Including weekend.
2017-11-06
2017-11-13
2017-11-20
2017-11-27
2017-12-04
2017-12-11
2017-12-18
Questions
When are we going to schedule press interviews/activity?
Next City of Culture to be announced as part of Substance???

## Partners
Partner | Chasing
The Guardian | Luke
Jeremy at Radio 3 | Martin intro and Luke follow up
Vice/Noisy

## Schedules
Thursday 7 December
Main Space Panels/Provocations/Keynotes
Time | Venue | Title of Panel | Speaker | Chair | Panelist 1 | Panelist 2 | Panelist 3 | Panelist 4 | Panelist 5
9:00 | Butler Whites/Church | Welcome
10:00 | Hull Minster | Keynote 1
11:00 | The Warehouse | Session 1
12:00 | Fruit | Session 2
13:00 | Lunch
14:00 |  | Session 4
15:00 |  | Session 5
16:00 |  | Session 6
17:00 | Break
18:00 | Summing Up | Hull Minster/Fruit
18:30 | Sessions end
20:00 | Fruit | Performance
Smaller Break Out Discussions
Time | Venue | Title of Session | Speaker
10:30
11:30
12:30
13:30
14:30
15:30
16:30
17:30