## Timeline
Slung Low: The Flood
|  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2016-10-01 |  |  |  | 2016-11-01 |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01
Activity | Lead | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Contract | Katy | bar: 2016-04-01 3
Comission Scripts | Slung Low | bar: 2016-04-01 3
Sign off detailed budget with Slung Low | Katy | bar: 2016-04-01 3
Secure Core Team | Slung Low | bar: 2016-04-01 3
PID signed off | Martin A/Katy | bar: 2016-04-01 3
HQ Selection | Slung Low/Katy | bar: 2016-09-01 1
London Meeting: Core Creative Team | Slung Low/Katy | bar: 2016-09-01 2
First draft script delivery | Slung Low: James Phillips | bar: 2016-10-01 1
Confirm Performance Sites | Katy/Slung Low/Tech | bar: 2016-08-01 1
Full Team Meeting | bar: 2016-11-01 1
Delivery Begins: Company On Site | Slung Low | bar: 2017-02-01 1
Make Digital Prologue | bar: 2017-02-01 2
Digital Prologue Projected on Caravan around the city for 7 days | bar: 2017-02-01 4
Recruit Community Cast | Slung Low/Marketing | bar: 2017-05-01 1
Rehearsing/Creating Part 1 | Slung Low | bar: 2017-03-01 1 to 2017-04-01 1
Performance of Flood Part 1 | Slung Low/Katy | bar: 2017-04-01 2
Recruitment for Part 2 of the Flood | bar: 2017-05-01 1
Create "Previously on The Flood" video | bar: 2017-05-01 2
Start Participatory sessions | bar: 2017-06-01 1 to 2017-07-01 4
Create the story that fits between live shows online | bar: 2017-07-01 3 to 2017-08-01 1
Rehearsals for The Flood: Part 2 Begin | bar: 2017-08-01 1 to 2017-09-01 2
Final performances of The Flood | bar: 2017-09-01 3 to 2017-09-01 4