**CREATIVE PARTNERS**
**END OF PROJECT REPORT**

**GENERAL INFORMATION**

|  |  |
| --- | --- |
| **ORGANISATION NAME:** | Hull 2017 |
| **PROJECT NAME:** | Epicycle |
| **MAIN CONTACT:** | Pippa Gardner |
| **REPORT SUBMISSION DATE:** | September 2017 |

**INTRODUCTION**

Everyone who receives funding from Hull UK City of Culture 2017 Ltd. must complete an end of project report, to inform us how they did against the agreed deliverables in their Agreement and Project Schedule. We recommend you read it straight away, as you will need to collect the information throughout your project.

We have done our best to ensure that the information being asked for already reflects the output data that you are collecting for other funders. However, due to the specific nature of this funding there are some additional outputs to be measured. This is due to the nature of our own funding agreements, and the need for us to provide certain evidence to these funders.

This end of project report tells us:

* What has happened during your project as a whole
* Your final income and expenditure figures
* What you have learned from the project, how you have adapted to these learnings, and what you plan to do with this learning in future.

We will send you a separate survey about the outcomes and impact of your Hull 2017 supported project separately. We will process the information you give us to understand:

* The overall effect of our grant and support;
* The overall effectiveness of our services and grants administration; and
* What the key things are that the city needs to be aware of in future, in terms of supporting the arts and culture sector.

We also use this information to report to our funders.

Please email this activity report to: [insert Hull contact]@hull2017.co.uk

**NB: Please note that these reporting templates have been designed to try and account for all different types of creative partner. As a result, there will be rows within the data tables that are not applicable to your organisation. If this is the case, please just leave these rows BLANK.**

**GLOSSARY OF TERMS**

* **Commission -** the hiring or payment to an artist / artistic company to create a new art work, project or performance. A commission can be wholly or partly funded by you / your organisation.
* **Participant opportunities** – workshops, classes, courses, engagement projects for members of the public (i.e. not including school’s engagement, artist development or staff training opportunities).
	+ **Workshops and classes**: individual occurrences of a workshop / class, even if it is the same one being delivered, e.g. the same contemporary dance workshop led by Hull Dance, delivered at 3 different venues or 3 times in a day, is 3 opportunities.
	+ **Courses and engagement projects**: a series of classes, workshops, activities, etc. where the same group of participants take part for the duration, and it is progressive in nature, e.g. a group of 8 circus skills classes to introduce participants to a range of acrobatic skills (once a week for 8 weeks), attended by the same 10 participants OR a community cast recruited to develop, rehearse and perform a drama.
* **School’s engagement opportunities –** as above, but organized formally with schools.
* **Artist development opportunities** – includes residencies, structured schemes, seed commissions, professional or industry advice, showcase opportunities, associate artist schemes, etc.
* **Staff training opportunities** – including formal training and development programmes, attendance at industry conferences and seminars, professional leave, work shadowing, mentoring, etc.
* **Audience** - those attending an exhibition or performance, and people getting access to work that is printed, recorded, broadcast or on the internet.
* **Participant** – those taking part in doing an activity.

 **OTHER INFORMATION**

In addition to these reports, we will also send each project lead, links to an online survey:

* **Survey 1:** The first survey will be sent in April 2017 and will seek to ask a few key questions, linked to the outcome areas we are measuring within the overall evaluation for Hull 2017, as well as ones about how we are performing in our role as your partner. This is so we can learn from your feedback and make necessary changes where improvements need to be made.
* **Survey 2:** This will be sent at the end of the agreement period with you, and will again ask a few key questions linked to the outcome areas we are measuring within the overall evaluation for Hull 2017; as well as any key learnings for Hull’s cultural sector beyond 2018 and future cities of culture.

A number of partners will also be contacted by our external evaluators to take part in in-depth interviews, which seek to explore the above in more detail.

1. **PROJECT REPORT**

Please attach the final versions of the listed documents (where applicable to your project). Please check the box to indicate that the document has been provided:

|  |  |  |
| --- | --- | --- |
| **DOCUMENTS** | **PROVIDED** | **N/A** |
| * Delivery Plan
 | [ ]  |  |
| * Budget
 | [ ]  |  |
| * Marketing & Communications Plan
 | [ ]  | [ ]  |
| * Learning & Engagement Plan
 | [ ]  | [ ]  |
| * Risk Register
 | [ ]  | [ ]  |

1. **MONITORING & EVALUATION REPORT**
2. **ACTIVITY**

**Overall, how did you do reaching the targets laid out in your agreement? Where the row is not applicable, please leave BLANK.**

**\* Target: target(s) listed within your agreement with Hull UK City of Culture 2017**

**\*Actual: final figures for your project**

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL** |
| **ACTIVITY** |
| **COMMISSIONS** |
| No. of commissions |  | 0 |
| No. of commissions inspired by history / heritage |  | 0 |
| **PRODUCTIONS AND PERFORMANCES** |
| No. of productions or co-productions |  | 0 |
| No. of productions or co-production performances |  | 0 |
| No. of productions or co-productions on tour |  | 0 |
| No. of visiting company productions |  | 1 |
| No. of visiting company production performances |  | 2 |
| No. of productions inspired by history / heritage |  | 0 |
| No. of accessible performances |  | 0 |
| **EXHIBITIONS AND SCREENINGS** |
| No. of exhibitions |  | 0 |
| No. of exhibitions on tour |  | 0 |
| No. of exhibition days |  | 0 |
| No. of exhibitions inspired by history / heritage |  | 0 |
| No. of access provisions |  | 0 |
| **FILMS** |
| No. of films |  | 0 |
| No. of films on tour |  | 0 |
| No. of screenings |  | 0 |
| No. of films inspired by history / heritage |  | 0 |
| No. of accessible screenings |  | 0 |

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL**  |
| **ACTIVITY** |
| **FESTIVALS & MUSIC EVENTS** |
| No. of festival days  |  | 0 |
| No. of artists / groups / companies programmed |  | 0 |
| No. of performances |  | 0 |
| No. of shows inspired by history / heritage |  | 0 |
| No. of accessible performances during festival |  | 0 |
| **LEARNING AND PARTICIPATION** |
| No. of participant opportunities\* (in-house) |  | 0 |
| No. of participant opportunities\* (outreach) |  | 0 |
| No. of school’s engagement opportunities\* (in-house) |  | 0 |
| No. of school’s engagement opportunities\* (outreach) |  | 0 |
| No. of artist development opportunities\* (in-house) |  | 0 |
| No. of artist development opportunities\* (outreach) |  | 0 |
| No. of staff training opportunities\* (in-house) |  | 0 |
| No. of staff training opportunities\* (outreach) |  | 0 |
| No. of opportunities exploring history / heritage |  | 0 |
| No. of opportunities to build historical / heritage-based skills or knowledge |  | 0 |
| No. of accessible learning and participation activities |  | 0 |

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL**  |
| **ACTIVITY VENUES/LOCATIONS** |
| No. of activities delivered in HU1 – HU9 |  | 1 |
| No. of activities delivered outside of HU1 – HU9 |  | 0 |

Please provide a short description of the additional activities delivered, since your last update report in the box below:

***Hull 2017 presents a mesmerising performance from internationally acclaimed French circus artists, CirkVOST.*** *Enter the circular universe of*Epicycle*. Drawing inspiration from European comics,*Epicycle *will take you on a rollercoaster journey through the lives of the inhabitants of a strange new world. Watch the ‘Cyclonauts’ as they perform breath-taking aerial acrobatics within a metal circle of immense scale. Featuring members of the legendary flying company Les Arts Sauts and directed by renowned choreographer and aerialist John-Paul Zaccarini, this spectacular display of aerial and acrobatic feats plays on and around the astounding metal structure.* Epicycle *will conjure the rhythm of the lives of its inhabitants in electrifying, heart-stopping style.*

If any of the above has been inspired by, explored, or built skills and knowledge in history / heritage (especially that linked to Hull’s past), please briefly explain how below.

N/A

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of the activity delivered (approximately 500 words):

See project team debrief notes.

1. **ADDITIONAL CAPACITY TO DELIVER YOUR PROJECT**

**In the table below, please enter the total number of additional people contracted by your organisation to make this project happen. The totals provided below should not include your core team who will be accounted for in the ORGANISATIONAL END OF YEAR REPORT (where applicable).**

**Some roles / work areas have been provided. However, please insert new roles into the table for anything not accounted for.**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **TOTAL NO. INDIVIDUALS**  | **TOTAL NO. WHO ARE HULL RESIDENTS** | **TOTAL NUMBER OF DAYS WORKED** |
| **CATEGORY OR ROLE** |
| **CORE CREATIVE TEAM (PRODCUTION / EXHIBITION SPECIFIC)** |
| Co-Director | 0 | 0 | 0 |
| Co-Producer | 0 | 0 | 0 |
| Other Production (please specify) | 4 | 0 |  |
| Artist / Performer | 8 | 0 |  |
| Other Creative (please specify) | 0 | 0 | 0 |
| Co-Curator | 0 | 0 | 0 |
| Other Curatorial (please specify) | 0 | 0 | 0 |
| Please specify:[Insert other production, creative or curatorial here]  |
| **OTHER** |
| Other | 0 | 0 | 0 |
| Please specify:[Insert other here] |

**In the tables on this and the following page, please enter the number of people contracted to make this project happen, who fall into each of the equal opportunities categories listed. If you do not know please leave this blank.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL** |  |  | **TOTAL** |
| **AGE GROUPS – DELIVERY TEAM** |  | **DISABILITY/LONG TERM ILLNESS – DELIVERY TEAM** |
| 16-17 years |  |  | Yes – limited a lot | 8% |
| 18-19 years |  |  | Yes – limited a little |  |
| 20-24 years |  |  | No | 58% |
| 25-29 years | 8% |  | Prefer not to say | 34% |
| 30-34 years | 8% |  | **CONDITIONS – DELIVERY TEAM (NON-MANDATORY)** |
| 35-39 years | 42% |  | Learning disability |  |
| 40-44 years | 17% |  | Long-term illness/condition |  |
| 45-49 years |  |  | Sensory impairment |  |
| 50-54 years |  |  | Mental Health condition |  |
| 55-59 years |  |  | Physical impairment |  |
| 60-64 years |  |  | Cognitive impairment |  |
| 65-69 years |  |  | Other |  |
| 70-74 years |  |  | **ETHNICITY – DELIVERY TEAM** |  |
| 75+ years |  |  | Welsh/English/Scottish/Northern Irish/British | 8% |
| Prefer not to say | 25% |  | Irish |  |
| **GENDER - DELIVERY TEAM** |  | Gypsy or Irish Traveller |  |
| Male | 42% |  | Polish |  |
| Female | 17% |  | Any other White background | 50% |
| Transgender |  |  | White and Black Caribbean |  |
| Gender non-conf |  |  | White and Black African |  |
| Prefer not to say | 25% |  | White and Asian |  |
|  |  |  | Any other Mixed/multiple ethnic background  |  |
|  |  |  | Indian |  |
| **In the tables on this page, please enter the number of additional people contracted to make this project happen, who fall into each of the equal opportunities categories listed. If you do not know please leave blank. We recommend using the Equal Opportunities form provided in the Hull 2017 Reporting Toolkit to collect this information.** |  |  | Pakistani |  |
|  |  |  | Bangladeshi |  |
|  |  |  | Chinese |  |
|  |  |  | Any other Asian background |  |
|  |  |  | African |  |
|  |  |  | Caribbean |  |
|  |  |  | Any other Black/African/Caribbean background  | 8% |
|  |  |  | Arab |  |
|  |  |  | Any other ethnic group  | 8% |
|  |  |  | Prefer not to say | 25% |

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of the additional capacity brought in to deliver your activity? - **Please see results from your Artist & Creative Team Survey, provided in the Hull 2017 Reporting Toolkit.**

See project debrief notes.

1. **AUDIENCES**

**In total, how many people have attended your activities?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL**  | **% FROM HU1-HU9\*** |
| Number of audience members\* (in-house) | 6100 | 35.5% |
| Number of audience members on tour | N/A | N/A |

**\*The % from HU1-HU9 can be taken from the results of audience surveys or your box office reports.**
 **Please complete the Total column within the tables below.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **%** |  |  | **%** |
| **AGE GROUPS - AUDIENCES** |  | **DISABILITY/LONG TERM ILLNESS - AUDIENCES** |
| 0-2 years | 0% |  | Yes – limited a lot | 2% |
| 3-5 years | 0% |  | Yes – limited a little | 4% |
| 6-10 years | 0% |  | No | 91% |
| 11-15 years | 0% |  | Prefer not to say | 3% |
| 16-17 years | 1% |  | **CONDITIONS – AUDIENCES (NON-MANDATORY)** |
| 18-19 years | 2% |  | Learning disability |  |
| 20-24 years | 4% |  | Long-term illness/condition |  |
| 25-29 years | 7% |  | Sensory impairment |  |
| 30-34 years | 6% |  | Mental Health condition |  |
| 35-39 years | 9% |  | Physical impairment |  |
| 40-44 years | 14% |  | Cognitive impairment |  |
| 45-49 years | 11% |  | Other |  |
| 50-54 years | 12% |  |  |  |
| 55-59 years | 13% |  |  |  |
| 60-64 years | 10% |  | **Please enter the % of your audience for the project in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking a sample of your audience the Equal Opportunities questions from the Audience Question Bank, provided in the Hull 2017 Toolkit.**  |  |
| 65-69 years | 8% |  |  |  |
| 70-74 years | 2% |  |  |  |
| 75+ years | 1% |  |  |  |
| Prefer not to say | 2% |  |  |  |
| **GENDER** |  |  |  |
| Male | 31% |  |  |  |
| Female | 67% |  |  |  |
| Transgender | 0% |  |  |  |
| Gender non-conf | 0% |  |  |  |
| Prefer not to say | 2% |  |  |  |

|  |  |
| --- | --- |
|  | **%** |
| **ETHNICITY** |  |
| Welsh/English/Scottish/Northern Irish/British | 98% |
| Irish | 0% |
| Gypsy or Irish Traveller | 0% |
| Polish | 0% |
| Any other White background | 0% |
| White and Black Caribbean | 1% |
| White and Black African | 0% |
| White and Asian | 0% |
| Any other Mixed/multiple ethnic background  | 0% |
| Indian | 0% |
| Pakistani | 0% |
| Bangladeshi | 0% |
| Chinese | 0% |
| Any other Asian background | 0% |
| African | 0% |
| Caribbean | 0% |
| Any other Black/African/Caribbean background  | 0% |
| Arab | 0% |
| Any other ethnic group | 0% |
| Prefer not to say | 1% |

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of audience engagement and feedback for your project? - **Please see results from your Audience Survey, provided in the Hull 2017 Reporting Toolkit.**

The majority of audiences felt Epicycle was an enjoyable experience and gave everyone the chance to share and celebrate together and for over half of respondents it introduced them to contemporary circus for the first time. Opinion was split as to whether it showed them there is more to Hull then they expected, made them look at Hull’s public spaces in a different way or challenges their understanding of art. Whilst audiences rated the performance highly in terms of it being important that it is happening here in Hull and it being an interesting idea, the performance received quite low ratings across some of the other Arts Council Quality metrics (including being thought-provoking, having something to say about the world in which we live, and being absorbing and holding attention). Audience comments appreciated the skill of the performers, the performance being free and in a public place, the logistics of the site and the quality of the performance. However, others raised concerns about visibility and the length, pace and timing of the performance (especially for children).

Around a third attended because it part of Hull UK City of Culture 2017, but slightly more than a third stated they attended because it is a unique event not to be missed – making this the most popular response choice. This is a positive indication of a desire to attend similar events beyond the UK City of Culture title year.

Access provisions of blue badge parking, seating and toilets all received over 4.5/5 ratings on average from those who used them. The only area to improve in regards to access was to have a separate queue for entry to the accessible seating.

1. **TICKETS**

**Overall, how many tickets did you sell?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL** | **% TO** **HU1 – HU9 RESIDENTS** |
| **TICKET SALES** |
| Number of full price tickets sold | N/A | N/A |
| Number of concessionary tickets sold | N/A | N/A |
| Number of free tickets issued | N/A | N/A |
| Value of all ticket sales | £ | £ |
| **BOOKING TRENDS %** |
| Telephone | N/A | N/A |
| Counter  | N/A | N/A |
| Website | N/A | N/A |
| Post | N/A | N/A |
| Agency | N/A | N/A |
| ONLINE TICKET SALES |
| Number of tickets sold online | N/A | N/A |
| Value of tickets sold online | £ | £ |
| FRIENDS/MEMBERSHIP |
| New memberships | N/A | N/A |
| Membership renewals | N/A | N/A |
| Tickets purchased by members | N/A | N/A |
| Value of tickets bought by members | £ | £ |

1. **PARTICIPANTS**

 **In total, how many people have participated in your activities? If Hull 2017 are providing your Box Office function, please highlight this and we will download and complete this data.**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL**  | **% FROM HU1-HU9** |
| Number of participants\* (in-house) | N/A | N/A |
| Number of outreach participants | N/A | N/A |
| **TOTAL PARTICIPANTS** |  |  |

**\*The % from HU1-HU9 can be taken from the results of participant surveys or registration**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **%** |  |  | **%** |
| **AGE GROUPS - AUDIENCES** |  | **DISABILITY/LONG TERM ILLNESS – AUDIENCES** |
| 0-2 years |  |  | Yes – limited a lot |  |
| 3-5 years |  |  | Yes – limited a lot |  |
| 6-10 years |  |  | No |  |
| 11-15 years |  |  | Prefer not to say |  |
| 16-17 years |  |  | **CONDITIONS – AUDIENCES (NON-MANDATORY)** |
| 18-19 years |  |  | Learning disability |  |
| 20-24 years |  |  | Long-term illness/condition |  |
| 25-29 years |  |  | Sensory impairment |  |
| 30-34 years |  |  | Mental Health condition |  |
| 35-39 years |  |  | Physical impairment |  |
| 40-44 years |  |  | Cognitive impairment |  |
| 45-49 years |  |  | Other |  |
| 50-54 years |  | **Please enter the % of your participants for the project in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking your participants the Equal Opportunities questions from the Participant Question Bank, provided in the Hull 2017 Toolkit, or making these questions part of the registration process.** |  |  |
| 55-59 years |  |  |  |  |
| 60-64 years |  |  |  |  |
| 65-69 years |  |  | **Please enter the % of your audience in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking a sample of your audiences across the year the Equal Opportunities questions form the Participant Question Bank, provided in the Hull 2017 Reporting Toolkit.**  |  |
| 70-74 years |  |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say |  |  |  |  |
| **GENDER** |  |  |  |
| Male |  |  |  |  |
| Female |  |  |  |  |
| Transgender |  |  |  |  |
| Gender non-conf |  |  |  |  |
| Prefer not to say |  |  |  |  |
|  |  |  |  |  |
|  | **%** |
| **ETHNICITY** |  |
| English/Welsh/Scottish/Northern Irish/British |  |
| Irish |  |
| Gypsy or Irish Traveller |  |
| Polish |  |
| Any other White background |  |
| White and Black Caribbean |  |
| White and Black African |  |
| White and Asian |  |
| Any other Mixed/multiple ethnic background  |  |
| Indian |  |
| Pakistani |  |
| Bangladeshi |  |
| Chinese |  |
| Any other Asian background |  |
| African |  |
| Caribbean |  |
| Any other Black/African/Caribbean background  |  |
| Arab |  |
| Any other ethnic group |  |
| Prefer not to say |  |

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of participant engagement and feedback for your project? - **Please see results from your Participant Survey, provided in the Hull 2017 Reporting Toolkit.**

­­

1. **DIGITAL**

**Overall, how has your project impacted upon your online presence?**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **TOTAL PAGE VIEWS** | **UNIQUE PAGE VIEWS** | **AVERAGE TIME ON PAGE** |
| https://www.hull2017.co.uk/whatson/events/epicycle/ | **15435** | **12154** | **1min 45 sec** |
|  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **SUBSCRIBERS AT START OF PROJECT** | **SUBSCRIBERS AT END OF PROJECT** | **CLICK THROUGHS** |
| E-newsletter subscribers via project routes |  |  |  |
| SMS subscribers via project routes |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **LIKES/FOLLOWERS/SUBCRIBERS AT START OF PROJECT** | **LIKES/FOLLOWERS/SUBSCRIBERS AT END OF PROJECT**  | **IMPRESSIONS ON POSTS RELATING TO THE PROJECT** | **ENGAGEMENTS WITH POSTS RELATING TO THE PROJECT** |
| Facebook |  |  |  |  |
| Twitter |  |  |  |  |
| Instagram |  |  |  |  |
| Other |  |  |  |  |

**DEFINITIONS**

* **Followers include:** Facebook Page Likes / Profile Friends; Twitter Followers; YouTube Subscribers; etc.
* **Impressions:** impressions (“views”) of Facebook posts linked to project; impressions (“views”) of Twitter tweets linked to project; views of YouTube videos linked to project; etc.
* **Engagements:** Facebook posts, likes, shares, comments; Twitter tweets, retweets, likes; YouTube shares, comments; etc.

**In the boxes below, please share a selection of audience comments or quotes from social media made about your project:**

|  |
| --- |
| Sue Butler: [#epicycle](https://www.facebook.com/hashtag/epicycle?source=feed_text&story_id=10213746835614512) amazing performance. Atmospheric music, comedy and daring, what more could you want? [Video] |
| Rob Deyes: Epicycle West Park Last night. I'm not sure wether it was a good show or not because it was so dim I couldnt see a thing?!!?!?!?? |
| Sara Elvin-Rawe: [#epicycle](https://www.facebook.com/hashtag/epicycle?source=feed_text&story_id=1651804171556850)westparkGreat performance last night, sorry about the photo quality, the pics don't do it justice at all, was a great spectacle to see! |
| Emma Hardy: Epicycle acrobatics at West Park is just about to start! I'm with 2 very excited children! (And I admit I'm excited too)!https://static.xx.fbcdn.net/images/emoji.php/v9/f57/1/16/1f609.png😉https://static.xx.fbcdn.net/images/emoji.php/v9/fd2/1/16/1f604.png😄 |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |
|  |

**vii. PARTNERS**

**Overall, how many partners were involved with your project?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL BASED IN** **HU1 – HU9** | **TOTAL BASED OUTSIDE** **HU1 – HU9** |
| **PARTNER TYPE**  |
| Artistic partner (e.g. theatre, art gallery, music venue) | 0 | 0 |
| Heritage partner (e.g. museum, archive) | 0 | 0 |
| Funder (e.g. Arts Council England, business, private trust) | 0 | 0 |
| Public Sector partner (e.g. libraries, GPs) | 1 | 0 |
| Voluntary sector partner (e.g. community group, charity) | 0 | 0 |
| Education (e.g. school, college, university) | 0 | 0 |
| Other | 1 | 0 |
| **PARTNERSHIP STAGE** |
| Number of new partnerships established via this project | 0 | 0 |
| Number of existing partners involved in this this project | 2 | 0 |

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of your partnerships on this project? **- Please see results from your Partner Survey, provided in the Hull 2017 Reporting Toolkit.**

Please see project team debrief notes.