|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Hull & East Riding Institute for the Blind (HERIB) |
| **Name of Project** | A Sight to Behold |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |
| --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** |
| 1st February 2017 | 30th February 2017 | Recruitment of Project Co-ordinator.  Appointment of local artists and sculptors |
| 1st January 2017 | 1st March 2017 | Promote opportunities for visually impaired people to be engaged in the project. Engage with external partners – artists / Yorkshire Sculpture Park / regional local sight support charities |
| 1st March 2017 | 31st 15th April 2017 | Visit Yorkshire Sculpture Park & other appropriate venues  Hold workshops to discuss the sculpture to be developed / materials to be used / how each society is going to work on it separately and collaboratively |
| 15th April 2017 | 30th September 2017 | Develop sculpture working with local specialist artists |
| 1st May 2017 | 30th September 2017 | During this period finalise the sculpture, arrange to site the sculpture at the Hull Eye Hospital. Arrange a celebration event open to the public and unveiling of the sculpture within the Eye Hospital. |
| October – exact date tbc |  | Celebration event unveiling of the sculpture at the Eye Hospital |
| October 2017 onwards | Ongoing | Sculpture based in Eye Hospital for all visitors to experience (approximately 1000 patientsvisitors per week plus additional family members)  Potential to move the sculpture to Castle Hill Hospital where ~Lucentis eye injections are also administered in order for an additional number of patients to experience the sculpture |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances