## Sheet1
|  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2016-10-01 |  |  |  | 2016-11-01 |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01
Activity | Lead | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Project scoping and priorities. | Curated Place | bar: 2016-01-01 1 to 2016-01-01 4
Initial site visits and project meetings. | Curated Place | bar: 2016-01-01 1 to 2016-01-01 4
Identifying goals and objectives. | Curated Place | bar: 2016-01-01 1 to 2016-01-01 4
Research into additional funding. | Curated Place | bar: 2016-01-01 1 to 2016-01-01 4
Initial research new music commissions and artists. | Curated Place | bar: 2016-02-01 1 to 2016-03-01 4
Initial research electronic commissions and artists. | Curated Place | bar: 2016-02-01 1 to 2016-03-01 4
Venue scouting. | Curated Place | bar: 2016-03-01 1 to 2016-03-01 4
Presentation of potential acts and exec greenlight. | Curated Place / Sam Hunt | bar: 2016-04-01 1 to 2016-04-01 4
Pre-Production sign off. | Curated Place / Sam Hunt | bar: 2016-04-01 1 to 2016-04-01 4
Initial venue negotiation. | Curated Place | bar: 2016-04-01 2 to 2016-05-01 4
Confirmed venue negotiation. | Curated Place | bar: 2016-04-01 2 to 2016-05-01 4
Artists approached. | Curated Place | bar: 2016-04-01 2 to 2017-03-01 4
Headlines confirmed. | Curated Place | bar: 2016-04-01 2 to 2016-05-01 4
Initial headlines marketing copy developed (biog/desc/headshots). | Curated Place/ Hull 2017 Marketing Team | bar: 2016-04-01 2 to 2016-05-01 4
Tech reccie venues. | Curated Place | bar: 2016-04-01 2 to 2016-05-01 4
Document venue costs and benefits. | Curated Place | bar: 2016-05-01 1 to 2016-05-01 4
Venues pencilled. | Curated Place | bar: 2016-05-01 1 to 2016-05-01 4
Secondary programme confirmed. | Curated Place | bar: 2016-05-01 1 to 2016-05-01 4
Venue booked to move to contract. | Curated Place | bar: 2016-06-01 1 to 2016-07-01 1
Initial (secondary) marketing copy developed. | Curated Place/ Hull 2017 Marketing Team | bar: 2016-06-01 1 to 2016-07-01 1
Programme development. | Curated Place | bar: 2016-06-01 1 to 2017-03-01 4
All marketing copy signed off. | Curated Place/ Hull 2017 Marketing Team
Additional artist approaches. | Curated Place
Artists contracted. | Curated Place
Artist riders received. | Curated Place
Tech scoped and hired. | Curated Place
Logistics in place for all events. | Curated Place | bar: 2017-01-01 1 to 2017-07-01 1