**RIBA/LOOK UP 2017 COMPETITION**

Draft Programme v1 290116

 2016

 **Competition Launch/Issue Competitors Invitations**

Invites out: 23rd May (2 weeks) – up to 20 practices

 Accepted by: 3rd June

 Press Launch: w/c 6th June

 Briefs issued: w/c 6th June

 RFC’s : by 17th June

 EOI’s[[1]](#footnote-1) in: by 24th June

 Shortlist: Review & finalise by 1st July (1 week)

**Detail Design[[2]](#footnote-2)** (3 competitors)

 Commence: w/c 4th July (12 weeks)

 Submit: by 23rd September

 **Review Detail Designs & Select Winning Scheme**

 Commence: w/c 26th September (1 week)

 **Announce Winning Design** (delivery subject to consents)

 Commence: w/c 3rd October

 **Consents** (inc. planning)

 Commence: w/c 10th October (12 weeks)

 2017

**Consents secured**

By: 3rd January

 **Fabrication & Installation**

Commence: w/c 9th January

 Complete: w/c 26th June (25 weeks)

 **Public Launch & Display**

Launch: w/c 3rd July (to coincide with 2017 ‘Freedom’ season

Conclude: w/c 23rd October (extends beyond ‘Freedom’ to cover opening of Turner Prize Competition & potential activities around Stirling Prize.

1. Expressions of Interest to include statement re; form of architect/artist collaboration, outline concept (no more than 2 pages of visuals, 500 word rationale, detailed cv’s of design team [↑](#footnote-ref-1)
2. Submissions to include model, renderings, plans, material samples, written description, programme and approximation of costs (i.e. to establish reasonable degree of aesthetic, cost, programme and technical feasibility) [↑](#footnote-ref-2)