## Sheet1
ASWARM
Voice Park
Staff Rota
TUESDAY 19th SEPTEMBER |  |  | Event Manager | Volunteer Lead | Producer
8:00 | On site | TG | GH
| Power install | TG
| FOH build | TG
| 2x SIA on site | Prestige
18:00 | Finish
| Security changover | Prestige
WEDNESDAY 20th SEPTEMBER
8:00 | Security changeover | Prestige | GH
8:00 | Load at staples | ASWARM
08:00 - 18:00 | Build | ASWARM
18:00 | Security changeover | Prestige
THURSDAY 21st SEPTEMBER
8:00 | Security changeover | Prestige | GH
08:00 - 18:00 | Build | ASWARM
18:00 | Security changeover | Prestige
FRIDAY 22nd SEPTEMBER
8:00 | Security changeover | Prestige | GH
08:00 - 18:00 | Build | ASWARM
18:00 | Security changeover | Prestige
SATURDAY 23rd SEPTEMBER
8:00 | Security changeover | Prestige | GH
AM | Rehearsal | ASWARM
PM | Rig and Test | ASWARM
18:00 | Security changeover | Prestige
SUNDAY 24th SEPTEMBER
8:00 | Security changeover | Prestige | GH |  | LY, MM, EB
11:00 - 15:00 | Rehearsal - Volunteer performers | ASWARM
15:00 - 18:30 | Testing | ASWARM
17:00 | Volunteer Lead on site and briefed | Hull2107 |  | EJB
18:00 | Security changeover | Prestige
18:30 - 21:30 | Soft Launch | ASWARM
MONDAY 25th SEPTEMBER
8:00 | Security changeover | Prestige | GH
08:00 - 18:00 | Testing | ASWARM
18:00 | Security changeover | Prestige
TUESDAY 26th SEPTEMBER
8:00 | Security changeover | Prestige | GH |  | LY, MM, EB
14:00 | Volunteer lead on site | EJB |  | EJB
14:30 | FOH Volunteers arrive and briefed | EJB
15:30 - 21:30 | Open to public | ALL
18:00 | Security changeover | Prestige
WEDNESDAY 27th SEPTEMBER
8:00 | Security changeover | Prestige | GH |  | LY
14:00 | Volunteer lead on site | EJB
14:30 | FOH Volunteers arrive and briefed | EJB
15:30 - 21:30 | Open to public | ALL
18:00 | Security changeover | Prestige
THURSDAY 28th SEPTEMBER
8:00 | Security changeover | Prestige | GH |  | MM
13:00 - 14:00 | School 1 visit | MM, EB
14:00 - 15:00 | School 2 visit | MM, EB
14:00 | Volunteer lead on site | EJB |  | EJB
14:30 | FOH Volunteers arrive and briefed | EJB
15:30 - 21:30 | Open to public | ALL
18:00 | Security changeover | Prestige
FRIDAY 29th SEPTEMBER
8:00 | Security changeover | Prestige | GH |  | MM
14:00 | Volunteer lead on site | EJB |  | EJB
14:30 | FOH Volunteers arrive and briefed | EJB
15:30 - 21:30 | Open to public | ALL
18:00 | Security changeover | Prestige
SATURDAY 30th SEPTEMBER
8:00 | Security changeover | Prestige | GH |  | LY
11:00 | Volunteer lead on site | EJB |  | EJB
11:30 | FOH Volunteers arrive and briefed | EJB
12:00 - 21:30 | Open to public | ALL
18:00 | Security changeover | Prestige
SUNDAY 1st OCTOBER
8:00 | Security changeover | Prestige | GH |  | MM
11:00 | Volunteer lead on site | EJB |  | EJB
11:30 | FOH Volunteers arrive and briefed | EJB
12:00 - 21:30 | Open to public | ALL
18:00 | Security changeover | Prestige
MONDAY 2nd OCTOBER
8:00 | Security stand down | Prestige | GH
08:00 -18:00 | Derig | ALL