## LONE TWIN
LOGG 2016 ARTIST | LONE TWIN
Area of Hull | Longhill
Site Visit/s dates/times | 4th August
Workshop/other dates/times | n/a
Delivery dates/Times | 25th August to 3rd September
Budget agreed | Yes
Invoice received
Contract signed
Highlighted to ESAG | on August 11th
Framework doc agreed
Concept/Creative matters
Locations used | St Margaret's or East Mount Community Centre (see below)
Licensing/TEN
Permissions/Consent | see safeguarding below regarding covert recording
PRS / PPL required | n/a
Venue agreement | Either St Margaret's or East Mount Community Centre as a project hub to be set after site visit. Venue agreement required.
H & S matters
Enviro Health matters | n/a
Staffing matters | will the Visitor be accompanied at all times?
Volunteer request | request for 2 local volunteers in case local knowledge required. Sue Nicholson is a Pioneer from Longhill - 07834727438 - speak to Harriet/Shaun?
Security matters
Equipment matters
Power/light/matters
Access matters | aiming to include disabled person as participant with Visitor
Access Guide sent
Safeguarding matters | covert recording, waiver required but creative solution sought. Visitor alone and/or with child? Organised vs random schedule?
DBS docs checked
Environmental matters
Audience control matters
Emergency concerns
Insurance checked
Timeline okay
RA's checked
Marketing matters | No marketing required
M & E notes
Blog started by artist
Other detail required
Anlaby Unit use agreed | Not required by the company
Key contacts for project | Karen Okra link with Longhill
Production Manager notes

## SCOTTEE
LOGG 2016 ARTIST | SCOTTEE
Area of Hull | East, Holderness Road (TBC)
Site Visit/s dates/times | 1st completed - 2nd due on 15+16 August
Workshop/other dates/times
Delivery dates/times | 1 to 4 September (TBC - subject to securing venue)
Budget agreed
Invoice received
Contract signed | Molly has signed
Highlighted to ESAG | on August 11th
Framework doc agreed
Concept/Creative matters
Locations used | Holderness Road (TBC)
Licensing/TEN | Required
Permissions/Consent
PRS / PPL required | Need to establish if required
Venue agreement | Agreement with shop unit required
H & S matters
Enviro Health matters | Refreshments offered to public, so EH to be informed and standards upheld
Staffing matters
Volunteer request | None requested
Security matters
Equipment matters | We need to see a layout or designs for inside the unit. May need a toilet brought in if unit does not have it. Check venue has running water.
Power/light/matters | Power may need enhancing in venue. Artist supplies lighting.
Access matters
Access Guide sent | Sent out 26 July
Safeguarding matters | Policy required with regards children accessing the space.
DBS docs checked
Environmental matters
Audience control matters | How will they manage crowds outside, assuming it's popular?
Emergency concerns | Will need evac plan from shop unit
Insurance checked
Timeline okay
RA's checked
Marketing matters | This project needs marketing to achieve the numbers they're aiming for. Marketing Plan requested
M & E notes
Blog started by artist
Other detail required
Anlaby Unit use agreed | Not requested
Key contacts for project | Landlord/agent…
Production Manager notes

## DOMINIC
LOGG 2016 ARTIST | DOMINIC WILCOX
Area of Hull | Boothsferry/Gypsyville/Walton Street market
Site Visit/s dates/times | 1st completed
Workshop/other dates/times | Around 25-28 Sept (TBC) schools performances
Delivery dates/times | 25 & 28 September at Market (TBC), 28 Sept at Rokeby School (1-3pm)
Budget agreed | Requires re-working based on improvisors being included
Invoice received
Contract signed
Highlighted to ESAG | on 11 August
Framework doc agreed
Concept/Creative matters | Experienced improvisors required for performances at market & schoools.
Locations used | Walton Road Market. Primary schools in the west, Rokeby Primary confirmed, but seem flexible - Francis Askew-26th September - Wheeler Primary-any of dates
Licensing/TEN | May need licence (ask Events team for guidance) for performances at Walton St Market
Permissions/Consent
PRS / PPL required | n/a
H & S matters
Enviro Health matters
Staffing matters
Volunteer request
Security matters
Equipment matters
Power/light/matters
Access matters
Access Guide sent
Safeguarding matters
DBS docs checked
Environmental matters
Audience control matters
Emergency concerns
Insurance checked
Timeline okay
RA's checked
Marketing matters | Not required
M & E notes
Blog started by artist | Imminently
Other detail required | Performers to be sourced for improvised show in late September
Anlaby Unit use agreed | Requested
Key contacts for project | Roisha (schools), Walton St market contact…
Production Manager notes

## THOR
LOGG 2016 ARTIST | THOR / ASWARM
Area of Hull | Beverley Road
Site Visit/s dates/times | 1st completed
Workshop/other dates/times | 1st workshop complete. Returning early August (TBC) to record voices.
Delivery dates/times | 24-28 Aug proposed pop-up phone booths activity. 28 Sept-2 Oct for bus stop installation.
Budget agreed
Invoice received
Contract signed
Highlighted to ESAG
Framework doc agreed
Concept/Creative matters
Locations used | Bus stop on Beverley Road. Other locations for phone booth to be agreed
Licensing/TEN | May be required due to the performance nature of the activity around the woodburner/tea - not the sound installation necessarily.
Permissions/Consent | Req from JC Decaux (in progress), Council streetscene (in progress) - Kerry is warming up Ian from JCDecaux, Dave is warming up Andy W from KWL . Also Asda. Also locations for 'pop up' phone booth. Needs to secure permission from sources for content.
PRS / PPL required | n/a
H & S matters | Woodburner, hanging speakers, distractions from driving, crowds gathering,
Enviro Health matters | Offering free mint tea to audience
Staffing matters
Volunteer request | Requested - but need to confirm role as it is limited under Hull 2017 rules
Security matters | Possible overnight security to look after site
Equipment matters
Power/light/matters | self-contained power, lighting, etc - probably 12v
Access matters
Access Guide sent | sent 27 July
Safeguarding matters | Awareness required given the public nature of site
DBS docs checked | n/a
Environmental matters
Audience control matters | This project largely reliant on passing audience but some awareness raising required with groups/individuals involved in source material
Emergency concerns
Insurance checked
Timeline okay
RA's checked
Marketing matters | No marketing required
M & E notes
Blog started by artist | Imminently
Other detail required
Anlaby Unit use agreed | Requested
Key contacts for project | Council: Kerry Ryan (public transport), Graham Lownsborough (works), Dave Baines (street lights). JCDecaux: Ian.
Production Manager notes

## JOSHUA
LOGG 2016 ARTIST | JOSHUA
Area of Hull | North - North point Shopping Centre
Site Visit/s dates/times | 1st completed.
Workshop/other dates/times | 1st completed.
Delivery dates/times | 27 Aug - 5 September
Budget agreed | Yes
Invoice received | Yes - 1st & 2nd paid
Contract signed | Yes
Highlighted to ESAG | on August 11th
Framework doc agreed
Concept/Creative matters
Locations used | shop unit in North Point Shopping Centre, Bransholme
Licensing/TEN
Permissions/Consent | Venue agreement required.
PRS / PPL required | n/a music in background?
H & S matters | A cast of your nose (using the alginate that dentists use to make impressions of your teeth). It takes about 5 minutes.Waiver required (in a creative way) regarding possible allergic reaction, etc.
Enviro Health matters | A thermoformed plastic version of the nose is made from the cast, water is used and plastic residues are left in the water - the water will be sived, plastic discarded into recycleing and water dispossed in outside grate
Staffing matters
Volunteer request | Requested
Security matters | n/a (because within North Point Shopping Centre)
Equipment matters | Thermoforming machine gets hot, this will be set up behind a screen with a windo in so public can see but not touch the equipment (see design)
Power/light/matters | North Point covering costs
Access matters | Centre and unit accessible to customers
Access Guide sent | sent 27 July
Safeguarding matters | Detailed plan required as there is phyical touching. Age limit and/or adult/parent accompaniment arrangement to be agreed. Background checks on staff (Joshua has DBS - but to be checked)
DBS docs checked | Required from all staff - Joshua check is form Scotland?
Environmental matters | Water to be sived before emptied in outside grate
Audience control matters | booking system is it gets busy
Emergency concerns | Most of these will be in consultation with the shopping centre with their own Emergency arrangements
Insurance checked
Timeline okay
RA's checked
Marketing matters | Twitter used by the artist
M & E notes
Blog started by artist
Other detail required
Anlaby Unit use agreed | Not requested
Key contacts for project | NP Shopping Centre… Louise Smith
Production Manager notes

## D & K
LOGG 2016 ARTIST | DAVY & KRISTEN
Area of Hull | West - Old Bingo Hall, Anlaby Road
Site Visit/s/times | completed
Workshop/other dates/times
Delivery dates/times
Budget agreed | yes
Invoice received | 2016-08-11
Contract signed | yes
Highlighted to ESAG | 2016-08-11
Framework doc agreed
Concept/Creative matters
Locations used
Licensing/TEN
Permissions/Consent
PRS / PPL required
H & S matters
Enviro Health matters | Lighting & Sound
Staffing matters
Volunteer request
Security matters
Equipment matters
Power/light/matters
Access matters
Access Guide sent | sent 27 July
Safeguarding matters | N/A
DBS docs checked
Environmental matters
Audience control matters
Emergency concerns
Insurance checked
Timeline okay
RA's checked
Marketing matters
M & E notes
Blog started by artist
Other detail required
Anlaby Unit use agreed
Key contacts for project
Production Manager notes

## PERIPLUM
LOGG 2016 ARTIST | PERIPLUM
Area of Hull
Site Visit/s dates/times
Workshop/other dates/times
Delivery dates/times
Budget agreed
Invoice received
Contract signed
Highlighted to ESAG
Framework doc agreed
Concept/Creative matters
Locations used
Licensing/TEN
Permissions/Consent
PRS / PPL required
H & S matters
Enviro Health matters
Staffing matters
Volunteer request
Security matters
Equipment matters
Power/light/matters
Access matters
Access Guide sent
Safeguarding matters
DBS docs checked
Environmental matters
Audience control matters
Emergency concerns
Insurance checked
Timeline okay
RA's checked
Marketing matters
M & E notes
Blog started by artist
Other detail required
Anlaby Unit use agreed
Key contacts for project
Production Manager notes