## Apr 2017
STAFFING AREAS | Proposed 2017
| ROLE | NAME | ORGANISATION | RESPONSIBILITIES | ESTIMATED TIME COMMITMENT | Project cost
Project Management | Executive Producer | Katy Fuller | Hull 2017 - core team | Overall accountability for project delivery, reporting to Hull 2017 Chief Executive. |  | No cost to Project
| Project Manager | Sara Black | Hull 2017 - project specific. | Day to day project lead responsible for ensuring project is delivered on time and budget, liaising with all project sub-teams, coordinating project / production meetings, day to day budget management, liaison with Tate Project Manager | 3 days p/w Jan-Apr, f/t May-Oct, 3 days Nov-Jan. | In Project Budget
| Assistant Producer - Turner Prize | Lily Mellor | Hull 2017 - project specific | Supporting the Project Manager and wider Project Team administratively and ensuring that all Hull 2017 processes are adhered to. | Average 3 days per week May to Jan. | In Project Budget
| Finance / Accounts / legal |  | Hull 2017 - core team | back office support |  | No cost to Project
Curatorial | Ferens Curator of Art | Kirsten Simister | HCAL | To act as lead representative of Ferens at key meetings and events relating to Turner and provide usual curatorial expertise and overview | Average 1 day per week with increased commitment in period May to September | No cost to Project
| Curator 1 |  | Hull 2017 | To act as the key liaison point for two of the nominated artists each; researching nominated artists and writing citations; securing works for loan; planning and implementing all aspects of mounting the exhibition including transport, security and insurance arrangement, contributing to the exhibition catalogues and materials, liaising with Tate Lead Curator, providing a curator tour of the exhibition for the press. | f/t May - Oct. 2-3 days pw Nov-Jan. | In Project Budget
| Curator 2 | George Vasey | HCAL |  | f/t May - Oct. 2-3 days pw Nov-Jan. | No cost to project. Fee covered by HCAL
Installation / technical | Exhibition Designer | To be appointed | Hull 2017 | Planning and design of the exhibition spaces including structural calcs if required etc. | 30 days | In Project Budget
| Technical Manager | Phil Burton | HCAL | Overseeing pre-fabrication, installation and de-installation periods in liaison with the exhibition designer and curators | p/t June - Aug. f/t Sept for build / install and deinstall apart from in exceptional circumstances | No cost to Project
| Install Technicians x 4 | To be identified | HCAL? | Delivering the exhibition pre-fabrication, installation and de-installations | 3 weeks in & 1 week out @ 6 day weeks? To be developed as exhibition confirmed. | In Project Budget
| Specialist technicians | To be identified | HCAL? | As above | 10 days allowed | In Project Budget
| Conservator | To be identified | HCAL? | At KS advice | 4 days allowed | In Proect Budget
| Registrar | Caroline Rhodes | HCAL | Supporting the curators with the management of loans | 1 day p/w June - Sept and then Jan 17?? | No cost to Project
Venue / Events | Event Manager | Jenny Hutt | Hull 2017 - core team | Overseeing planning and delivery of special events including Press Preview, Opening and Awards Ceremony. | Average 2 days per week from July to December | No cost to Project
| Visitor operations manager | Hayley Killingbeck / Lorna Weston | HCAL | Management of invigilators and visitor assistants, facilitating group visits where appropriate (e.g. through education work), involvement in planing and delivery of special events in association with Event Manager. | To be discussed | No cost to project
| Invigilators / volunteer supervisors | To be identified | HCAL | Invigilation supervision, workng with teams of Hull 2017 volunteers | As per proposal | In Project Budget
| Visitor Assistants | To be identified | Hull 2017 and Ferens Volunteers | Public facing information role | As per proposal | No cost to project
| Merchandise Manager | To be discussed | HCAL (to be discussed) | Managing merchandise sales, stock take and reporting |  | No cost to project
| HCAL Event Staffing | To be identified | HCAL | Front of House, Technical | usual base numbers provided for events at City hall / Ferens | no cost to project
| Additional Event Staffing | To be identified | Hull 2017 | Front of House, Technical | As required by the event | In Project Budget
Comms & Audience Dev. | Communications Lead | Ben McKnight | Hull 2017 - core team | Lead on Communications strategy |  | No cost to project
| Specialist Visual Arts PR | Bolton & Quinn | Bolton & Quinn | Delivery of PR and additional coordination of Press Preview Event |  | No cost to project
| Marketing Lead | To be identified | Hull 2017 - core team | Planning and Delivery of Marketing Campaign |  | No cost to project
| Digital Lead | To be identified | Hull 2017 - core team | Planning and Delivery of Digital Campaign |  | no cost to Project
Learning & Engagement | Learning Lead 2017 | Ian Reed | Hull 2017 - core team | Together, the parties will develop the Learning and Engagement Plan for Turner Prize 2017 and agree the model for delivery and associated budget
| Engagement Lead 2017 | James McGuire | Hull 2017 - core team
| Learning Lead HCAL | Jane Avison | HCAL |  | To be agreed as budgetary implications | Some provision in Project Budget
| Engagement Lead HCAL | Malcolm Dunn | HCAL
Evaluation | Evaluation and Monitoring Manager | Elinor Unwin | Hull 2017 - core team | To develop and implement the evaluation and monitoring plan |  | No cost to project