## Sheet1
PROJECT PLAN
Dream.Think.Speak | v1
PRODUCTION
[6 empty] | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER
TASK | WHO | RESULT | DEADLINE DATE | CONSULTATION | NOTES | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
Apply for Premise License | CT | bar: MARCH 27
Receive technical information from commissioned work |  | Collated into Production Specification
Artists questionnaire sent | CT
Ensure all performers have their accommodation booked | CT
Collate ALL technical specifications into specifications for procurement | CT
Contract venues ??
Artists questionnaires chased and collated | CT | Production specification completed
Procurement of sound/light/projection |  | UNDER PROCUREMENT EXERCISE (____)
Accomodation confirmed and booked |  | Details to be included in Artists Packs
Procurement of stewarding/FOH management |  | 3x quotes from Framework??
Appoint Tech Supplier
Appoint FOH management
Appoint Local crew
Confirm schedule with get-in/out, tech, rehearsal |  | Agreed with tech supplier and venue
Confirm arrangements for catering/wefare |  | Once LX/Tech/FOH costs confirmed
Full production schedule produced |  | Including SM, Artist Liaison,
Production Meeting
Accreditation produced | CT/MM | To be included in Artists Packs | 2017-08-18 | bar: AUGUST 14
Produce stage managers notes |  | For cirulation with Production Schedule | bar: MARCH 20
Artists packs produced and sent | bar: AUGUST 21
SHOW 1 | bar: SEPTEMBER 4 to OCTOBER 2
Debrief